## Projects
City of Ann Arbor Capital Improvement Projects
Active or Programmed Only
ID | ProjectID | Project Name | Total Project Cost | Planning Area | Location | Department | Division | SubCategoryId | IdentifiedNeed | ScopeItems | Priority | CorridorComponent? | CorridorComponent | CorridorProjectName | Classification | Beneficial Impacts | Community Benefit | Public Engagement Anticipated? | Public Plan Review/CPC Approval Needed? | Schedule Justification | Planning Start Quarter | Planning Start Year | Planning End Quarter | Planning End Year | Planning $ Amount | Design/Acquisition Start Quarter | Design/Acquisition Start Year | Design/Aquisition End Quarter | Design/Acquisition End Year | Design/Acquisition $ Amount | Construction/Installation Start Quarter | Constructio/Installation Start Year | Construction/Installation End Quarter | Construction/Installation End Year | Construction/Installation $ Amount | Annual Operations Cost | Operations Increase/Decrease | Annual Maintenace Cost | Maintenance Increase/Decrease | Years in CIP | Operating Impact | Maintenace Impact | To be Completed By | Completed By | Date Completed/Updated | Project Completed? | Major Changes | SBP_Support | Current Budget | Actual Expenditures | MapImageName | Staff_With_Info1 | Staff_With_Info2 | Staff_With_Info3 | Staff_With_Info4 | Staff_With_Info5 | NeedSource_OutsideRequest? | NeedSource_OutsideRequest1 | NeedSource_OutsideRequest2 | NeedSource_OutsideRequest3 | NeedSource_OutsideRequestOther | NeedSource_Staff? | NeedSource_Staff1 | NeedSource_Staff2 | NeedSource_Staff3 | NeedSource_StaffOther | NeedSource_MasterPlan? | NeedSource_MasterPlan1 | NeedSource_MasterPlan2 | NeedSource_MasterPlan3 | NeedSource_MasterPlan4 | Status_CIP | Status_CPPT | Prioritization Model Score | Prioritization Model Rank | CPPT_Status Comment | CPPT_Project Contact | CPPT_Detail Scope items | CPPT_Public Engagement Strategy | CPPT_Complexity Scale | CPPT_Planning Start Date | CPPT_Planning Completion Date | CPPT_Design Start Date | CPPT_Design Completion Date | CPPT_Construction Start Date | CPPT_Construction Completion Date | CPPT_Complexity-Public Outreach | CPPT_Complexity-Multi-Disciplined | CPPT_Complexity-Multi-Agency | CPPT_Complexity-EnvironmentalIssues | CPPT_Complexity-CommunityImpactScope | CPPT_Complexity-MultipleFundingSources | CPPT_Complexity-LegalIssues | CPPT_Complexity-Other | CPPT_Complexity-SCORE | HRWCStormProject | C-PAN Responsible Unit | SRF | NoFundingPastFY | FileNumber | PlanBudget | PlanBudgetDate | DesignBudget | DesignBudgetDate | ConstBudget | ConstBudgetDate | SubCityEng | AntBidQuarter | AntBidYear | BidOpenQuarter | BidOpenYear | ConstContractAmount | BudgetAward | BudgetAwardDate | CouncilApprovedDate | AdjustBudget | AdjustBudgetDate | ConstCompleteQuarter | ConstCompleteYear | RemainCost | FinalCost | FinalCostDate | ScopeChange | ScopeChangedate | Onhold | OnholdDate | CombinedTo | CombinedToDate | Renamed | RenamedDate | Reassigned | ReassignedDate | PlanningBudgetType | DesignBudgetType | ConstructBudgetType | OverheadMultiplier | ConstructionEstimate | ConstructionEstimateDate | QuarterlyReportAmount | QuarterlyReportAmountDate | FinalStudyCost | FinalDesignCost | FinalConstructionCost | FinalConstructinContractCost | FinalFieldOpsCost | FinalPubleEngageCost | FinalOtherCosts | ComEngageLevel | RFPFileNumber1 | RFPReportDate1 | RFPProjectCosttoDate1 | RFPFileNumber2 | RFPReportDate2 | RFPProjectCosttoDate2 | RFPFileNumber3 | RFPReportDate3 | RFPProjectCosttoDate3 | RecurFundProject2 | SustainEnegry | EnergyConservation | HighPerformBldg | EngagedCommunity | DiverseHousing | HumanServices | SafeCommunity | ActiveLiveLearn | EconomicVitality | TransportationOptions | SustainSystems | IntegratedLandUse | CleanAirWater | HealthyEcosystems | ResponseLandUse | LocalFood | SustainClimateEnergy | SustainCommunity | SustainLandUseAccess | PublicArtEnhanced | PublicArtBudget | SustainResourceMgmt
97 | UT-SN-01-09 | Facilities Renovation | 1222280000 | Ann Arbor Twp. | Wastewater Treatment Plant | PUBLIC SERVICES | WASTEWATER TREATMENT | 12 | Develop and implement a plan to replace deteriorating infrastructure and equipment while optimizing plant efficiency and treatment. | West plant replacement, east plant improvements and admin building replacement | Urgent | NULL | 0 | NULL | 6 | Necessary to repair deteriorating infrastructure; equipment ineffective; optimize process systems; logical prioritization based on plan; improved treatment capabilities. | the entire | 1 | 1 | Allows time to implement recommended improvements to repair, replace or optimize plant treatment systems. Activities are scheduled to maintain process integrity. | 3 | 2001 | 4 | 2004 | 400000 | 2 | 2005 | 4 | 2011 | 8800000 | 1 | 2012 | 1 | 2017 | 113100000 | NULL | NULL | NULL | NULL | 7 | Decrease | Decrease | Amicangelo, Mike | Gosselin, Deb | 43003 | 1 | Changes in budget; soils encountered that exceed metals criteria; regulatory issues being analyzed. FAll17: marked as TBC. | Maintain, improve or replace infrastructure and equipment. Maintain safe work environment. Provide highest quality service consistent with regulations and community environmental values. | 8040396 | 6761817 | utsn0109.jpg | Amicangelo, Mike | Kenzie, Earl | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | NULL | 1 | Water Treatment Plant Facilities Master Plan (2006) | NULL | NULL | NULL | Active | Construction | 80.77 | 1 | NULL | Amicangelo, Mike | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | 1 | Minimal | 1 | 0 | NULL | 5 | 0 | WWTP | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1738 | TR-OT-15-03 | East Liberty Street Tree Pit Expansion | 100000 | NULL | Liberty (Main to Division) | NULL | NULL | 9 | Trees dying sue to insufficient root room in small pits | New street trees; Expand tree pits horizontally; remove concrete and install brick. Add tree grates; consider green infrastructure ; coordinate with streetlight installation: DDA project | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 2 | 2024 | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 43437 | 0 | Fall 2016: set rank to zero and moved to 24 as not on current DDA list. Fall 18; updated $ per DDA | NULL | 0 | 0 | TROT1503.jpg | Pollay, Susan | Gray, Kerry | Miller, Amber | Elenbaas, Chris | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
393 | TR-AT-01-07 | Arboretum/Gallup Underpass | 2250000 | Northeast | Along Bike path between Gallup Park and Nichols Arboretum | COMMUNITY SERVICES | PARKS & RECREATION | 6 | Engineering and construction of a tunnel under the Norfolk and Southern railroad for pedestrian and bicycle access between Gallup Park and Nichols Arboretum. Illicit RR crossings. | MDOT RR involvement. Environmental Assessment (EA) likely required including section 4-F determination. U of M involvement. Feasibility study done. Art enhancemment requested. | Important | No | 0 | NULL | 1 | Construction of the tunnel will facilitate safe access between these two parks and continue the Huron River greenway on the south side of the river. | the entire | 1 | 1 | Preliminary work for this project was scheduled for 2001-2002 of the Park Rehabilitation and Development Millage. The funding is available for engineering, but have had some difficulty locating engineering firms willing to perform the work. | 1 | 2004 | 3 | 2005 | 50000 | 4 | 2020 | 4 | 2022 | 300000 | 2 | 2023 | 4 | 2023 | 4100000 | 0 | 500 | 0 | 500 | 4 | Increase | Increase | Hanzel, Hillary | Gosselin, Deb | 43433 | 0 | Past amount spent per AK 9.19.13 email ;Fall 2016: moved to FY21/22 to go after Bandemer and Border to Border and EMC ; art asked 6/2017 but whose funds?. Fall 18: updated dollars and assumed TAP and some GF and added art money within grant for now | NULL | NULL | NULL | trat0107.jpg | Kuras, Amy | Cooper, Eli | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | Washtenaw County Parks and Recreation Commission | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | AnnArbor Transportation Plan Update (2009) | Parks & Recreation Open Space (PROS) Plan | NULL | Programmed | Inactive | 72.71 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 150000 | 0
628 | TR-AP-99-11 | Terminal Expansion | 327000 | Pittsfield Twp. | Airport | PUBLIC SERVICES | FLEET & FACILITY | 5 | Expand terminal to include full access (day and night), accessible restrooms and meeting room(s) and pilots' lounge. | Energy improvements; examine use of green roof | Important | No | 0 | NULL | 7 | Handicapped access to conference rooms, offices and pilots lounge. Increase rentable and City office space. | the entire | 0 | 1 | Availability of federal and state funds. | NULL | NULL | NULL | NULL | 0 | 4 | 2023 | 1 | 2024 | 62000 | 2 | 2024 | 3 | 2024 | 714000 | 0 | 5000 | 0 | 5000 | 9 | Increase | Increase | Kulhanek, Matt | Gosselin, Deb | 42691 | 0 | Fall 2016: moved to Fy2023 and updated $ | Ensure adequacy of City infrastructure. | NULL | NULL | trapMain.jpg | Kulhanek, Matt | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Condition Analysis | Customer Level of Service | NULL | 1 | AIP Capital Improvement Plan | NULL | NULL | NULL | Programmed | Inactive | 54.6 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | 1 | NULL | NULL | 1 | NULL | 1 | 1 | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 20000 | 0
423 | MF-PR-01-04 | Open Space and Park Acquisitions | 60000000 | TBD | Citywide and Greenbelt Region | COMMUNITY SERVICES | PARKS & RECREATION | 3 | Purchase land for public use and purchase development rights as recommended by the Parks Adv. Comm., Greenbelt Adv. Comm. Utilizing Open Space & Parkland Mileage funds to leverage Local, State and Federal Grant Funds. | Greenbelt Millage went into effect 2005 extending funding for 30 years. | Important | No | 0 | NULL | 5 | Preserve quality natural areas and groundwater recharge zones, connect existing parks, and create added public open space. Purchase development rights on agriculture property to preserve operation of active farmland. | the entire | 1 | 0 | Development pressures and rising land costs necessitate the purchase as soon as project is identified. Schedules for specific parcels are dictated by availability and by the procedures of the granting agency, if grant funds are used. | 2 | 2001 | 2 | 2033 | 0 | 2 | 2001 | 2 | 2035 | 60000000 | NULL | NULL | NULL | NULL | 0 | 0 | 20000 | 0 | 20000 | 7 | Increase | Increase | Smith, Colin | Smith, Colin | 43431 | 0 | Extended funding to end of millage life in 2035. Edited it to go through FY2019 as 2M annual revenue. Fall 2016: NC Fall 18: updated outer years | NULL | NULL | NULL | mfpr0104.jpg | Trocchio, Ginny | Kuras, Amy | Smith, Colin | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Planning | 57.93 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | 1 | NULL | 1 | 2 | 2 | 2 | NULL | 2 | 0 | 1 | 1 | NULL | NULL | 1
595 | UT-SN-01-03 | Austin Sanitary Sewer Outlet | 725000 | Northeast | Austin Avenue and Fair Oaks Parkway area. | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Concern of 8-inch and 15-inch pipes flowing into an 8-inch, capacity issues and pipe restriction could cause blockages. Condition of crosslot from Scottwood/Austin needs to be lined or abandoned. | Address restriction of 8-inch and 15-inch pipes flowing into an 8-inch, downstream 8 and 10 inch pipes extending approximately 3400 feet flow full during wet weather. Consider alternate paths, pipe upsizing, FDD's and condition/service life(Water & Storm) | Important | No | 0 | NULL | 6 | This project would relieve flooding of basements. | a subarea of the | 1 | 0 | To relieve the flooding. Project to be re-evaluated as part of a complete sanitary system hydraulic model to determine if it is still needed due to the flow reductions of implementing a city-wide footing drain disconnection program. | 2 | 2011 | 4 | 2011 | 0 | 4 | 2021 | 1 | 2022 | 40000 | 2 | 2022 | 4 | 2022 | 685000 | 0 | 0 | 0 | 13700 | 7 | Not Affect | Decrease | Baughman, Troy | Gosselin, Deb | 43045 | 0 | Numbers not cost forwarded Fall 2014; so put entire $725,000 in FY21 whether or not any monies previously spent; project may go away so did not cost update. Fall 2016: Did split into 40//60. Fall 17: NC Fall 18 | Ensure adequacy of City infrastructure. | NULL | NULL | utsn0103.jpg | Baughman, Troy | Hupy, Craig | Wooden, Dan | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Capacity Analysis | NULL | NULL | 1 | Sanitary Sewer Capacity Audit and Model | NULL | NULL | NULL | Programmed | Inactive | 37.83 | 23 | NULL | TBD | Involve Baughman in the early stages to understand capacity issues. High likelihood of cross-lot impacts. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 0 | 0 | Moderate | 0 | 1 | NULL | 5 | 0 | Project Management | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
597 | UT-SN-01-28 | South Boulevard Lift Station Elimination & Gravity Sewer | 325000 | South | South Boulevard | PUBLIC SERVICES | WASTEWATER TREATMENT | 12 | Provide gravity flow sewer, eliminate pump station which requires on-going maintenance and confined space entry | Requires cross lots easement; determine routing; coordinate with water main project. Will require easement from Woodbury Apartments. | Desirable | Yes | 1 | 14 | 6 | This project would lower operation and maintenance costs. | a subarea of the | 1 | 0 | Priority tied to water main project. Continued maintenance costs keep rising. | NULL | NULL | NULL | NULL | 0 | 3 | 2018 | 4 | 2018 | 92000 | 2 | 2019 | 2 | 2019 | 1218000 | 0 | 2500 | 0 | 2500 | 7 | Decrease | Decrease | Humphriss, Tesha | Slizewski, Brian | 43391 | 0 | Fall 2016: moved to FY20 to align with water; costs not updated; Fall 17: moved to FY19 and increased cost to $500K (needs more analysis). Project cost updated based on eliminating lift station and crosslot sewer; rerouting Coler and South to the west | Maintain, improve or replace infrastructure and equipment. Provide highest quality service consistent with regulations and community environmental values. | NULL | NULL | utsn0128.jpg | Slotten, Cress | Amicangelo, Mike | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 39 | 20 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 80484.8 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
600 | UT-SN-87-07 | Calvin Street Sanitary Sewer | 850000 | West | Calvin and Woodrow | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Extend sanitary sewer service to residents along Calvin and Woodrow. | (from past CIP document);Calvin did have someone on pump/haul (years ago), haven't heard anything recent though | Important | No | 0 | NULL | 1 | Eliminate questionable septic fields. | a subarea of the | 1 | 0 | Calvin and Woodrow Streets are part of an unrecorded plat, and there is no recorded dedication of them as a public right-of-way. Legal issues preventing access to construct utilities here and lack of owner desire prevent this project from moving forward. | NULL | NULL | NULL | NULL | 0 | 3 | 2024 | 4 | 2024 | 98000 | 2 | 2025 | 4 | 2025 | 1302000 | 0 | 0 | 0 | 950 | 21 | Not Affect | Increase | Baughman, Troy | Baughman, Troy | 43390 | 0 | Updated cost estimate and schedule; updated schedule in 2012; numbers not updated in Fall 2014 or Fall 2016. Fall 17: NC; 2018 cost updated | Ensure adequacy of City infrastructure. | NULL | NULL | utsn8707.jpg | Slotten, Cress | Hupy, Craig | Heatley, Alison | NULL | NULL | 1 | Citizen/Property Owner | Washtenaw County Environmental Health | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 41.93 | 17 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
852 | UT-WS-01-06 | Calvin Street Water Extension | 625000 | West | Calvin and Woodrow | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Water service is not yet installed property owners on wells | Failing septic. No right-of-way, private street. Public easement will need to be granted, special assessment, fixed charge. Coordinate with sanitary extension | Important | No | 0 | NULL | 1 | Water service will not be available for new development or if existing wells fail. | a subarea of the | 1 | 0 | Construct water main and sewer jointly to save road restoration costs. | NULL | NULL | NULL | NULL | 0 | 3 | 2024 | 4 | 2024 | 45000 | 2 | 2025 | 2 | 2025 | 580000 | 0 | 0 | 0 | 1000 | 7 | Not Affect | Increase | Gosselin, Deb | Gosselin, Deb | 42715 | 0 | Fall 2016: moved to beyond 2023 as no activity; cost not updated. Fall 18 to 25-26 | Ensure adequacy of City infrastructure. | NULL | NULL | utws0106.jpg | Slotten, Cress | Hupy, Craig | Heatley, Alison | NULL | NULL | 1 | NULL | NULL | NULL | County Env.... Health | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.91 | 36 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 2 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 0 | NULL | NULL | 0
864 | UT-WS-01-31 | State St (at Stimson) Raw Water - Reconstruct Interconnection | 225000 | South | State Street and Stimson | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Install a replacement inter-connection between the raw and treated water mains at State Street and Stimpson | Space considerations | Desirable | No | 0 | NULL | 2 | Well water safe for drinking may supply the distribution system if treated water source cannot meet demand in emergency conditions. | the entire | 1 | 0 | Aging valves need to be replaced to ensure reliability of the isolation at this emergency inter-connection point. | NULL | NULL | NULL | NULL | 0 | 4 | 2022 | 4 | 2022 | 50000 | 2 | 2023 | 2 | 2023 | 175000 | 0 | 0 | 0 | 0 | 7 | Not Affect | Not Affect | Baughman, Troy | Gosselin, Deb | 43046 | 0 | Updated schedule; moved out to 2021 possibly eliminate? Fall 2016: moved to 23. Fall 17: NC Fall 18 NC | Ensure adequacy of City infrastructure. Provide effective wastewater and water systems and facilities planning. | NULL | NULL | utws0131.jpg | Sanford, Larry | Hupy, Craig | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 31.28 | 56 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
635 | TR-OT-01-07 | Plymouth Road/Commonwealth Signal | 90000 | Northeast | Plymouth Road at Commonwealth | PUBLIC SERVICES | PROJECT MANAGEMENT | 9 | Install traffic signal. | Developer money in escrow. In 2017, a temporary signal was placed at this location during construction of the Nixon/Green/DhuVarren roundabout. It was then removed. This location will continue to be evaluated. | Desirable | No | 0 | NULL | 1 | Reduction of delay and increased safety at this intersection. | a subarea of the | 1 | 0 | The actual traffic in the intersection needs to meet at least one signal warrant. | NULL | NULL | NULL | NULL | 0 | 3 | 2024 | 1 | 2025 | 3000 | 2 | 2025 | 2 | 2025 | 87000 | 0 | 1000 | 0 | 3500 | 7 | Increase | Increase | Liu, Luke | Gosselin, Deb | 43437 | 0 | Schedule adjusted; again in 2012. Developer contribution was made by First Martin in the 1980s. Fall 2016; pushed to end as no activity on this. Fall 18; pushed again | This project will improve city services to the traveling public in a cost effective manner by using developer contribution, and ensure adequacy of traffic control system infrastrucuture. | NULL | NULL | trot0107.jpg | Sipowski, Les | Slotten, Cress | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 15.65 | 20 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
871 | UT-ST-88-05 | Evergreen Subdivision Storm Water (Phase II) | 100000 | West | Evergreen and Scioto Hills Subdivision (S of Dexter, E of Rose) | PUBLIC SERVICES | SYSTEM PLANNING | 13 | Develop and construct a storm water drainage system for the Evergreen Subdivision area. Alternate forms of storm water management will be considered. | Unimproved streets. Assessment issues. Outlet issues. | Desirable | No | 0 | NULL | 1 | Reduce flooding and ponding. | a subarea of the | 1 | 0 | Long standing problem that the residents want addressed. The project has not yet been initiated due to lack of funding, resistance to assessments, and lack of storm water outlet for the area. | 3 | 2018 | 2 | 2019 | 0 | 3 | 2024 | 4 | 2024 | 8000 | 2 | 2025 | 4 | 2025 | 92000 | 0 | 0 | 0 | NULL | 20 | Not Affect | Not Affect | Kotlyar, Igor | Gosselin, Deb | 43423 | 0 | Revised schedule. Revised again in 11/12; costs not updated Fall 2014. Fall 2016: costs not updated; moved to beyond. Fall 17: NC Fall 18 to FY25 | Ensure adequacy of City infrastructure. Provide effective wastewater and water systems and facilities planning. | 0 | 0 | utst8805.jpg | Ernst, Kevin | Pennington, Kirk | Slotten, Cress | Carson, Chris | Hancock, Jerry | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 34.92 | 29 | NULL | TBD | NULL | High level of engagement - Strategy TBD | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Moderate | 1 | 0 | outreach will be complex | 8 | 1 | Systems Planning | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
876 | UT-WS-03-01 | Ann Arbor Railroad Water Main Bore | 225000 | South | Bore water under railroad to connect Boardwalk Drive with Eisenhower Corporate Park. | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Bore water main under railroad approximately 120 feet of 12-inch to connect Boardwalk Drive with Eisenhower Corporate Park. | Permitting through AARR; sizing to be determined; confirm that easements have been obtained | Desirable | No | 0 | NULL | 1 | Will strengthen fire protection for Eisenhower Corporate Park and general water system grid will be strengthened. | a subarea of the | 1 | 0 | To provide a second source (link) to back-up the primary water supply piping that has been lacking for 10 years. | NULL | NULL | NULL | NULL | 0 | 3 | 2024 | 4 | 2024 | 30000 | 2 | 2025 | 4 | 2025 | 130000 | 0 | 0 | 0 | 100 | 5 | Not Affect | Increase | Slotten, Cress | Gosselin, Deb | 42710 | 0 | Updated cost estimate. Fall 2016: costs not updated; moved to beyond 23. Fall 18: moved back one year; costs not updated | Ensure adequacy of City infrastructure. | NULL | NULL | utws0301.jpg | Slotten, Cress | Baughman, Troy | Hupy, Craig | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 10.3 | 86 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
879 | UT-WS-01-30 | South Boulevard Water Main (Packard to Dead End) | 160000 | South | South Boulevard (Packard to Dead End) | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Water quality issues; aging main | Upsize main; Look at looping main; challenging to find location; easement will be required; coordinate with sanitary lift station removal; boundary considerations; approximately 700 feet of 8-inch. Address water quality issues; | Important | Yes | 1 | 14 | 1 | Construction of this main will eliminate color complaints and water quality issues. It will also replace a 4" main with an 8" looping main improving fire coverage. | a subarea of the | 1 | 0 | This work should be done while street is torn up for sewer lift station work. May be delayed due to easement acquisition. | NULL | NULL | NULL | NULL | 0 | 3 | 2018 | 4 | 2018 | 0 | 2 | 2019 | 4 | 2019 | 500000 | 0 | 0 | 0 | 200 | 7 | Not Affect | Increase | Humphriss, Tesha | Baughman, Troy | 43389 | 0 | Project delayed several years; updated schedule; received email from resident on 6.20.16 expressing decreased water quality. Fall 2016: left in 2020; upped numbers but still seem low. Fall 17: moved to FY19 and increased to $350K | Ensure adequacy of City infrastructure. | NULL | NULL | utws0130.jpg | Slotten, Cress | Warrow, Anne | Sanford, Larry | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 30.49 | 59 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | 2018-025 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
943 | TR-NS-95-01 | Oakbrook Drive Extension (west of State Street) | 2475000 | South | From the easterly end of existing Oakbrook (at the Harbor House Development/Oakbrook Park) to South State Street | PUBLIC SERVICES | SYSTEM PLANNING | 8 | System continuity, local access to UM South Campus | Wetland impacts; U of M coordination; Utilities; ROW delineation; Intersection design. Stormwater management/detention; traffic impacts per State Street Corridor Transportation Study | Important | No | 0 | NULL | 1 | A portion of traffic on Eisenhower Parkway, the only other east-west option in this area, will shift to the Oakbrook collector street. This street will provide access to U-M planned facilities. | a subarea of the | 1 | 1 | As a special assessment project that also involves the University of Michigan, substantial time should be devoted to the study and design phase of the project. | 3 | 2022 | 2 | 2023 | 200000 | 3 | 2023 | 4 | 2023 | 450000 | 2 | 2024 | 2 | 2025 | 1825000 | 0 | 0 | 0 | 1000 | 13 | Increase | Increase | Gosselin, Deb | Gosselin, Deb | 43432 | 0 | Project moved back pending coordination with the U of M ; Checked and updated 12/4/12; moved back again in Fall 2013 as no activity. UM now interested in this happening. 8/15/14. Fall 2016: moved back. Fall 18; moved back; feasible? | This project is needed to provide an alternate east-west route to Eisenhower Pkwy & access to U-M planned facilities, thus ensuring the adequacy of the city's trasportation infrastructure system | NULL | NULL | trns9501.jpg | Pulcipher, Connie | Slotten, Cress | NULL | Hancock, Jerry | Sipowski, Les | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | On Hold (comment required) | 40.17 | 5 | waiting for the UM to develop plans for their property | TBD | Regulated wetlands TBD; Inland Lakes & Streams TBD | informational | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Minimal | 1 | 1 | Coordination with UM | 7 | 0 | Systems Planning | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 2 | NULL | 2 | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
949 | TR-AT-02-13 | Main St (AA-Saline to East Stadium) Shared Use Path | 1000000 | South | South Main Street (Ann Arbor-Saline Road to East Stadium Boulevard) on east side | PUBLIC SERVICES | SYSTEM PLANNING | 6 | The construction of a non-motorized path and retaining walls along the east side of South Main Street.. | Alternatives analysis needed. 10' shared use path or sidewalk plus added bike lanes; Several options outlined in process with AAGO. Mike Nearing has project files. TE Funding award was turned back to MDOT in lieu of Stadium Blvd Bridges TE application. | Urgent | No | 0 | NULL | 1 | The project will eliminate the safety hazard for pedestrians and bicyclists in proximity to major pedestrian generators (U-M athletic campus and Pioneer High School). | the entire | 1 | 0 | This project will be a special assessment project and will require grading easements, and design of retaining walls so as to minimize the impacts of the project to the existing natural features. Also, a TEA-21 grant application will be considered. | 3 | NULL | 1 | NULL | 0 | 3 | 2020 | 4 | 2020 | 220000 | 2 | 2021 | 4 | 2021 | 2010000 | 0 | 0 | 0 | 0 | 6 | Not Affect | Not Affect | Hutchinson, Nick | Gosselin, Deb | 43433 | 0 | Updated cost based on MGN cost estimate done in 2006, and cost forwarded that amount to 2018 dollars. Fall 18: moved ot FY21-22 and using 0062 and STP | By construction a non-motorized transportation facility where one is lacking, this project will help ensure the adequacy of the city's non-motorized transportation infrastructure system. | 1223050 | 318600 | trat0213.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | Capacity Analysis | NULL | 1 | Ann Arbor Non-Motorized Plan | NULL | AnnArbor Transportation Plan Update (2009) | NULL | Programmed | Inactive | 72.6 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
665 | TR-OT-01-09 | Seventh Street Signal Interconnect | 600000 | West | Seventh Street (Scio Church to Miller) | PUBLIC SERVICES | PROJECT MANAGEMENT | 9 | Connect last corridor into signal system | From Transportation Plan update. Explore CMAQ and ITS funds; particularly key to event traffic | Desirable | No | 0 | NULL | 1 | Reduction of delays and air pollution, increased reliability. | a subarea of the | 1 | 0 | The schedule is based on requirements for the federal funding for this project. | NULL | NULL | NULL | NULL | 0 | 2 | 2016 | 2 | 2016 | 75000 | 3 | 2016 | 4 | 2017 | 754640 | 0 | 0 | 0 | NULL | 7 | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 42986 | 1 | updated schedule; again; Got $650K CMAQ so moved to FY18 in Fall 2015 Fall 2016: just edited rank and Luke updated numbers; Fall 17 marked as TBC | NULL | 167459 | 0 | trot0109.jpg | Cawley, Pat | Sipowski, Les | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 30.84 | 8 | Need to apply for CMAQ funding when it is appropriate (FY 2015 at the earliest) | Sipowski, Les | NULL | NULL | NULL | NULL | NULL | 41456 | NULL | NULL | NULL | 0 | 0 | 0 | 0 | Minimal | 1 | 0 | CMAQ Funding | 2 | 0 | Project Management | No | NULL | NULL | NULL | NULL | 50000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
838 | UT-WS-92-35 | WTP: Steere Farm Well Booster Station | 1500000 | TBD | Along raw water main from Steere Farm Wells to Water Treatment Plant. | PUBLIC SERVICES | WATER TREATMENT | 14 | Increase well water capacity to WTP. | Add booster pumping station to well water line. Define locations. | Important | No | 0 | NULL | 1 | Increased plant capacity, improved winter operations- both for sludge handling and water quality, and increased reliability of quality source water. | the entire | 1 | 0 | Necessary improvement to maintain future reliability of water treatment plant operation. Project delayed to await completion of Water Resources Study. | 4 | 2012 | 3 | 2013 | 0 | 3 | 2022 | 2 | 2023 | 500000 | 3 | 2023 | 2 | 2025 | 2500000 | NULL | 10000 | NULL | 10000 | 16 | Increase | Increase | Wiczorek, Glen | Wiczorek, Glen | 43438 | 0 | Fall 2015: Moved to FY20 and FY21 and increased total budget to $2M; Fall 2016: GRW - increased budget as location is currently unknown. Fall 18 pushed back | Ensure the adequacy of City infrastructure. | NULL | NULL | utws9235.jpg | Steglitz, Brian | Sanford, Larry | Slotten, Cress | Hupy, Craig | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Water Treatment Plant Facilities Master Plan (2006) | NULL | NULL | NULL | Programmed | Inactive | 14.16 | 85 | NULL | Steglitz, Brian | Potential locations need to be identified - may require easements/property acquisition. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | 0 | Minimal | 0 | 1 | confirm with PM; power needs; railroad coordination required? | 3 | 0 | WTP | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
883 | UT-WS-01-08 | Eisenhower Parkway (Packard to Stone School) Water Main | 275000 | South | Eisenhower Parkway (Packard to Stone School Road) | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Complete line where there is currently a gap in the system, and provide looping | Construct water main in Eisenhower Parkway from Packard 800 feet west toward Stone School Road.. 800 LF of 16" water main and hydrants and valves. Coordinate with Packard Road resurfacing | Desirable | No | 1 | 37 | 1 | Will improve the water transmission system in the Southeast Pressure district | a subarea of the | 1 | 0 | Needs to be completed to provide service and to strengthen water system grid. Some parcels do not have water service available. Project scope reduced because first half (west portion) of the project, approximately 700 feet, completed by a developer. | NULL | NULL | NULL | NULL | 0 | 3 | 2025 | 4 | 2025 | 75000 | 2 | 2026 | 2 | 2026 | 200000 | 0 | 0 | 0 | 550 | 7 | Not Affect | Increase | Baughman, Troy | Gosselin, Deb | 41969 | 0 | Updated schedule; moved way out because road got resurfaced; added limits to project name on 10.10.14 Fall 2016: moved to beyond 23. Fall 18: costs not updated and no raodwork known so moved to 26 | Ensure adequacy of City infrastructure. | NULL | NULL | utws0108.jpg | Baughman, Troy | Rolla, Liz | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 28.41 | 64 | confirm need to coordinate/schedule with Packard resurfacing. | Rolla, Liz | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 0 | 0 | Moderate | 0 | 0 | coordination with resurfacing | 5 | 0 | Project Management | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
924 | UT-SN-01-30 | Springbrook Sanitary Sewer Extension | 260000 | South | Springbrook Ave and Marshall Street | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Extend sanitary sewer service approximately 550 feet of 8-inch sewer from Marshall Street north on Springbrook, and then crosslots easterly to serve four city owned parcels. | Coordinate with AAHC and their program for the properties needing service; possible coordinate Springbrook Subdivision Storm replacement project | Desirable | No | 0 | NULL | 1 | Provide sanitary sewer service for potential affordable housing site. | a subarea of the | 1 | 0 | Extend sanitary sewer service to serve a city-owned parcel that has been tagged as a potential affordable housing site. | NULL | NULL | NULL | NULL | 0 | 4 | 2023 | 4 | 2023 | 0 | 2 | 2024 | 4 | 2024 | 700000 | 0 | 0 | 0 | 100 | 7 | Not Affect | Increase | moved out agina | Gosselin, Deb | 42717 | 0 | Updated schedule and cost estimate; costs not updated Fall 2014. Fall 2016: no activity on this site per JH so moved out: costs not updated. Fall 18 | Ensure adequacy of City infrastructure. | NULL | NULL | utsn0130.jpg | Slotten, Cress | Hall, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 35.02 | 28 | NULL | TBD | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
934 | UT-SN-02-11 | Wet Weather Mitigation (Long Term) | 63945000 | City-wide | Locations throughout the city | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Reduce flow in sanitary sewers during storm events. | Per Sanitary Sewer Wet Weather Evaluation Project, reserve capital funds to address improvements in the identified five study areas after prelim. engr.; other approved study recommendations; developer offset mitigation program mgt.; homeowner outreach | Important | No | 0 | NULL | 1 | Prevent backups of sewage into residents' basements. | the entire | 1 | 0 | Residents are very concerned about recurring backups and desire immediate action to prevent future incidents. Prevent law suits and regulatory penalties. | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | 1 | 2016 | 2 | 2036 | 27932000 | 0 | 0 | 0 | 15000 | 6 | Decrease | Increase | Hutchinson, Nick | Gosselin, Deb | 43045 | 1 | Updated funding. Fall 2106: lowered FY20becasue assume Dom money will be available. Fall 17: Reduced FY18 313K to cover changes | Ensure adequacy of City infrastructure. | NULL | NULL | utsn0211.jpg | Warrow, Anne | Hupy, Craig | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 46.4 | 6 | NULL | Warrow, Anne | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 997944.13 | 2018-03-31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | 2014-042 | NULL | NULL | 2015-019 | 2017-06-30 | 129645.52 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
997 | UT-WS-04-07 | Cedar Bend (Lower) Water Main Replacement | 175000 | Northeast | Cedar Bend Drive (Fuller Road to Cul-de-sac end) | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Water quality improvement | Replace water main; coordinate with termination of dead end street | Important | Yes | 0 | NULL | 2 | Eliminate need for weekly flushing due to water quality issues and prevent costly main break repairs. | a subarea of the | 1 | 0 | Many water quality complaints and several recent water main breaks. | NULL | NULL | NULL | NULL | 0 | 3 | 2018 | 4 | 2018 | 0 | 2 | 2020 | 4 | 2020 | 350000 | 0 | 4000 | 0 | 0 | 4 | Decrease | NULL | Humphriss, Tesha | Baughman, Troy | 43389 | 0 | 2016 - Cost Updated; assumes it will be done with road project Fall 18 2018, no recent water quality complaints, consider pushing back until road is needed to be done. Filter at 1030 Cedar Bend; mostly garvel; | Ensure adequacy of City infrastructure. | NULL | NULL | utws0407.jpg | NULL | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 30.1 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
966 | TR-AP-03-10 | Terminal Auto Parking Lot Expansion | 242000 | Pittsfield Twp. | Airport | PUBLIC SERVICES | FLEET & FACILITY | 5 | Expand existing terminal area automobile parking lot. | Examine parking lot standards for Pittsfield Township with goal to achieve them; consider rain gardens (stormwater BMP's), LED lighting. | Important | No | 1 | 27 | 1 | Current parking facility is inadequate for peak periods, causing drivers to circle the lot looking for an available space. | a subarea of the | 0 | 1 | Availability of federal and state funds. | NULL | NULL | NULL | NULL | 0 | 3 | 2020 | 4 | 2020 | 38000 | 3 | 2021 | 4 | 2021 | 394000 | 0 | 0 | 0 | 0 | 5 | Not Affect | Not Affect | Kulhanek, Matt | Gosselin, Deb | 42691 | 0 | Adjusted schedule; removed relocation of Airport DR; Fall 2015: adjusted schedule and budget per MK; Fall 2016: moved to Fy2021 and updated $; pushed back due to runway delays | Ensure adequacy of City infrastructure. | NULL | NULL | trapMain.jpg | Kulhanek, Matt | Crum, Lynn | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 1 | AIP Capital Improvement Plan | NULL | NULL | NULL | Programmed | Inactive | 43.29 | 4 | Request made to MDOT to move project into state FY12 budget cycle. | Kulhanek, Matt | Plans submitted do not need Township board approvals (only staff review and comment) | Engagement for airport user community only (through the Airport Advisory Committee) | NULL | NULL | NULL | 40909 | 41030 | 41091 | 41183 | 0 | 0 | 1 | 0 | Minimal | 1 | 0 | NULL | 3 | 0 | Fleet and Facilities | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | 1 | NULL | 1 | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
968 | TR-AP-20-01 | Airport Access Road Reconstruction (Airport Blvd) | 327000 | Pittsfield Twp. | Airport | PUBLIC SERVICES | FLEET & FACILITY | 5 | Rehabilitation of existing Airport Blvd.; design and Phase 1 construction may be separate from a Phase 2 | Include pedestrian side path along one side of Airport Blvd (approximately 2000 LF); include boulevard entrance at Ellsworth; install curb and gutter and conveyance stormwater pipes thereby reducing flow to County drain system | Important | No | 0 | NULL | 3 | Will reduce current maintenance costs and provide storm drain system and curbing. | the entire | 0 | 0 | Availability of federal and state funds | NULL | NULL | NULL | NULL | 0 | 1 | 2021 | 2 | 2021 | 42000 | 2 | 2021 | 4 | 2021 | 522000 | 0 | 0 | 0 | 0 | 5 | Not Affect | Not Affect | Kulhanek, Matt | Gosselin, Deb | 43011 | 0 | adjusted schedule and updated funding sources; Fall 2015: moved out a year and updated funds per MK. Fall 2016: revised $ and schedule; Fall 2016: costs updated and spread over two years FY18/FY19. Fall 17: shifted to FY19/20 | Ensure adequacy of City infrastructure. | NULL | NULL | trapMain.jpg | Kulhanek, Matt | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | AIP Capital Improvement Plan | NULL | NULL | NULL | Programmed | Planning | 39.49 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 2 | 2 | NULL | 1 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
971 | TR-AP-03-03 | Airport Stormwater Detention Pond and System | 128000 | Pittsfield Twp. | Airport | PUBLIC SERVICES | FLEET & FACILITY | 5 | Modification of the airport's stormwater drainage and detention system for the airport's existing and future facilities north of the Wood Drain Creekshed, including the removal of an small, existing pond at the Bijan Air facility. WCWRC | Market driven (need for additional hangars) | Important | No | 0 | NULL | 6 | Provide a total storm water drainage and detention system for all facilities rather that for each new development. | the entire | 0 | 1 | Availability of Federal and State funding. | NULL | NULL | NULL | NULL | 0 | 4 | 2024 | 1 | 2025 | 20000 | 2 | 2025 | 3 | 2025 | 125000 | 0 | 0 | 0 | 5000 | 5 | Not Affect | Increase | Kulhanek, Matt | Gosselin, Deb | 42691 | 0 | adjust schedule; Fall 2016: NC | Ensure adequacy of City infrastructure. | NULL | NULL | trapMain.jpg | Kulhanek, Matt | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | Allowance for future hanger development | 1 | AIP Capital Improvement Plan | NULL | NULL | NULL | Programmed | Inactive | 27.2 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 1
978 | UT-SN-03-29 | Southside Interceptor Rehabilitation | 12170000 | Northeast | Sanitary Sewer Trunk System on the south side of the Huron River from Glen Avenue to the Wastewater Treatment Plant. | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Investigate and install CIPP lining as required to improve life span of the existing pipe and prevent failures that could discharge to the Huron River. Approximately 5 miles total of various diameter pipes: 24-inch, 36-inch and 42-inch. | Manholes in wooded areas (to be raised) and some on private property - - need to verify existing easements and access; examine aerial crossings;Future phases - 5500LF (chalmers to Hickory Lane) - $1.7M Proj Cost; then, Geddes to Pineview(ish) (2500LF) | Important | No | 0 | NULL | 3 | Identify and correct potential pipe failures which could result in discharges to the Huron River. | the entire | 1 | 0 | NULL | 4 | 2007 | 2 | 2008 | 100000 | 3 | 2006 | 4 | 2014 | 550000 | 2 | 2008 | 4 | 2018 | 13975000 | 0 | 0 | 0 | 0 | 5 | Not Affect | NULL | Slizewski, Brian | Gosselin, Deb | 42716 | 0 | Updated funding and schedule; updated again in 11/2012. Fall 2106: someone slightly adjusted FY18 and FY 19 upward; Last phase will be helicopter pad to glen/fuller(2500LF) | Ensure adequacy of City infrastructure. | 1187829 | 74026 | utsn0329.jpg | Warrow, Anne | Amicangelo, Mike | Baughman, Troy | Hupy, Craig | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 45.38 | 11 | NULL | Kotlyar, Igor | Check pipes for sediment build-up. UM involvement (Arboretum). | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | 1 | Minimal | 0 | 1 | NULL | 5 | 0 | Project Management | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 103522.37 | 2014-06-28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 3033000 | 2016-06-10 | 2191293.68 | 2017-07-10 | 0 | 16364.14 | NULL | 87158.23 | NULL | NULL | NULL | Low Local | 2015-031 | NULL | NULL | 2017-037 | 2019-03-30 | 7886 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | 2 | 2 | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
1040 | MF-SW-06-03 | Drop-off Station | 4900000 | Pittsfield Twp. | Wheeler Center or other site | PUBLIC SERVICES | SYSTEM PLANNING | 15 | Relocation and upgrading of recycling and solid waste drop-off station for public use; existing facility is badly deteriorating. | Pittsfield Twp review required if in Twp; partnering with Washtenaw County and surrounding townships and other agencies as over 60% of users are from outside the city; composting restrooms. Art enhancement. | Important | Yes | 1 | 25 | 2 | Expands capacity of facility, removes aging, existing site from Ellsworth Road corridor. | the entire | 1 | 1 | Land: $344,870. Design: $30,000 | 2 | 2016 | 2 | 2017 | 59350 | 3 | 2019 | 2 | 2020 | 275000 | 3 | 2020 | 2 | 2021 | 4800000 | NULL | NULL | NULL | NULL | 2 | Not Affect | Not Affect | Gomes, Christina | Gosselin, Deb | 43410 | 0 | Changed split to 40% City. 60% other; cost forwarded by bumping up 10% ; Fall 2015: added City/County split for feasibility study to FY16 and bumped rest to FY18 and FY19; Fall 2016; moved to FY20/21; added art request 6/2017;Fall 18: spread to 20-22 | Improved customer service and environmental protection. | 897843 | 21400 | mfswMain.jpg | Gomes, Christina | Slotten, Cress | NULL | NULL | NULL | 1 | Washtenaw County | University of Michigan | Pittsfield Township | NULL | 1 | Customer Level of Service | Condition Analysis | Capacity Analysis | NULL | 1 | Ann Arbor Solid Waste Plan | NULL | NULL | NULL | Programmed | Planning | 83.73 | 1 | lack of partner and solid waste funding | McMurtrie, Tom | Partnership-County, Pittsfield, UM?-funding should acknowledge land acquisition by the City (solid waste fund). There is an existing Area Plan PUD (Preliminary Phase) through Pittsfield Twp. for this property; will need to follow the next approval steps. | Follow Pittsfield Township requirements. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | 0 | Minimal | 1 | 1 | NULL | 5 | 0 | Systems Planning | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 2 | 1 | 2 | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 2 | NULL | NULL | NULL | 2 | NULL | 1 | 1 | 1 | 2 | 55000 | 1
1045 | TR-SC-06-05 | Detroit Street Brick Rd Pavement Reconstruction | 2000000 | Central | Detroit Street (Catherine to 5th and Kingsley to N Division) | PUBLIC SERVICES | SYSTEM PLANNING | 11 | Restore condition of brick pavement | Reconstruct ex brick; place new conc. base, remove slate curb; historic district impacts/involvement; environmental contamination near N. Div; porous pavers; public involvement. DDA streetscape; art enhancement | Desirable | Yes | 1 | 12 | 8 | By replacing this brick street with brick pavement rather than with asphalt, the character of the area will be maintained while improving the streets for the travelling public. | the entire | 1 | 0 | This brick pavement is in extremely poor condition and in need of replacement. Applications will be made for TEA-21 grant funding as a historical pavement. Also, coordination with DDA is needed relative to their plans for improvements to North Fifth Ave | NULL | NULL | NULL | NULL | 0 | 3 | 2021 | 1 | 2023 | 220000 | 2 | 2023 | 4 | 2023 | 2780000 | NULL | NULL | NULL | 1000 | 2 | Not Affect | Decrease | Dykman, Dave | Hutchinson, Nick | 43418 | 0 | Removed funding - incorporated into new project Annual Street Resurfacing Program (tr-sc-13-06); then added costs back; has not broken out design. Added $1M for DDA streetscape. Updated schedule/funding. Fall 17: NC Fall 18 $ need to add 50K for art next | This project will help to ensure adequacy of the transportation system infrastrucuture. | NULL | NULL | trsc0605.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 52.09 | 25 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 2 | NULL | 3 | 3 | NULL | NULL | 0 | 1 | 1 | 2 | 50000 | 0
1056 | UT-WS-06-08 | WTP: Gravity and West High Boundary Valve Replacement | 400000 | West, Central | District boundary between Gravity and West High Service Districts | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Control leaking check valves across pressure district boundary. Consider replacing with stop valves. | Remove check valves and replace with isolation valves. Should be coordinated with road resurfacing. Consider replacing programmatically | Desirable | No | 0 | NULL | 2 | NULL | a subarea of the | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2021 | 1 | 2022 | 50000 | 3 | 2022 | 2 | 2023 | 350000 | NULL | NULL | NULL | NULL | 2 | Decrease | Not Affect | Wiczorek, Glen | Gosselin, Deb | 43438 | 0 | Fall 2015: Moved back to FY2022; Larry did not think these should be touched until the West High Elevated Tank is complete; Fall 2016: Fall 1* NC | Ensure adequacy of City infrastructure. | NULL | NULL | utws0608.jpg | Sanford, Larry | Wiczorek, Glen | Woodward, Nichole | briz | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 20.49 | 78 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1052 | UT-SN-06-01 | Valhalla Sanitary Sewer Service Extension | 1300000 | South | Valhalla Drive | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Install sanitary system, including lift station, to service several properties lacking service in area that is high priority for County Health Department | lift station required due to inability to obtain easement through U-M golf course; coordinate with water main work; gas main relocation needed; lack of public ROW requires grant of easement from all property owners; | Important | Yes | 1 | 23 | 1 | Extend service to area now served by septic. | a subarea of the | 1 | 0 | This will avoid problems with failed septic fields. | NULL | NULL | NULL | NULL | 110000 | 3 | 2023 | 4 | 2023 | 100000 | 2 | 2024 | 4 | 2024 | 1200000 | NULL | NULL | NULL | 2000 | 2 | NULL | Increase | Warrow, Anne | Gosselin, Deb | 42717 | 0 | Updated schedule; updated again 11/26/12. Officially closed out fiscally by Finance on 8/26/15 at cost of about $156,500.. Called it eliminated; Fall 2016: put back but in FY24/25 | Ensure adequacy of City infrastructure. | NULL | 13213 | utsn0601.jpg | Warrow, Anne | Baughman, Troy | Nearing, Mike | Amicangelo, Mike | Slotten, Cress | 1 | Citizen/Property Owner | NULL | NULL | County Health Department | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 41.93 | 17 | Moving slowly due to easement issues 10.08.13. Possibly need to go to condemnation. Would have to annex first. | Warrow, Anne | Relates to associated water project. | Will require significant cooperation between property owners. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Moderate | 0 | 1 | NULL | 8 | 0 | Project Management | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1055 | UT-WS-06-07 | WTP: Geddes and South East District Control Valve | 250000 | Northeast | Huron Parkway, between Washtenaw and Huron Hills Golf Course | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Remote control of a boundary valve between Geddes and SE High Service districts. | Add valve, valve pit with sump (or drainable), and remote control capability for added operation flexibility of water distribution system. Need to site based on pressure districting. Preliminary study underway as part of district modeling. | Important | No | 1 | NULL | 1 | The valve should allow flow in either direction for redundancy of supply to both districts. | a subarea of the | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2019 | 3 | 2019 | 50000 | 4 | 2020 | 2 | 2020 | 200000 | NULL | NULL | NULL | 500 | 2 | Not Affect | Increase | Wiczorek, Glen | Wiczorek, Glen | 43438 | 0 | None. Not cost forwarded Fall 2014 Fall 2016: changed schedule. faLL 17: PUT ALL IN fy20 Fall 18: updated | Ensure adequacy of City infrastructure. | NULL | NULL | utws0607.jpg | Sanford, Larry | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 26.43 | 68 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1078 | TR-SC-06-07 | State St (Kingsley to Fuller/Depot) Brick Pavement Reconstruction | 300000 | Central | North State Street, between Kingsley and Fuller/Depot | PUBLIC SERVICES | SYSTEM PLANNING | 11 | Reconstruction of the brick pavement on this downtown street. | Sidewalks with steps; steep grades between walk and b/curb. Slate curb; historic district impacts/involvement; possible porous pavers, in-line storm water detention; public involvement. Coordinate with water main. Evaluate bike lanes | Desirable | Yes | 1 | 13 | 2 | By replacing this brick street with brick pavement rather than with asphalt, the character of the area will be maintained while improving the streets for the travelling public | the entire | 1 | 0 | This brick pavement is in poor condition and in need of replacement. Applications will be made for TEA-21 grant funding as a historical pavement. | NULL | NULL | NULL | NULL | 0 | 3 | 2014 | 1 | 2016 | 0 | 2 | 2022 | 4 | 2022 | 750000 | NULL | NULL | NULL | 1000 | 2 | Not Affect | Decrease | Slotten, Cress | Gosselin, Deb | 43038 | 0 | Fall 2016: moved to FY23. Fall 17: NC | This project will help to ensure adequacy of the transportation system infrastrucuture. | NULL | NULL | trsc0607.jpg | Hutchinson, Nick | Nearing, Mike | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 42.86 | 34 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1085 | TR-SC-08-01 | Fuller Rd/Maiden Ln/East Medical Center Dr Area Rd. Design | 4563500 | Central | Intersection of Fuller Road and Maiden Lane/East Medical Center Drive | PUBLIC SERVICES | PROJECT MANAGEMENT | 11 | Intersection capacity, level of service and safety related to motorized and non-motorized users | Design improvemetns to address traffic needs in this area; consider roundabouts, road widenings, etc; also address non-motorized safety elements; may require bridge widening; coordinate with Border to Border and bridge improvements | Important | No | 1 | 24 | 2 | Improve traffic flow at the intersection and access to and from the University Hospital. Increase pedestrian safety and aesthetics. | the entire | 1 | 1 | NULL | 2 | 2006 | 1 | 2013 | 318700 | 2 | 2013 | 4 | 2024 | 1026000 | 2 | 2026 | 4 | 2026 | 0 | NULL | NULL | NULL | NULL | 0 | Not Affect | Not Affect | Nearing, Mike | Gosselin, Deb | 43434 | 0 | Updated status; schedule and funding.: need to add 500K for Fuller Rd paving. Fall 2016: updated per Nick's spreadsheet. Fall 17: updated per NH; Fall 18: renamed as desing only for now until needs are redefined | NULL | 292826 | 47311 | trsc0801.jpg | Dykman, Dave | Cooper, Eli | Sipowski, Les | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 65.28 | 2 | UM partnership | Dykman, Dave | DLZ Community Engagement and Design Consultant | TBD | NULL | NULL | NULL | NULL | 41061 | NULL | NULL | 1 | 1 | 1 | 0 | Severe | 1 | 0 | traffic maintenance | 9 | 0 | Project Management | No | NULL | 2005-058 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 3425509.02 | 2015-02-07 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 698905.86 | 2019-03-30 | NULL | 321061.36 | 630993.79 | 2254663.37 | NULL | NULL | 218790.51 | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 2 | NULL | 2 | NULL | 2 | NULL | 1 | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 100000 | 1
1101 | UT-WS-08-14 | WTP: South Industrial Tank Roof Repair and Painting | 500000 | South | 2000 South Industrial Highway | PUBLIC SERVICES | WATER TREATMENT | 14 | Address corrosion identified on underside of roof at S Industrial Tank. | Repair roof by coating areas where corrosion is apparent on tank interior roof. | Desirable | No | 0 | NULL | 3 | Repairing the coating system will extend the life ot the tank and prevent a potential structural failure. | the entire | 0 | 0 | Repair before coating failure could have structural consequences. | NULL | NULL | NULL | NULL | 0 | 4 | 2016 | 2 | 2017 | 50000 | 3 | 2017 | 2 | 2018 | 745000 | NULL | NULL | NULL | NULL | 0 | Not Affect | Not Affect | Wiczorek, Glen | Wiczorek, Glen | 42661 | 1 | None. Fall 2015: Moved to FY19 and upped budget to $600K; Fall 2016: GRW - expedited project. Fall 17: added additional funds; marked to be done by end of FY19 in Fall 2018 | NULL | 0 | 0 | utws0814.jpg | Steglitz, Brian | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | Water Treatment Plant Facilities Master Plan (2006) | NULL | NULL | NULL | Active | Construction | 24.95 | 71 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 666564 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1090 | UT-WS-08-05 | WTP: Filter Press Improvements | 400000 | West | Water Treatment Plant, 919 Sunset Rd. | PUBLIC SERVICES | WATER TREATMENT | 14 | Filter press plates have reached end of usable life; feed pumps are in need of repair or replacement; ancillary equipment is problematic | Replace filter press plates; switch to plastic plates from cast iron (cheaper, lighter, don't corrode); repair or replace feed pumps; hydraulic system improvements needed. | Desirable | No | 0 | NULL | 2 | Plates must be replaced because they have exceeded their useful life. | the entire | 0 | 0 | Replace plates prior to coating failure. | NULL | NULL | NULL | NULL | 0 | 3 | 2022 | 2 | 2023 | 150000 | 3 | 2023 | 2 | 2024 | 1500000 | NULL | NULL | NULL | NULL | 0 | NULL | Decrease | Wiczorek, Glen | Wiczorek, Glen | 43438 | 0 | Adjusted schedule. Fall 2015: moved to FY19; Fall 2016: renamed; GRW - scope of work and budget increased; schedule expedited due to criticality. Fall 18 updated | NULL | 0 | 0 | utws0805.jpg | Sanford, Larry | Steglitz, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 31.88 | 55 | Installation only, no design required. | Steglitz, Brian | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | None | 0 | 0 | NULL | 0 | 0 | WTP | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1089 | UT-WS-08-04 | WTP: Structural Repairs Project Phase 2 | 1750000 | West | Water Treatment Plant, 919 Sunset Rd. | PUBLIC SERVICES | WATER TREATMENT | 14 | Repair deteriorating concrete and brick at the Water Treatment Plant. | Repair deteriorating concrete and brick at the Water Treatment Plant; roof repairs; miscellaneous repairs | Important | No | 0 | NULL | 3 | Replacement/rehbabilitation of infrastruture before it fails is more cost effective then waiting until failure. Proper timing of this work reduce its net cost . | the entire | 0 | 0 | Work must be completed before structural failures increase the potential repair costs. | NULL | NULL | NULL | NULL | 0 | 3 | 2017 | 4 | 2018 | 125000 | 1 | 2019 | 4 | 2020 | 2400000 | NULL | NULL | NULL | NULL | 0 | Not Affect | Decrease | Wiczorek, Glen | Wiczorek, Glen | 43438 | 0 | Fall 2015: Moved FY16 to FY21 per B.S.; Fall 2016: GRW - changed schedule and reallocated budget Fall 18 updated | NULL | 1832701 | 1213082 | utws0804.jpg | Steglitz, Brian | Sanford, Larry | Wade, Molly | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | Water Treatment Plant Facilities Master Plan (2006) | NULL | NULL | NULL | Programmed | Inactive | 33.46 | 52 | NULL | Steglitz, Brian | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | None | 0 | 0 | NULL | 0 | 0 | WTP | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1091 | UT-WS-08-06 | WTP: Steere Farm Well Pump Engine Replacements | 1550000 | Pittsfield Twp. | Steere Farm | PUBLIC SERVICES | WATER TREATMENT | 14 | Remote control capability for Steere Farm Well pump engines. | Replace engines with dual-drive engines capable of operating on electric as well as natural gas. Provide capability of remote start/stop. | Urgent | No | 0 | NULL | 2 | Wells are a critical component of the source water for the water treatment plant. Without reliable pump engines, the reliability of the well supply to the plant is jeopardized. | the entire | 1 | 0 | Project to be initiated before major overhaul of engines is required. | 4 | 2014 | 2 | 2015 | 30500 | 3 | 2015 | 3 | 2016 | 289500 | 4 | 2016 | 2 | 2018 | 3360000 | NULL | NULL | NULL | NULL | 0 | Decrease | Decrease | Wiczorek, Glen | Wiczorek, Glen | 42684 | 1 | Fall 2015: Kept $250K for design in FY16 and increased FY 17 to be construction at $2.75M per B.S. Fall 2016: spread costs per anticipated spending;marked to be done by end of FY19 in Fall 2018 | NULL | 0 | 0 | utws0806.jpg | Steglitz, Brian | Brix, Andrew | Naud, Matt | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 1 | Water Treatment Plant Facilities Master Plan (2006) | NULL | NULL | NULL | Active | Construction | 57.52 | 5 | NULL | Steglitz, Brian | NULL | Public education for alternative energy component. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 0 | Minimal | 1 | 0 | Electrial power access? | 5 | 0 | WTP | Unknown | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 3009318 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1094 | TR-AP-08-02 | New Corporate Hangar | 1000000 | Pittsfield Twp. | Airport | PUBLIC SERVICES | FLEET & FACILITY | 5 | New corporate hangar near terminal | Economy driven for need | Important | No | 0 | NULL | 1 | Provide additional revenue and expand airport capacity | the entire | 0 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 4 | 2022 | 1 | 2024 | 70000 | 2 | 2023 | 4 | 2023 | 930000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | Kulhanek, Matt | Gosselin, Deb | 42691 | 0 | Fall 2016: moved to FY2020 | NULL | 0 | 0 | trapMain.jpg | Kulhanek, Matt | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | Tenants | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 21.25 | 10 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 0
1093 | UT-WS-08-07 | Dams: Barton Pond Early Warning System | 325000 | West | Barton Pond | PUBLIC SERVICES | WATER TREATMENT | 14 | Provide water quality monitoring in Huron River to provide early warning in the event of a river contamination event. | Determine location and type of monitors to install. Coordinate with automated water quality monitoring system (stormwater project; DWRF project. Coordinate with Surface Water Intake Protection Plan (SWIPP). Added USGS Gauging Station upstream of Barton. | Important | No | 0 | NULL | 1 | Protects drinking water supply for the City. Portion of project will be coordinated with water quality monitoring project (stormwater) | the entire | 0 | 0 | Per recommendations of Master Plan - 2006. | 3 | NULL | 3 | NULL | 0 | 3 | 2021 | 4 | 2021 | 25000 | 3 | 2021 | 2 | 2022 | 300000 | NULL | NULL | NULL | NULL | 0 | Increase | Increase | Wiczorek, Glen | Gosselin, Deb | 43438 | 0 | Adjust project funding schedule. Changed schedule again Fall 2103; In Fall 2015, moved design from FY17 to FY18; Fall 2016: moved to FY19/20. Ffall 17: put all funds in FY20 Fall 18 updated | NULL | 0 | 0 | utws0807.jpg | Robinson, Molly | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 33.46 | 52 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1099 | UT-WS-08-12 | WTP: Steere Farm New Well | 1900000 | Pittsfield Twp. | Steere Farm | PUBLIC SERVICES | WATER TREATMENT | 14 | Increase well water supply capacity for water treatment plant. | Develop new well at Steere Farm. | Important | No | 0 | NULL | 1 | Improves reliability of potable well water supply for the water system. Well water is critical to the treatment process as well as provides a back-up supply if the river supply is not available. | the entire | 0 | 0 | Improve reliability of the well water supply for the City's drinking water. | 3 | 2022 | 1 | 2023 | 200000 | 3 | 2023 | 1 | 2024 | 100000 | 4 | 2024 | 2 | 2025 | 1600000 | NULL | NULL | NULL | NULL | 0 | Increase | Increase | Wiczorek, Glen | Wiczorek, Glen | 43438 | 0 | Fall 2016: changed schedule to FY21 and beyond and spread costs Fall 18: pushed back | NULL | 0 | 0 | utws0812.jpg | Steglitz, Brian | Sanford, Larry | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 1 | Water Treatment Plant Facilities Master Plan (2006) | NULL | NULL | NULL | Programmed | Inactive | 18.51 | 82 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1103 | TR-AT-08-02 | Shared Use Path: Northeast Area | 365000 | Northeast | Pontiac Trail to Bandemer Park, in former Huron Parkway extension right-of-way | PUBLIC SERVICES | SYSTEM PLANNING | 6 | Construct a non-motorized trail as recommended in the Northeast Area Transportation Plan | Trail currently being used as unimproved, mountain bike trail; approximate length is 3555 LF | Desirable | No | 0 | NULL | 5 | NULL | a subarea of the | 1 | 0 | Allocation of federal funding and MDOT permits/easements must be secured | 1 | 2017 | 2 | 2017 | 0 | 3 | 2025 | 4 | 2025 | 75000 | 2 | 2026 | 4 | 2026 | 925000 | NULL | NULL | NULL | NULL | 0 | Not Affect | Increase | Cooper, Eli | Cooper, Eli | 42690 | 0 | Project moved to end of CIP period for planning and design. Updated schedule. Fall 2016: moved to 23/24. Fall18: updated cost to $1M based on Wastnenaw path and inflated; ; needs more thought | NULL | 0 | 0 | trat0802.jpg | Slotten, Cress | Kuras, Amy | Rampson, Wendy | Cooper, Eli | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 44.02 | 27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1108 | UT-SN-08-02 | Dover Place/Riverview Sanitary Sewer | 500000 | Northeast | Dover Place and Riverview Drive off of Geddes Avenue | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Extend sanitary sewer to service homes on septic systems; | Extend sanitary sewer to service homes presently on septic systems; Twp. Parcels. Coordinates with water project | Desirable | No | 1 | 7 | 1 | Removes properties from septic systems | a subarea of the | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 2 | 2017 | 4 | 2018 | 75000 | 2 | 2019 | 3 | 2019 | 988400 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | Nearing, Mike | Gosselin, Deb | 43045 | 0 | Updated cost estimate and schedule. Changed schedule to match programming for water on 11/26/12. Fall 2015: moved to FY20 pending any petition. Fall 2016: upped dollars and spread costs and schduled in FY2018/19. Fall 17:NC Fall 18: $ updated | NULL | 0 | 0 | utsn0802.jpg | Slotten, Cress | Rolla, Liz | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 44.18 | 13 | NULL | Rolla, Liz | Coordinate with water project. Improvement charges. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 0 | Moderate | 0 | 1 | NULL | 7 | 0 | Project Management | No | NULL | 2013-037 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 118930.87 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1107 | UT-SN-08-01 | Wagner Road Sanitary Sewer - South | 475000 | West | Wagner Road, between Liberty Road and Jackson Plaza | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Extension of sanitary sewer to service the remaining properties on the east side (city service side) of Wagner Road with sanitary sewer. | Wagner Road is WCRC jurisdiction for permitting; existing sanitary sewer for joint use is Scio Township's; In May 2016, a citizen stopped in to request expediting this project and indicated that several other neighbors are also very interested | Desirable | No | 0 | NULL | 1 | Removes properties from septic systems (some of which may be failing) near Sisters Lakes | a subarea of the | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 4 | 2022 | 1 | 2023 | 45000 | 2 | 2023 | 3 | 2024 | 555000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 43046 | 0 | Project is on hold due to no request from any property owner. UPDATED MAY 2016 (SEE ABOVE) Updated cost by 25% in Fall 2014 since its inclusion in the plan was years ago; Fall 2016: left in FY19 but can be moved later. Fall 17: moved back | NULL | 100000 | 11177 | utsn0801.jpg | Kotlyar, Igor | Wooden, Dan | Slotten, Cress | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | On Hold (comment required) | 44.18 | 13 | NULL | Kotlyar, Igor | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1111 | UT-SN-08-05 | Geddes Ave (Huntington to Hickory) Sanitary Sewer | 1405000 | Northeast | Geddes Avenue between Huntington and Heatherway and additional areas within extension of sewer. | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Construction of an 8" sanitary sewer to serve properties on Geddes Avenue currently on septic systems | Construct sanitary sewer; coordinate with road construction and stormwater projects. Recognition of other possible needs in corridor. | Important | Yes | 1 | 7 | 1 | Replaces septic systems | a subarea of the | 1 | 0 | Need to coordinate with other work in the area. | 1 | 2013 | 2 | 2013 | 75000 | 3 | 2013 | 4 | 2014 | 45000 | 2 | 2015 | 4 | 2015 | 1285000 | NULL | NULL | NULL | NULL | 0 | Increase | Increase | Slizewski, Brian | Gosselin, Deb | 41968 | 1 | Updated schedule; revised revenue on 1/26/12 to reflect prior year funding as all tied up in 2013; showed funds being used in 2015 | NULL | 225000 | 0 | utsn0805.jpg | Rolla, Liz | Pulcipher, Connie | Slotten, Cress | Pirooz, Homayoon | Selvig, Beverly | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 43.92 | 20 | Survey work being done. | Rolla, Liz | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 0 | 1 | Moderate | 0 | 1 | NULL | 7 | 0 | Project Management | NULL | NULL | 2013-037 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 524227.75 | 2017-02-24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1507066 | 2019-03-30 | NULL | 68048 | 70974 | 385205.75 | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1900 | UT-WS-18-01 | Maywood Water Main Replacement | 840000 | NULL | Maywood | NULL | NULL | 14 | Replace againg main | Coordinate with Maywood stormwater project | NULL | No | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 0 | 2 | 2019 | 2 | 2019 | 840000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Humphriss, Tesha | Baughman, Troy | 43389 | 0 | Fall 2016: new; March 2019 CPAN: added Hartford Place to Scope; eval 6" main size to reduce risk of stagnant water in neighborhood; 2018 added Hartford & Maywood, cost updated; Feb 2019 reduced scope to only Maywood and used -59 for Dunmore etc | NULL | 0 | 0 | UTWS1801.jpg | Baughman, Troy | Slizewski, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 30.49 | 59 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | 50000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 193283.73 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1116 | UT-SN-08-10 | Parkwood/Fernwood Crosslots Sanitary Lining/Repair | NULL | South | Between Parkwood and Fernwood, north of Packard and east of Platt Road | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Repair, replacement or lining of the existing crosslots 8" sanitary sewer | NULL | Urgent | No | 0 | NULL | NULL | This exisitng sewer is in a failing condition, and in critical need or repair, replacement or lining. In addition, the sewer is near or under an existing private structure (garage). | the entire | 0 | 0 | This existing sewer is in a failing condition, and in critical need or repair, replacement or lining. In addition, the sewer is near or under an existing private structure (garage). | NULL | NULL | NULL | NULL | 0 | 3 | 2007 | 4 | 2007 | 30000 | 4 | 2007 | 4 | 2007 | 200000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | Anne Warrow | 39777 | 1 | New project | NULL | 15000 | 15232 | utsn0810.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Completed | 41.43 | 14 | NULL | Hutchinson, Nick | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1124 | MF-PR-08-07 | Tennis & Basketball Court Renovations | 1050000 | TBD | Citywide | COMMUNITY SERVICES | PARKS & RECREATION | 3 | Staff to evaluate need on annual basis | Burns Park, Cranbrook, Pilgrim, and SE Area Park basketball courts. Consider rain garden and other improvements to offset imperviousness. | Urgent | No | 0 | NULL | 3 | Upgrade aging facilities | the entire | 1 | 0 | Scheduled as required per condition of courts | NULL | NULL | NULL | NULL | 0 | 1 | 2011 | 2 | 2017 | 50000 | 3 | 2011 | 2 | 2024 | 1500000 | NULL | NULL | NULL | NULL | 0 | Not Affect | Not Affect | Smith, Colin | Smith, Colin | 43431 | 0 | (formerly Sport Court Renovations). Funding added for 2021. Wheeler, Hunt, Allmendinger done. Fall 2015: Added in FY17, $50K from Packard Square for a park in that area and reduced Parks contribution accordingly; Fall 2016: Added FY23 $ Fall 18 update | NULL | 0 | 0 | Citywide.jpg | Warba, Matt | Smith, Colin | Kuras, Amy | pennington, Tracy | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | Condition Analysis | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Active | Construction | 49.97 | 13 | West Park tennis court reconstruction approved by City Council. | Kuras, Amy | Includes retaining wall, shuffleboard court and pathway work at West Park; construction budget is $200,000 | Part of the West Park master plan - for information only. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 0 | 0 | Minimal | 0 | 0 | NULL | 2 | 0 | Parks and Recreation | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | 2 | 1 | 2 | 1 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1144 | UT-WS-08-27 | Traver Rd PRV (between Barton and Leslie Golf Course) | 100000 | Northeast | Traver Road between Barton and Leslie Golf Course | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Installation of a pressure reducing valve in a vault for expansion of an existing reduced pressure zone. | Installation of a pressure reducing valve in a vault for expansion of an existing reduced pressure zone. | Desirable | No | 0 | NULL | 1 | Allows closed valve to be opened allowing flow during pressure drops. | a subarea of the | 1 | 0 | Completion of Hideaway Lane development anticipated for 2008. | NULL | NULL | NULL | NULL | 0 | 3 | 2020 | 4 | 2020 | 25000 | 4 | 2021 | 3 | 2021 | 75000 | NULL | NULL | NULL | NULL | 0 | Not Affect | Increase | Woodward, Nichole | Gosselin, Deb | 43439 | 0 | Update schedule. No change in 11/12. Fall 2106: NC. Fall 17: NC Fall 18; moved ot FY21 as not done | NULL | 0 | 0 | utws0827.jpg | Heatley, Alison | Steglitz, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 15.25 | 84 | Priority desirable, contact TBD. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1165 | UT-ST-08-11 | Marlborough Storm Main Replacement | 150000 | South | Marlborough Street | PUBLIC SERVICES | SYSTEM PLANNING | 13 | Replacement of failing (failed?) storm main | Storm system connects into County Drain (Malletts Creek), permit/coordination required | Important | No | 0 | NULL | 2 | Sewer is failing/has failed to the point that maintenance cannot be performed on the line. | a subarea of the | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2021 | 4 | 2021 | 0 | 2 | 2022 | 4 | 2022 | 520000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | Matthews, Paul | Gosselin, Deb | 43423 | 0 | Updated Scheduled; updated again in 11/12. Costs not updated Fall 2014. Fall 2016: moved out; costs look really low but not touched. Fall 17: NC | NULL | 0 | 0 | utst0811.jpg | Ernst, Kevin | Warba, Matt | Woodward, Nichole | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 15.95 | 39 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
1185 | UT-WS-08-34 | Detroit Street Brick Rd Water Main Replacement | 490000 | Central | Detroit Street (Catherine to 5th and Kingsley to N Division) | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Replace approximately 1500 feet of 6-inch ductile iron pipe water main on Detroit Street. | coordinate with stormwater improvements, street reconstruction, HDC. Confirm sizing funding source | Desirable | Yes | 1 | 12 | 2 | Eliminate water quality issues and prevent costly main break repairs. | a subarea of the | 1 | 0 | Perform with brick replacement project. | NULL | NULL | NULL | NULL | 0 | 3 | 2019 | 4 | 2019 | 85000 | 2 | 2020 | 4 | 2020 | 1115000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Updated Schedule; costs not updated Fall 2014. Fall 2106: costs not updated; 2018 cost upated and to FY25 with street | NULL | 0 | 0 | utws0834.jpg | Slotten, Cress | Baughman, Troy | Sanford, Larry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Capacity Analysis | Condition Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 34.65 | 46 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1186 | UT-WS-08-35 | State St (Kingsley to Fuller/Depot) Water Main Replacement | 235000 | Central | North State Street between Kingsley and Fuller/Depot | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Replace approximately 750 feet of 6-inch ductile iron pipe on North State Street | Coordinate with N State St. main replacement and brick repaving; confirm sizing of new main | Desirable | Yes | 1 | 13 | 2 | Eliminate water quality issues and prevent costly main break repairs. | a subarea of the | 1 | 0 | Perform with brick replacement project. | NULL | NULL | NULL | NULL | 0 | 3 | 2024 | 4 | 2024 | 25000 | 2 | 2025 | 2 | 2025 | 210000 | NULL | NULL | NULL | NULL | 0 | Not Affect | Decrease | Slotten, Cress | Gosselin, Deb | 43046 | 0 | Updated schedule; costs not updated Fall 2014. Fall 2016: moved to FY23 to match road; costs not updated. Fall 17: NC Fall 18; | NULL | 0 | 0 | utws0835.jpg | Slotten, Cress | Zink, Denny | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 21.19 | 76 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1189 | MF-SW-08-01 | Solid Waste Management Plan Update (2013-2017) | NULL | City-wide | NULL | NULL | NULL | 15 | Update the City's Five-Year Solid Waste Management Plan | potential of inclusion within city's master plan | Important | No | 0 | NULL | 4 | NULL | the entire | 1 | 0 | NULL | 3 | 2011 | 2 | 2013 | 25000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | McMurtrie, Tom | Cresson Slotten | 39762 | 1 | NULL | NULL | 0 | 0 | Citywide.jpg | Slotten, Cress | Rampson, Wendy | Stone, Nancy | FOS Solid Waste | Naud, Matt | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | NULL | NULL | 1 | Ann Arbor Solid Waste Management Plan | NULL | NULL | NULL | Active | Inactive | 31.31 | 8 | NULL | McMurtrie, Tom | Sustainability Framework Plan integration? | typical master plan process involvement | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Minimal | 0 | 0 | NULL | 5 | 0 | Systems Planning | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1206 | MF-PR-08-21 | Recreation Facility Updates and Infrastructure Repairs | 2205000 | City-wide | Various Recreational Facilities in Park System | COMMUNITY SERVICES | PARKS & RECREATION | 3 | Perform upgrades to facility infrastructure. Projects to be determined through needs assessment or as identified by staff on an annual basis. | Potential projects include: pool and rink mechanical upgrades. Incorporate Honeywell audit recommendations where feasible. Docks at Gallup and Dolph. Cobblestone and Farmers Market restroom upgrades | Urgent | No | 0 | NULL | 3 | Will maintain or improve facility infrastructure and services provided to the community. | a subarea of the | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2010 | 3 | 2019 | 50000 | 3 | 2010 | 2 | 2024 | 3905000 | NULL | 1000 | NULL | 1000 | 0 | Decrease | Decrease | Smith, Colin | Smith, Colin | 43431 | 0 | Updated funding. Established annual pots in 12/12 Fall 2016: updated funding and added in outer years. Fall 17: added $150K to FY19). Fall 18 updated | NULL | 115000 | 0 | Citywide.jpg | Warba, Matt | Smith, Colin | Landefeld, Josh | NULL | Simon, Dennis | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Active | Construction | 81.93 | 1 | Veterans Pool Locker rooms approved by City Council. Buhr Ice Arena steel paint complete. Gallup Canoe Livery entry improvements - MDNR Trust Fund grant pending. | Kuras, Amy | NULL | Continuing | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Moderate | 1 | 1 | Grant agreement with MDNR | 9 | 0 | Parks and Recreation | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | 1 | 2 | NULL | 2 | 1 | 2 | 1 | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 0
1219 | TR-SC-09-03 | Stadium Blvd (Main to Kipke) Road Reconstruction | NULL | South | Stadium Boulevard (Main to Kipke) | PUBLIC SERVICES | PROJECT MANAGEMENT | 11 | Poor pavement condition; reconstruct roadway in accordance with Complete Streets Policy; replace failing retaining wall along south side at AAGO Property; complete sidewalk gap along south side in front of AAGO property. | Roadway Reconstruction - Complete Streets; replace/upgrade water main; storm water improvements in accordance with Green Streets; address sight distance issue on south side of S. Main Street intersection. | Urgent | Yes | 1 | 2 | 2 | NULL | NULL | 1 | 0 | To prevent further pavement deterioration and capture Federal STPU funds | NULL | NULL | NULL | NULL | 0 | 1 | 2014 | 2 | 2016 | 1019100 | 4 | 2016 | 4 | 2017 | 8063550 | NULL | NULL | NULL | NULL | NULL | Not Affect | Decrease | Nearing, Mike | Nearing, Mike | 43038 | 1 | Revised limits of project in Summer 2016 due to bid prices. Fall 17: NC | NULL | 0 | 0 | TRSC0903.jpg | Slotten, Cress | Rolla, Liz | Nearing, Mike | Sheehan, Harry | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 59.38 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2014-035 | NULL | NULL | 1370267.11 | NULL | 10664000 | NULL | NULL | 1 | 2016 | 3 | 2016 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1.564 | 7693610.73 | 2016-08-08 | 5255940.73 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1224 | UT-ST-09-04 | Stadium Blvd (Main to Kipke) Storm Sewer Replacement | 945000 | South | Stadium Boulevard - 500' east of Hutchins to Kipke Drive | PUBLIC SERVICES | PROJECT MANAGEMENT | 13 | Provide storm sewer upgrades and reconfiguration consistent with roadway reconstruction activities. Construct storm water infiltration/in-line detention for proposed storm sewer. | In past SRF project plan. First-flush and bank-full detention. Public involvement/engagement to be performed with roadway project. | Urgent | Yes | 1 | 2 | 2 | NULL | NULL | 0 | 0 | Part of the Stadium Boulevard Reconstruction Project (TR-SC-09-03) | NULL | NULL | NULL | NULL | 0 | 3 | 2014 | 2 | 2016 | 132800 | 3 | 2016 | 3 | 2017 | 1342700 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 43017 | 1 | Adjusted schedule to reflect re-bidding of project due to inflated construction pricing received in February 2016. See Project TR-SC-09-03 for complete cost breakdown of the work. Fall 17; marked TBC | NULL | 0 | 0 | UTST0904.jpg | Nearing, Mike | Rolla, Liz | Sheehan, Harry | Carson, Chris | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 48.02 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | NULL | Yes | NULL | 2014-035 | NULL | NULL | 140700 | NULL | 1334855 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1312400 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1230 | TR-AP-10-01 | Six Box Hangers | 1000000 | South | Airport | PUBLIC SERVICES | FLEET & FACILITY | 5 | Additional tenant space | Timing based on market demand. | Important | Yes | 0 | 28 | 1 | NULL | NULL | 0 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 4 | 2021 | 1 | 2022 | 100000 | 2 | 2022 | 4 | 2022 | 900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kulhanek, Matt | Gosselin, Deb | 42691 | 0 | adjust schedule; Fall 2016: moved to FY2020 | NULL | 0 | 0 | TRAP1001.jpg | Kulhanek, Matt | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | Tenants | 1 | Capacity Analysis | NULL | NULL | NULL | 1 | AIP Capital Improvement Plan | NULL | NULL | NULL | Programmed | Inactive | 22.27 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 0 | NULL | NULL | 0
1246 | UT-SN-10-05 | Sanitary Sewer System Public Works Capital Maintenance | 1150000 | Citywide | Programmatic, locations TBD by field staff | PUBLIC SERVICES | FIELD OPERATIONS | 12 | Manhole structures are failing - citywide | Repair/replace structures to allow access for maintenance. | Important | No | 0 | 0 | 2 | Provides safe access for maintenance of sanitary sewer. | a subarea of the | 0 | 0 | Repair before access is needed for future maintenance. | NULL | NULL | NULL | NULL | 0 | 1 | 2013 | 2 | 2013 | 50000 | 3 | 2013 | 2 | 2023 | 4025000 | NULL | NULL | NULL | NULL | NULL | Not Affect | Decrease | Elenbaas, Chris | Gosselin, Deb | 42668 | 0 | Funding updated for biannual rehab. Fall 2016: Changed name and funding for Public Works to do manhole replacement, small lining, etc. | NULL | 0 | 0 | UTSN1005.jpg | Hupy, Craig | Wooden, Dan | Ernst, Kevin | Cozart, Mark | Baughman, Troy | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 36.51 | 25 | multiyear projects | Woodward, Nichole | Cooridnated with input from PM, SPU, and FO to selct best use of funds, Huron/Washtenaw/Zina Pitcher mentioned; also Arborview | notification of street closures | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | 0 | Minimal | 0 | 0 | NULL | 3 | 0 | Field Operations | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1247 | UT-WS-10-01 | Dams: Barton Dam Coating and Structural Steel Repairs | 400000 | West | Barton Dam | PUBLIC SERVICES | WATER TREATMENT | 14 | Re-coat structural steel to extend life of asset | Blast and remove existing coating system, and re-coat all structural steel. Must determine if scope includes coating of both wet and dry sides. | NULL | No | 0 | 0 | 3 | Extend life of the asset. | the entire | 0 | 0 | Based on expected life of coating system. | NULL | NULL | NULL | NULL | 0 | 3 | 2020 | 1 | 2021 | 50000 | 3 | 2021 | 2 | 2022 | 750000 | NULL | NULL | NULL | NULL | NULL | Not Affect | Decrease | Wiczorek, Glen | Gosselin, Deb | 43438 | 0 | Fall 2016: Updated schedule based on results from FERC inspection. Fall 17: pushed back one year Fall 18 to Fy21-22 | NULL | 0 | 0 | UTWS1001.jpg | Steglitz, Brian | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.81 | 37 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1251 | MF-SW-10-01 | Single Stream Recycling | NULL | Citywide | City-wide | PUBLIC SERVICES | SYSTEM PLANNING | 15 | Need to increase recycling | NULL | Important | No | 0 | 0 | NULL | Increases collection efficiencies and increase public convenience | the entire | 1 | 0 | NULL | 3 | 2009 | 4 | 2009 | 30000 | NULL | NULL | NULL | NULL | 0 | 1 | 2010 | 2 | 2011 | 5500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Tom McMurtrie | 39767 | 1 | NULL | NULL | 0 | 0 | MFSW1001.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Implementation | NULL | NULL | NULL | McMurtrie, Tom | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1256 | UT-SN-10-06 | Michigan Stadium Sanitary Sewer Reroute | 700000 | Central | University of Michigan Stadium at South Main and Berkley | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Remove city sanitary sewer flow from pipes located beneath the UM Stadium. Eliminate O&M and liability issues for this location. | Reroute city sanitary sewage flow out of UM Stadium. Convert Sanitary lines beneath the stadium to private sewer. Coordinate work with Main Street corridor work. A portion of the work will involve deep construction. | Desirable | No | 0 | 0 | 2 | Improves ability to properly maintain this section of the collection system. Removes potential liabilty for backups upstream or in the stadium due to pipe failures at this location and eliminates the potential for costly repairs and restoration. | a subarea of the | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2023 | 4 | 2023 | 150000 | 2 | 2024 | 4 | 2024 | 1950000 | NULL | NULL | NULL | NULL | NULL | Not Affect | Decrease | Baughman, Troy | Baughman, Troy | 42664 | 0 | Updated cost. Assumed re-route would be contained in ROW (from Berkley/Main northerly to Keech, easterly to Green, northerly to terminal MH in Greene). Route could be re-examined. Fall 2016: moved out and spread. Fal 18 NC | NULL | 0 | 0 | UTSN1006.jpg | Hupy, Craig | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 36.51 | 25 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1262 | UT-WS-10-06 | Washtenaw Ave (South University to Wayne Street) Water Main Upgrade | 560000 | Central | Washtenaw (between South University & Wayne Street) | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Fire flow improvement; age and size | Location within ROW TBD; permit from MDOT; Outcome from New Life Church lawsuit settlement | Desirable | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2020 | 4 | 2020 | 75000 | 2 | 2021 | 4 | 2021 | 1025000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | 2016 - cost updated; assumed project will not be done as part of a larger road project. Fall 17: NC; 2018 cost updated and moved back | NULL | 0 | 0 | UTWS1006.jpg | Baughman, Troy | Hupy, Craig | Slotten, Cress | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 36.04 | 43 | NULL | Baughman, Troy | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1264 | TR-AP-10-02 | Airport Looping Water Main | 330000 | South | City Airport | PUBLIC SERVICES | FLEET & FACILITY | 5 | Completion of water main loop identified during plan review of new box hangars | Twp. involvement with connecting to Twp. main in Ellsworth. Backflow prevention. | Urgent | No | 0 | 0 | 1 | NULL | a subarea of the | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 4 | 2021 | 1 | 2022 | 30000 | 2 | 2022 | 3 | 2022 | 300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kulhanek, Matt | Gosselin, Deb | 42691 | 0 | Tied to the construction of new box hangars. Schedule adjustment. Fall 2106: moved to FY2020; costs not adjusted | NULL | 0 | 0 | TRAP1002.jpg | Kulhanek, Matt | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.9 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1267 | MF-CB-10-05 | Guy C. Larcom Municipal Building: Primary Chiller Replacement | 200000 | Central | Guy C. Larcom Municipal Building | PUBLIC SERVICES | FLEET & FACILITY | 1 | Aging, inefficient unit nearing the end of it's life cycle; annual maintenance and rehab costs increasing; | Will be smaller, more efficient unit than existing | Important | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 4 | 2015 | 1 | 2016 | 0 | 3 | 2017 | 2 | 2018 | 280000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kulhanek, Matt | Gosselin, Deb | 42661 | 1 | No change in 12/12; Council pushed back at Spring 2013 capital budget Fall 2016: upped budget | NULL | 0 | 0 | MFCB1005.jpg | Crum, Lynn | Kulhanek, Matt | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 28.76 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1271 | TR-AP-10-03 | Runway Safety Extension Environmental Assessment | NULL | Couth | Runway 6-24 | PUBLIC SERVICES | FLEET & FACILITY | 5 | Required to move forward with Runway Safety Extension Project | NULL | Urgent | NULL | 0 | 0 | NULL | NULL | NULL | 0 | 0 | NULL | 2 | 2009 | 1 | 2015 | 270000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kulhanek, Matt | Cresson Slotten/Matt Kulhanek | 39777 | 1 | New project | NULL | 0 | 0 | TRAP1003.jpg | Kulhanek, Matt | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | AIP Capital Improvement Plan | NULL | NULL | NULL | Active | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1272 | TR-AP-10-04 | Runway Safety Extension | 2135000 | South | Airport (Runway 6-24) | PUBLIC SERVICES | FLEET & FACILITY | 5 | Addressing local safety concerns - clearance at State Road (15-foot minimum) and Part 77 Transitional Surface (steep approach angle); line of sight problem from tower; runway overruns. | B2 aircraft critical aircraft under state (4300-foot runway recommended), existing runway 3500 feet; Consider State Rd Corridor Study recommendations; shifting runway to southwest to address safety concerns; LED's; include approach study; rehabilitate WC | Urgent | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2020 | 1 | 2021 | 398000 | 2 | 2021 | 4 | 2021 | 3466000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kulhanek, Matt | Gosselin, Deb | 43423 | 0 | Updated schedule; could still go in FY14 but no action as of 9/12/13 on the ESA; Fall 2016: moved to 2018 and costs updated; Fall 17: shifted to FY19 as NEPA still in public response; Fall 18: FAA change scope; 9 month review + 12 months | NULL | 0 | 0 | TRAP1004.jpg | Kulhanek, Matt | Crum, Lynn | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | AIP Capital Improvement Plan | NULL | State Road Corridor Study (Pittsfield) | NULL | Programmed | Inactive | 54.08 | 2 | Removed by Council from FY2012-2017 CIP (February 2011); EA submitted to FAA in Nov 2010 and is awaiting final determiniation of FONSI. | Kulhanek, Matt | NULL | Robust (both city residents and non-city residents) | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | 0 | Severe | 1 | 1 | NULL | 9 | 0 | Fleet and Facilities | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | 1 | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1279 | UT-WS-10-07 | Water Laboratory Information Management System | NULL | West | 919 Sunset Road | PUBLIC SERVICES | WATER TREATMENT | 14 | Process and Lab Data management systems are cumbersome and outdated. It is difficult to retrieve data and reporting functions are limited. | Replace informal spreadsheet data management system with comprehensive Laboratory Information Management System (LIMS). | Important | No | 0 | 0 | 1 | More efficient management of data, better reporting, and easier retrieval of information. | the entire | 0 | 0 | Lab currently tracks using spreadsheets. Is cumbersome to use, has limited functionality and is maintenance intensive. Replacing with a LIMS will improve lab efficiency, increase functionality and storage data. | 3 | 2010 | 4 | 2010 | 0 | NULL | NULL | NULL | NULL | 0 | 1 | 2011 | 2 | 2011 | 110000 | NULL | NULL | NULL | NULL | NULL | Decrease | Not Affect | Robinson, Molly | Molly Robinson | 40520 | 1 | New project. | NULL | 0 | 0 | UTWS1007.jpg | Robinson, Molly | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | NULL | NULL | Contract awarded | Robinson, Molly | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1283 | TR-AT-10-04 | Non-Motorized Corridor Project: Liberty (State Street to City Boundary) | 178000 | Central, West | Liberty St from downtown to City boundary | PUBLIC SERVICES | SYSTEM PLANNING | 6 | Non-Motorized Plan Implementation | Bike Lane, Sharrows, Major Mid Block Crossings, Sidewalk - new construction | Important | NULL | 0 | 0 | 1 | C | a subarea of the | 1 | 0 | Changed dates as project was delayed due to emphasis on ARRA funded improvements. | 1 | NULL | 2 | NULL | 0 | 1 | 2013 | 2 | 2013 | 0 | 3 | 2013 | 4 | 2013 | 40000 | NULL | NULL | NULL | NULL | NULL | Not Affect | Increase | Cooper, Eli | Eli Cooper | 41222 | 1 | Updated dates. Assigned to Pat Cawley in spring 2013; much of this work has been completed with other projects so budget was adjusted downward; remaining work is pavement markings, signal heads, and maybe curb ramps | NULL | 0 | 0 | TRAT1004.jpg | Cooper, Eli | Cawley, Pat | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | AnnArbor Transportation Plan Update (2009) | NULL | NULL | Active | Planning | 43.12 | 23 | NULL | Cooper, Eli | near-term recommendations from No-Mo Plan | public information only | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | Minimal | 0 | 0 | NULL | 1 | 0 | Systems Planning | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1284 | TR-AT-10-05 | Main St (Eisenhower to M-14 Ramp) Non-Motorized Corridor Project | 397000 | West, Central, South | Main Street | PUBLIC SERVICES | SYSTEM PLANNING | 6 | Non-motorized Plan implementation | Bike Lanes, Sharrows, Major Mid block crossing, sidewalk construction. Coordinate North Main Vision Task Force. | Important | No | 1 | 43 | 1 | NULL | a subarea of the | 1 | 0 | Project budget too large for one budget cycle. | 3 | NULL | 4 | NULL | 0 | 3 | 2020 | 4 | 2020 | 15000 | 2 | 2021 | 4 | 2021 | 183500 | NULL | NULL | NULL | NULL | NULL | Not Affect | Increase | Cooper, Eli | Gosselin, Deb | 43434 | 0 | Minor updates to description and identification of source. Fall 2106; moved to FY20 to allow time to evaluate mid-block crossings etc.; some work may be done. Fall 18: moved to FY22 to match MDOT project and adjusted to available funds | NULL | 0 | 0 | TRAT1005.jpg | Cooper, Eli | Cawley, Pat | Kuras, Amy | Nearing, Mike | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | AnnArbor Transportation Plan Update (2009) | NULL | NULL | Programmed | Inactive | 54.62 | 14 | NULL | Cooper, Eli | near-term recommendations from No-Mo Plan; multiple constraints/issues along North Main, RR overpass to Huron River Drive; South Main Stadium to AA-Saline, recalcitrant owners along route (AAGO & U-M) | public information only | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | 0 | Minimal | 0 | 0 | NULL | 2 | 0 | Systems Planning | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1289 | TR-TR-12-17 | Queue Jump Lanes: Washtenaw Avenue | 3440000 | Northeast | Between US 23 and Platt Road. Three signalized Intersections | PUBLIC SERVICES | SYSTEM PLANNING | 16 | Increased reliability and schedule efficiency for transit operations. | Partnership with AATA necessary; CMAQ funding or other grant needed | Desirable | No | 0 | 0 | 1 | NULL | a subarea of the | 1 | 0 | NULL | 3 | 2022 | 1 | 2023 | 100000 | 3 | 2023 | 4 | 2023 | 250000 | 3 | 2024 | 4 | 2024 | 3090000 | NULL | NULL | NULL | NULL | NULL | Not Affect | Increase | Cooper, Eli | Gosselin, Deb | 43433 | 0 | Project without identified funding source. Anticipated CMAQ funding and potential partnership with AATA. Source identified. Eli moved back one year. Fall 2016: moved out. Fall 17: NC Fall 18 changed from AT to TR and pushed back as no active interest | NULL | 0 | 0 | TRSC1217.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | AnnArbor Transportation Plan Update (2009) | NULL | NULL | NULL | Programmed | Inactive | 43.12 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1293 | TR-TR-12-20 | Queue Jump Lanes: Plymouth Road | 2360000 | Northeast | Between US 23 and Huron Parkway. Two signalized Intersections | PUBLIC SERVICES | SYSTEM PLANNING | 16 | Increased reliability and schedule efficiency for transit operations. | Partnership with AATA necessary; CMAQ funding or other grant needed | Desirable | No | 0 | 0 | 1 | NULL | a subarea of the | 1 | 0 | NULL | 3 | 2022 | 1 | 2023 | 100000 | 3 | 2023 | 4 | 2023 | 200000 | 3 | 2024 | 4 | 2024 | 2060000 | NULL | NULL | NULL | NULL | NULL | Not Affect | Increase | Cooper, Eli | Gosselin, Deb | 43433 | 0 | Project without identified funding source. Anticipated CMAQ funding and potential partnership with AATA. Identified source.; no changes in 12. Fall 2016: moved out. Fall 17: NC Fall 18 changed from AT to TR and pushed back as no active interest | NULL | 0 | 0 | TRSC1220.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | AnnArbor Transportation Plan Update (2009) | NULL | NULL | NULL | Programmed | Inactive | 43.12 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 2 | NULL | NULL | NULL | 2 | 1 | NULL | 1 | 2 | 1 | 3 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1310 | UT-ST-10-13 | Flood Mitigation Implementation Grant Matching | 600000 | Citywide | NA | PUBLIC SERVICES | SYSTEM PLANNING | 13 | FEMA Flood Mitigation Grants have a 25% local match requirement | FEMA grant applications can be submitted each year to implement specific projects identified in the City of Ann Arbor Flood Mitigation Plan, or for purchase of floodplain property and demolition of buildings as opportunities arise. | Desirable | No | 0 | 0 | 5 | Reduces flood damage and risk. Facilitate creation of greenways in floodplain areas. | the entire | 1 | 1 | $100,000.00 each year to provide 25% matching funds for potential FEMA Flood Mitigation Grant projects. | NULL | NULL | NULL | NULL | 0 | 3 | 2010 | 4 | 2025 | 1500000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Not Affect | Not Affect | Hancock, Jerry | Gosselin, Deb | 43417 | 0 | Added monies for 2019 and skipped 2014 per JH; changed title to reflect broader use of funds on 9.30.13. Fall 2016: added money to outer years. Fall 17: NC Fall18: upped $ | NULL | 0 | 0 | UTST1013.jpg | Hancock, Jerry | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 34.21 | 30 | NULL | Hancock, Jerry | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | Systems Planning | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1313 | TR-AT-10-20 | Major Mid Block Crossing Improvements | 200000 | Citywide | Citywide | PUBLIC SERVICES | SYSTEM PLANNING | 6 | Non-motorized Transportation Plan (NTP), page 165. Improve pedestrian safety and ability to walk cross roads. | Initial phase through FY2020 is for RRFBS; later work will continue to evaluate conditions & schedule improvement for additional major mid-block crossing opportunities identified in NTP. Coordination with AATA and AAPS needed. | Desirable | No | 0 | 0 | 1 | NULL | the entire | 1 | 0 | Project and level of funding would establish a program to address an important need in the community. | NULL | NULL | NULL | NULL | 0 | 3 | 2013 | 2 | 2014 | 75000 | 3 | 2014 | 4 | 2023 | 1585200 | NULL | NULL | NULL | NULL | NULL | Not Affect | Increase | Allen, Jane | Gosselin, Deb | 43433 | 0 | Inclusion of RRFBs in scope. Leave this as a place holder but within any two year cycle, must have a specific plan and name a project accordingly. Fall 2016: allocated county millage funds to this to total $1M. Fall 17: adj per NH; added later. Fall 18: N | NULL | 0 | 0 | Citywide.jpg | Cooper, Eli | Redinger, Cynthia | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | AnnArbor Transportation Plan Update (2009) | NULL | NULL | Active | Design | 72.09 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 89014.53 | 2019-06-30 | Included W Stadium Mid-Blck Crossing in 2016 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 57656.86 | 2017-07-25 | NULL | 2006.12 | 1248.5 | 85759.91 | NULL | NULL | NULL | High Local | 2015-030 | NULL | NULL | 2016-042 | 2018-09-29 | 390748 | 2018-035 | 2019-06-30 | 89014.53 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1324 | TR-SC-10-09 | Geddes Ave (Huntington to Hickory) Road Reconstruction | 3080000 | Northeast | Geddes Ave (Apple Way to Huron Pkwy) | PUBLIC SERVICES | PROJECT MANAGEMENT | 11 | Deteriorating pavement condition | Road project: vertical alignment, sidewalk, ramps, non-motorized path, and utility needs; community involvement, Forestry management, Township parcels, traffic control/detour, Non-Motorized Plan. County Drain. Coordinate with corridor project. | Important | Yes | 1 | 7 | 2 | Improved pavement condition and non-motorized access | the entire | 1 | 0 | NULL | 1 | 2013 | 2 | 2013 | 0 | 1 | 2014 | 1 | 2015 | 180000 | 2 | 2015 | 4 | 2016 | 5310750 | NULL | NULL | NULL | NULL | NULL | Not Affect | Decrease | Slizewski, Brian | Gosselin, Deb | 41667 | 1 | Rolled SC-10-14 in with this and combined; also includes old sloughing correction (TR-OT-10-04); updated project name to show starting at Apple Way; edited dollars to match Nick's 0062 spreadsheet 1.28.14 | NULL | 0 | 0 | TRSC1009.jpg | Pulcipher, Connie | Cooper, Eli | Sheehan, Harry | Selvig, Bev | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Planning | 56.5 | 6 | Currently determining if sanitary sewer will be extended to requested sites. Additional project scope may be part of a new project. May consider interim resurfacing project to address poor pavement conditions. | Rolla, Liz | NULL | robust | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Severe | 1 | 0 | side path; no curb and gutter; traffic control; private roads | 10 | 0 | Project Management | No | NULL | 2013-037 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Note that "road" total presently includes some general fund contribution and some storm costs that will be special assessed | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 6620698 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1326 | TR-AP-10-06 | Taxilane For Box Hangers | 193000 | South | Airport | PUBLIC SERVICES | FLEET & FACILITY | 5 | Connect new box hangers to taxiway | Timing based on market demand for new box hangers | Important | Yes | 1 | 28 | 1 | NULL | NULL | 0 | 0 | NULL | 3 | NULL | 3 | NULL | 0 | 4 | 2021 | 1 | 2022 | 12000 | 2 | 2022 | 4 | 2022 | 181000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kulhanek, Matt | Gosselin, Deb | 42691 | 0 | adjust schedule and cost estimate; Fall 2016: put in 2023 | NULL | 0 | 0 | TRAP1006.jpg | Kulhanek, Matt | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | Tenants | 1 | Capacity Analysis | NULL | NULL | NULL | 1 | AIP Capital Improvement Plan | NULL | NULL | NULL | Programmed | Inactive | 33.3 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 0
2071 | UT-ST-18-20 | Springwater Phase V Stormwater Improvements | 1020000 | NULL | Rosedale (all); Redwood and Sharon (Springbrook to Platt) | NULL | NULL | 13 | Replace existing storm sewer system in streets slated for reconstruction | Replace existing storm sewer system in streets slated for reconstruction | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 75000 | 2 | 2025 | 4 | 2025 | 945000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43045 | 0 | New Fall 2016. Fall 17: NC | NULL | 0 | 0 | UTST1820.jpg | Warrow, Anne | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.52 | 13 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1332 | UT-ST-10-16 | Street Tree Replanting | 1575000 | Citywide | Streets throughout the City | PUBLIC SERVICES | SYSTEM PLANNING | 13 | Replace trees lost to the emerald ash borer and as a regular planting program to replace trees that have died. | Tree planting program to be coordinated with Forestry Field Operations. Project receives State Revolving Fund ("SRF") dollars. | Important | No | 0 | 0 | 2 | City loses 1% of its tree population each year to a variety of factors; this was exacerbated by the loss of 8000 ash street trees to EAB. These trees provide benefits to the City from stormwater detention to aesthetic. | the entire | 0 | 0 | Based on tree planting each year from FY12-FY16 | NULL | NULL | NULL | NULL | 0 | 3 | 2009 | 2 | 2014 | 450000 | 3 | 2009 | 4 | 2020 | 2895000 | NULL | NULL | NULL | NULL | NULL | Increase | Increase | Gray, Kerry | Kerry Gray | 41968 | 1 | Updated funding | NULL | 0 | 0 | Citywide.jpg | Gray, Kerry | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Construction | 53.2 | 9 | NULL | Gray, Kerry | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1336 | UT-ST-10-20 | Geddes Ave (Huntington to Hickory) Stormwater Improvements | 800000 | Northeast | Geddes Avenue from Arlington to Huron Parkway | PUBLIC SERVICES | PROJECT MANAGEMENT | 13 | Stormwater improvements related to road and corridor work. | Minimal existing formal system. Road project will involve utilities, alternative transportation issues, etc.; a | Important | Yes | 1 | 7 | 1 | NULL | NULL | 1 | 0 | Related to corridor project | NULL | NULL | NULL | NULL | 0 | 3 | 2013 | 4 | 2014 | 50000 | 2 | 2015 | 4 | 2015 | 1950000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 41929 | 1 | Figure updated per HRC estimate of 10.16.14 | NULL | 0 | 0 | UTST1020.jpg | Rolla, Liz | Ernst, Kevin | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 36.05 | 27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | NULL | Yes | NULL | 2013-037 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1570821 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1337 | UT-ST-10-21 | Stone School Rd (I-94 to Ellsworth) Storm Improvements | 1320000 | South | Stone School Road between Ellsworth and I-94 | PUBLIC SERVICES | PROJECT MANAGEMENT | 13 | Improve surface drainage, provide detention, investigate standing water conditions in sewer at Champagne | Coordinate with road reconstruction project. Mallets Creek (County drain). Meet detention requirements for reconstruction project. Investigate ditches vs. possible new storm sewer (none existing currently at some locations). Tie to UT-ST-12-18. SRF. | Desirable | Yes | 1 | 10 | 1 | NULL | NULL | 1 | 0 | NULL | 1 | 2013 | 4 | 2013 | 200000 | 1 | 2013 | 4 | 2013 | 20000 | 2 | 2014 | 3 | 2014 | 1980000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 41974 | 1 | Updated schedule & scope; Costs updated in Fall 2014;to reflect total cost of $2.2M | NULL | 0 | 0 | UTST1021.jpg | Hutchinson, Nick | Ernst, Kevin | Lawson, Jennifer | Sheehan, Harry | Rolla, Liz | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 53.05 | 4 | NULL | TBD | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 0 | Moderate | 1 | 0 | NULL | 7 | 1 | Project Management | Yes | NULL | 2011-029 | NULL | NULL | 161000 | NULL | 1990100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2162400 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1345 | UT-SN-10-11 | 2780 Packard Sanitary Extension | 320000 | South | Packard Road between Colony and Easy Street | PUBLIC SERVICES | SYSTEM PLANNING | 12 | Parcel does not have sanitary availability and it has been requested. | Sanitary connection from south of property via easement acquired from sale of property to housing commission. | Important | Yes | 0 | 41 | 1 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 4 | 2016 | 4 | 2017 | 30000 | 2 | 2018 | 4 | 2018 | 290000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43003 | 1 | Adjusted schedule. Note: Figure not updated in Fall 2014. Fall 2016: cost unchanged. Fall17: spent $10K to end of FY17 and put balnce of $310b FY18 | NULL | 0 | 0 | UTSN1011.jpg | Slotten, Cress | Heatley, Alison | Baughman, Troy | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 30.67 | 25 | NULL | TBD | NULL | contact the property owners | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 0 | 0 | Minimal | 0 | 1 | NULL | 3 | 0 | Project Management | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 123024 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1354 | UT-WS-10-12 | Stadium Blvd (Main to Kipke) Raw and Domestic Water Main Replacement | 1476290 | South | E. Stadium Blvd (200' west of S. Main Street to Kipke Drive) | PUBLIC SERVICES | PROJECT MANAGEMENT | 14 | Upsize raw water main to 30"; replace domestic 6" water main with 12" water main to complete system upgrades within project area. | Replace and upsize existing mains from S. Main to Kipke. Public involvement/engagement to be performed with roadway project. Coordinate with UT-ST-18-16 as well as road project. | Important | Yes | 1 | 2 | 2 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2014 | 2 | 2016 | 218400 | 3 | 2016 | 2 | 2017 | 1257890 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 43011 | 1 | Updated funding schedule & project schedule to reflect revised funding amounts. Project to begin construction November 2016. Also rolled in old UT-WS-13-02. Fall 17: changed to TBC and calculated cash flow in FY18 for Marti; didi not change in database | NULL | 0 | 0 | UTWS1012.jpg | Zink, Denny | Hupy, Craig | Sanford, Larry | Nearing, Mike | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 51.24 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2014-035 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1.347 | 970550.96 | NULL | 1378800 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1356 | UT-WS-10-14 | Valhalla Drive Water Main | 325000 | South | Valhalla Drive | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Extend water main to service homes with private wells. | Coordinate w/ sanitary; obtain easements; relocate MichCon gas main; township islands; | Important | Yes | 1 | 23 | 1 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 2009 | 4 | 2024 | 35000 | 2 | 2026 | 2 | 2026 | 290000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43046 | 0 | Officially closed old part of this project fiscally on 8/26/2015; Fall 2016: CH said to leave the project live so added beyond 2023; costs not updated. Fall 17: NC Fall 18; moved out 1 year, cots not updated | NULL | 0 | 0 | UTWS1014.jpg | Warrow, Anne | Baughman, Troy | Nearing, Mike | NULL | NULL | 1 | NULL | NULL | NULL | Wash Co Health | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | On Hold (comment required) | 38.91 | 36 | NULL | Warrow, Anne | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 0 | Moderate | 0 | 1 | Easements are required | 7 | 0 | Project Management | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1359 | UT-WS-10-17 | North University Court Water Main | 235000 | Central | NULL | PUBLIC SERVICES | SYSTEM PLANNING | 14 | Fire flows in UM dorm area | District boundary considerations; look at looping potential; | Desirable | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2024 | 4 | 2024 | 25000 | 2 | 2025 | 4 | 2025 | 210000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 42690 | 0 | Updated schedule. Fall 18: $ not updated but moved out | NULL | 0 | 0 | UTWS1017.jpg | Heatley, Alison | Sanford, Larry | Baughman, Troy | Chamberlain, Kathleen | NULL | 1 | University of Michigan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 25.64 | 70 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1361 | TR-AT-10-29 | ADA Ramp Replacements (Outside of DDA) | 5396000 | Citywide | City-wide | PUBLIC SERVICES | FIELD OPERATIONS | 6 | Citizen requests for sidewalk ramps | Examine tree impacts. Grading easements. Drainage. Sight distance. | Urgent | No | 0 | 0 | 2 | NULL | NULL | 0 | 1 | Work required to be completed by Consent Decree. Current funding set such that work could be substantially completed by the end of 2016. | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | 4 | 2011 | 2 | 2017 | 6422000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43041 | 1 | Fall 17: marked TBC | NULL | 0 | 0 | Citywide.jpg | Hutchinson, Nick | Kluczynski, Brad | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | settlement agreement | 0 | NULL | NULL | NULL | NULL | Active | Construction | 53.64 | 12 | NULL | Kluczynski, Brad | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2016-021 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1145988 | 2016-04-02 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1500447.41 | 2017-08-04 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | 2016-021 | NULL | NULL | 2017-021 | 2017-06-30 | 165260.18 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1365 | TR-BR-10-01 | Biennial Bridge Inspection Program | 910000 | Citywide | Citywide | PUBLIC SERVICES | PROJECT MANAGEMENT | 7 | Inspection and evaluation of 15 city owned bridges, and/or structures that qualify as bridges, for compliance with current state and federal requirements. This project is required to comply with federal mandates for biennial bridge inspections. | Perform inspection (bridges over water bodies one year, bridges over land the next); complete required federal forms; prepare written reports that document, prioritize and define the work needed on each bridge. Each bridge is inspected every other year. | Urgent | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 2 | 2014 | 4 | 2025 | 1480000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 42702 | 0 | Updated funding for FY12 & FY13. Fall 2016: extended thru FY23. Fall 18: ext to 25 | NULL | 0 | 0 | TRBR1001.jpg | Nearing, Mike | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inspection | 76.08 | 2 | NULL | Nearing, Mike | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2016-014 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 114215.72 | 2016-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 143138.93 | 2018-11-24 | NULL | 114215.72 | NULL | NULL | NULL | NULL | NULL | Low Local | 2016-014 | NULL | NULL | 2018-014 | 2019-01-05 | 68362.2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1366 | TR-NS-10-05 | Burton Road Improvements | 1500000 | South | Burton Rd | PUBLIC SERVICES | PROJECT MANAGEMENT | 8 | Pave gravel road when Burton Commons improvements occur | Tied to Burton Commons site plan. Natural features impacts. Include stormwater management. | Desirable | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | 2 | 2022 | 4 | 2022 | 1500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hall, Jennifer | Gosselin, Deb | 43432 | 0 | Adjusted schedule. Fall 2015: Moved FY16 to FY18 per AH as no forward progress on Burton Commons. Fall 2016: moved again to FY20 on same basis;Fall 18: moved to 22 on same basis | NULL | 0 | 0 | TRNS1005.jpg | Baughman, Troy | Hancock, Jerry | Rampson, Wendy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | On Hold (comment required) | 56.87 | 3 | NULL | Baughman, Troy & Heatley, Alison | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 2 | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1367 | TR-OT-10-06 | Bird Road Retaining Wall | 150000 | West | On Bird Road, west of preservation area. | PUBLIC SERVICES | FIELD OPERATIONS | 9 | Replace failed retaining wall. | Private utilities. Existing trees. Resident concerns and desires. Curb replacement. | Urgent | No | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | 3 | 2018 | 4 | 2018 | 150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43039 | 0 | Changed from $NO$ to 0062 per Marti as can't include a non-funded project in present cycle unless grant funding is anticipated.; Fall 2016: showed as Act 51; if not funded, not repaired. Fall 17: shifted to FY19 | NULL | 0 | 0 | TROT1006.jpg | Pennington, Kirk | Hupy, Craig | Slotten, Cress | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 19.11 | 19 | waiting for funding | Woodward, Nichole | AT&T, MichCon interface | communicate with neighbors | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 0 | 1 | Moderate | 1 | 0 | grading easements | 6 | 0 | Field Operations | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1371 | MF-PR-10-01 | Playgrounds and Neighborhood Park Improvements | 1014000 | Citywide | Citywide | COMMUNITY SERVICES | PARKS & RECREATION | 3 | Staff evaluate need on an annual basis | Replacement of play areas and other amenities at areas to be determined. Tentative location for improvements includes Waymarket and Fuller. | Urgent | No | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 2011 | 1 | 2015 | 28000 | 2 | 2011 | 2 | 2024 | 1711000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | (Replaced project MF-PR-08-04). Updated funding. Started annual "pot" in 12/12 Gallup west is done. Considering Churchill Downs to be coordinated with the storm basin. Repairs done at Fuller; Fall 2016: funded rest of years. Fall 17 updated Fall 18 upda | NULL | 0 | 0 | MFPR1001.jpg | Warba, Matt | Smith, Colin | Kuras, Amy | Hancock, Jerry | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Active | Construction | 68.62 | 2 | S. University and Placid Way targeted for 2012 construction. | Kuras, Amy | Winewood Thaler, Beckley Neighborhood Parks have been approved by City Council for renovations. $50,000 project donation for the S. University project. | Public meetings with neighbors | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 0 | 0 | Minimal | 1 | 0 | Coordinate with Project Management | 4 | 0 | Parks and Recreation | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 2 | NULL | 1 | 2 | 2 | 2 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | 2 | 5000 | 0
1372 | MF-PR-10-02 | Parks Roads, Bridges and Parking Lots | 1620000 | Citywide | Citywide | PUBLIC SERVICES | FIELD OPERATIONS | 3 | Staff to evaluate needs annually. | Tentative projects: Repair/replace Gallup vehicular bridge. Lot repair/replacement at Fuller Pk, Senior Ctr, Brokaw. Meet Ch 63 stormwater req. . Repair ped. bridges at Mitchell, Barton Nature Area,& Argo Cascades. | Urgent | No | 0 | 0 | 3 | NULL | NULL | 0 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 2011 | 1 | 2015 | 150000 | 2 | 2011 | 2 | 2025 | 2590000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | Updated Prior Year funding; extended annual funding through 2021. Fall 2105: reduced FY 17 from $200K to $100K; Fall 2016: NC. Fall 17: increased 18 to $320K. Fall 18 updated $ | NULL | 0 | 0 | Citywide.jpg | Smith, Colin | Warba, Matt | Carson, Chris | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Active | Planning | 53.97 | 11 | NULL | Kuras, Amy | Argo Livery to be revisted after Argo Headrace construction complete. Veterans Park coordination with Dexter Road reconstruction project. Riverside Park to be managed by Project Management. | Buhr Park and Riverside Park public engagement ongoing. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 0 | 1 | Moderate | 1 | 1 | May need an agreement with UM for Riverside Park. Community impact varies by location. | 8 | 0 | Parks and Recreation | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | 1 | NULL | 1 | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1380 | TR-AT-10-37 | Shared Use Path: West Huron River Drive to North Main Street | 900000 | West | Access Under M-14 bridge | PUBLIC SERVICES | SYSTEM PLANNING | 6 | Safe access to West Huron River Drive from N. Main Street | Identify access for grade separated improvement under M-14 using M-14 bridge and area adjacent to Amtrak corridor. Reevaluate need after Allen Creek Greenway Master Plan is completed and status of Bandemer to Barton tunnel is determined; abt. 1680 LF | Important | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | will require acquisition of ROW at north end of Main Street and MDOT authorization to work under M-14. Order of magnitude cost estimate. | 3 | 2017 | 4 | 2017 | 0 | 3 | 2024 | 4 | 2024 | 150000 | 2 | 2025 | 4 | 2025 | 750000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43434 | 0 | Project description added. Fall 2016: moved back to FY 22/23 as AC Greenway and Bandemer to Barton may eliminate Fall18: moved to FY26 based on long-term TAP planning | NULL | 0 | 0 | TRAT1037.jpg | Cooper, Eli | Cawley, Pat | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | AnnArbor Transportation Plan Update (2009) | NULL | NULL | Programmed | Inactive | 66.85 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1383 | TR-OT-20-09 | Accessible Pedestrian Signals | 100000 | Citywide | NULL | PUBLIC SERVICES | FIELD OPERATIONS | 9 | Upgrade existing pedestrian signals with ADA accessible equipment | Direct involvement with Disabilities Commission. With location and funding determined/recommended by commission. Swift and Broadway identified need for audible.. As road projects occur, signals to be upgraded. PROWAG draft guidelines show mandating audio | Urgent | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | 3 | 2019 | 2 | 2021 | 100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Liu, Luke | 43390 | 0 | Updated schedule (moved back); extended thru 2019; eliminated per CH as these get rolled into road project costs and no independent project is proposed. | NULL | 0 | 0 | TROT2009.jpg | Fojtik, Chuck | Sipowski, Les | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 46.74 | 9 | NULL | Fojtik, Chuck | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1382 | TR-OT-10-08 | State St Corridor Transportation Study | 300000 | South | Ellsworth to Oakbrook | PUBLIC SERVICES | SYSTEM PLANNING | 9 | Transportation Plan Update | Evaluate traffic needs for this key corridor. Consider boulevard designed as a complete street with indirect left turns. Coordinate with Land Use Study of the corridor; investigate possible roundabout at Hilton. Coordinate w/ Connector Study (AATA). | Important | Yes | 1 | 33 | 6 | NULL | a subarea of the | 1 | 1 | NULL | 3 | 2014 | 3 | 2015 | 300000 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 41957 | 1 | Updated funding to indicate unfunded study. Revised dollars to be study only and not detailed design and to request general funds | NULL | 0 | 0 | TROT1008.jpg | Rampson, Wendy | Cooper, Eli | Sipowski, Les | Pulcipher, Connie | Hupy, Craig | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 1 | AnnArbor Transportation Plan Update (2009) | Ann Arbor Non-Motorized Plan | NULL | NULL | Active | Design | 45.56 | 1 | planning has not begun; soil borings complete | Thacher, Jill | look at sanitary capacity if land use changes; potential storm water management improvements | robust | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Moderate | 1 | 1 | NULL | 9 | 0 | Planning & Development | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2643.26 | 2014-12-27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1386 | TR-OT-10-12 | Watershed Drive Retaining Wall | 350000 | Northeast | 725 Watershed Drive/3485 Narrow Gauge | PUBLIC SERVICES | FIELD OPERATIONS | 9 | Repair failing retaining wall | Private property ROW concerns. Private utilities. Not CIP qualified individually but needs to remain to either be part of wall program or picked up when road is done. | Important | No | 0 | 0 | 9 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 2 | NULL | 1 | NULL | 0 | 2 | 2014 | 3 | 2014 | 35000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 42986 | 1 | Updated schedule; corrected goofy $350K to $35K; changed schedule from FY17 to FY14; marked TBC 9/8/2017 | NULL | 0 | 0 | TROT1012.jpg | Pennington, Kirk | Kluczynski, Brad | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 7.73 | 14 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1388 | TR-OT-10-14 | Newport Road Retaining Walls | 200000 | West | Newport Road - 1300 Newport, 1270 Newport, 1230 Newport | PUBLIC SERVICES | FIELD OPERATIONS | 9 | Replace failing retaining wall | Failing retaining wall. Dry-laid flagstone. Sidewalk considerations. Projecting beyond back of curb. Not CIP qualified individually but needs to remain to either be part of wall program or picked up when road is done.300 LF., 2 ft. high max. | Desirable | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 4 | 2021 | 1 | 2022 | 20000 | 2 | 2022 | 3 | 2022 | 180000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43437 | 0 | Updated schedule; again. Fall 2016: moved to FY20. Fall 18: moved to FY22 cost needs to be updated | NULL | 0 | 0 | TROT1014.jpg | Pennington, Kirk | Kluczynski, Brad | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 9 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1392 | TR-BR-10-05 | Morehead-Delaware Pedestrian Bridge
Morehead-Delaware Pedestrian Bridge ELIM | 350000 | South | Between Morehead and Delaware drives in Lansdowne subdivision, crosses Malletts Creek in City dedicated ROW | PUBLIC SERVICES | PROJECT MANAGEMENT | 7 | Re-Opening of pedestrian crossing over Malletts Creek | Existing bridge sat on weir controlled & owned by Lans. Basin; weir was failing & unable to support existing bridge; WCWRC & MDNRE permitting required; examining options for design-build of new bridge | Desirable | No | 0 | 0 | 6 | NULL | a subarea of the | 1 | 0 | Project Schedule unknown at this time. Current timeline reflects estimated time to design and construct project when the project is undertaken. Construction easements will be necessary and can impact actual project schedule. | NULL | NULL | NULL | NULL | 0 | 4 | 2018 | 2 | 2019 | 100000 | 2 | 2019 | 4 | 2019 | 250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 41898 | 1 | Updated possible project costs for informational purposes for others within organization. As more and better information becomes available, this form will be updated to reflect the revised information. ELIMINATED AND CHANGED TO ALT TRANS PROJECT | NULL | 0 | 0 | TRBR1005.jpg | Hupy, Craig | Woodward, Nichole | Nelson, Jen | Pirooz, Homayoon | Sheehan, Harry | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Planning | 15.23 | 4 | Council approved funding of $120,000 for design of the bridge; appropriated from the Major Streets fund. | Dykman, Dave | The old bridge was removed by Field Operations in summer, 2011. The Lans Basin homeowners association is obligated to design and reconstruct the weir per their bylaws. The bridge and construction of the weir must be a coordinated effort. | Council members Higgins/Teal have been working with the Lans Basin homeowners. Staff to determine what has been discussed and begin meeting with homeowners to coordinate design and reconstruction. Determine a broader stakeholder group for communication | NULL | 40792 | NULL | NULL | NULL | 41091 | NULL | 1 | 1 | 1 | 1 | Moderate | 0 | 1 | Easements and grading permits may be required. WCWRC & MDNRE permitting required. Check with J. Hancock about recent mapping of the floodplain. | 8 | 0 | Project Management | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1397 | TR-NS-10-07 | Clark Rd. Extension (Huron Pkwy to US-23) | 1125000 | Northeast | North of Washtenaw, between Huron Parkway and US-23 | PUBLIC SERVICES | SYSTEM PLANNING | 8 | Provide additional, secondary access for properties off Chalmers and for Arborland. | Natural features; floodplain; need /ROW west of Chalmers; coord. w/Washtenaw Visioning Study; stormwater mgt.; utilities. Inter. w/ Huron Pkwy impacts. WCWRC coordination. Part being built by priv. devl. who is also dedicating RW to US 23 | Important | No | 0 | 0 | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | 2 | 2017 | 3 | 2017 | 1125000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Heatley, Alison | Gosselin, Deb | 42318 | 0 | Fall 2013: Moved to 2017. Fall 2015: left in FT17 because South Pond site plan in progress; Fall 2016: South Pond to do part of this and dedicate right of way for balance to 23; part west of Chalmers still necessary also. Rename Clark Rd Ext. | NULL | 0 | 0 | TRNS1007.jpg | Redinger, Cynthia | Heatley, Alison | Slotten, Cress | Pulcipher, Connie | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | 2030 Long Range Transportation Plan for Washtenaw County (2005) | NULL | NULL | NULL | Programmed | Inactive | 46.95 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 2 | NULL | 2 | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1410 | MF-PR-10-15 | Fuller Pool Spray Park | 800000 | Northeast | Fuller Park Pool | COMMUNITY SERVICES | PARKS & RECREATION | 3 | To attract younger children to Fuller Park, to provide more amenities, and generate revenue | Construct new spray park including fountain equipment, surfacing, fencing | Desirable | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2021 | 1 | 2023 | 75000 | 2 | 2023 | 4 | 2023 | 725000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 42688 | 0 | Adjusted schedule; moved revenue to right year. Fall 2016: moved to FY 22-23. Fall 18 NC | NULL | 0 | 0 | MFPR1015.jpg | Hurn, Gayle | Kuras, Amy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Programmed | Inactive | 31.13 | 18 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 0
2199 | TR-SC-20-11 | Granger (State to Packard) Resurfacing | 440000 | NULL | Granger (State to Packard) | NULL | NULL | 11 | Address street condition | Resurface street; | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2019 | 4 | 2020 | 440000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2011.jpg | Dykman, Dave | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.68 | 39 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1401 | MF-PR-10-06 | Trails & Pathways - Repairs & Reconstruction | 1330000 | Citywide | Citywide | PUBLIC SERVICES | FIELD OPERATIONS | 3 | Staff to evaluate needs on an annual basis. New projects to be scheduled each year per condition assessment | Repair & reconstruct pathways as needed. Tentative projects include replacing existing path, Gallup Park (vehicular bridge west to Mitchell) andRiverside Park. Evaluate Furstenberg, Argo, and other boardwalks. Make Barton Nature Area trail ADA accessible. | Urgent | No | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 4 | 2011 | 4 | 2015 | 0 | 1 | 2011 | 2 | 2015 | 25000 | 2 | 2011 | 2 | 2024 | 3127500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kuras, Amy | Smith, Colin | 43431 | 0 | Eliminated funding for FY12 & FY13; updated numbers through FY2021. Fall 2015: TAP funds of $447,500 in FY16. in Fy17 $50K from developer contribution for 618 S Main for Wooster Park; Fall 2016: added funds from FY19 on. Fall 18n update | NULL | 0 | 0 | Citywide.jpg | Warba, Matt | Smith, Colin | Pennington, Tracy | Gray, Kerry | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | Ann Arbor Non-Motorized Plan | NULL | Active | Design | 63.83 | 4 | NULL | Kuras, Amy | Veterans is complete. Riversie Park scope items captured in MF-PR-10-02 | Gallup Canoe Livery TBD | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 0 | 1 | Minimal | 0 | 0 | NULL | 3 | 0 | Parks and Recreation | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | 1 | 2 | 2 | 1 | 2 | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1402 | MF-PR-10-07 | Trails & Pathways - New Construction | 600000 | Citywide | Citywide | COMMUNITY SERVICES | PARKS & RECREATION | 3 | Connectivity and barrier free access | Improve access to the river. Reference NMHRVTF report. other sidewalk gaps. Potential boardwalk at Dolph Park | Urgent | No | 0 | 0 | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 2011 | 1 | 2015 | 25000 | 2 | 2011 | 3 | 2019 | 125000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | New project (Moved back one year to fit funding - Cresson Slotten, 12/22/10); showed annual amounts. Fall 2016: zeroed out 2018 and 2019 to make way for sidewalk monies. Fall 18 NC | NULL | 0 | 0 | Citywide.jpg | Warba, Matt | Kuras, Amy | Smith, Colin | Landefeld, Josh | Straw, Jeff | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | Ann Arbor Non-Motorized Plan | NULL | Active | Planning | 60.22 | 5 | NULL | Kuras, Amy | Barrier free path to raptors at LSNC scope expanded to include stormwater and pedestrian circulation master plan for the entire site. | TBD-LSNC Board involvement. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Moderate | 1 | 1 | State Revolving Fund potential | 9 | 0 | Parks and Recreation | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 2 | NULL | 1 | 2 | 2 | 1 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1404 | MF-PR-10-09 | Picnic Shelters | 300000 | Citywide | Citywide | PUBLIC SERVICES | FIELD OPERATIONS | 3 | Renovations at various park shelters. | Replace shelter at Veterans - identify infrastructure needs. Add shelter at Fuller fields and Wheeler; rehabilitate at Island. | Important | No | 0 | 0 | 7 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 4 | 2014 | 4 | 2014 | 10000 | 2 | 2015 | 2 | 2024 | 790000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | Added new set for FY2017 Gallup done. Fall 2015: Moved FY16 funds to FY17 and increased from $100K to $200K; Fall 2016: Added funds in FY18 and FY19. Fall 17: moved FY17 funds to FY18. Fall 18 updated | NULL | 0 | 0 | Citywide.jpg | Warba, Matt | Kuras, Amy | Black, Jessica | Smith, Colin | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Active | Construction | 44.4 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1408 | MF-PR-08-19 | Baseball/Softball Field Renovations | 950000 | Citywide | Citywide | PUBLIC SERVICES | FIELD OPERATIONS | 3 | Staff to identify needs bi-annually. | Renovate infields, outfields, backstops, benches, lighting if existing. Lighting at Vets (ballfields and skatepark) | Desirable | No | 0 | 0 | 3 | NULL | NULL | 0 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 2011 | 4 | 2015 | 50000 | 3 | 2021 | 2 | 2022 | 1050000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | New project. Show bi-annually beginning in 2016. Fall 2105: Moved FY16 bucket to FY17; updated Fall 18 | NULL | 0 | 0 | Citywide.jpg | Warba, Matt | Smith, Colin | Pennington, Tracy | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Active | Planning | 55.04 | 10 | 90% plans available after Labor Day. | Warba, Matt | Veterans Memorial Park, Southeast Area Park, West Park, Allmendinger Park. May be irrigation updates in some locations. Repair/replace fencing in some locations. Construction may be done in two phases. | Recreation Advisory Commission - Parks Advisory Commission. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Moderate | 0 | 1 | Use Agreement with AAPS | 8 | 0 | Field Operations | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 2 | NULL | NULL | 1 | 2 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1413 | MF-PR-10-17 | Bandemer Park Access | 550000 | West | Bandemer Park at Lakeshore Drive | COMMUNITY SERVICES | PARKS & RECREATION | 3 | Entry to Bandemer Park either through crossing of railroad at Lakeshore Drive (preferred alternative) or an access road from Barton Drive if this is not feasible. | If railroad crossing is feasible, then gates and signals for railroad crossing. If not feasible, construction of access drive from Barton Drive. Related issue, no sidewalk on west side of North Main Street, no safe way to cross Main. HAWK signal? MDOT | Important | No | 1 | 43 | 1 | NULL | NULL | 1 | 0 | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 2023 | 2 | 2024 | 50000 | 3 | 2024 | 4 | 2024 | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43039 | 0 | Updated schedule in 12/12. Fall 2106: moved to FY23-24. Fall 17: NC | NULL | 0 | 0 | MFPR1017.jpg | Kuras, Amy | Bahl, Sumedh | Cooper, Eli | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | NULL | Parks & Recreation Open Space (PROS) Plan | NULL | Programmed | Inactive | 42.24 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
1423 | TR-SC-12-01 | Zina Pitcher/Catherine (Ann to Glen) Resurfacing | 220000 | NULL | Ann to Glen | NULL | NULL | 11 | Resurfacing/Reconstruction, pavement failing. | Significant U of M frontage. Watermain project on Catherine. Kresge demo and other U of M projects. Concrete base may need replacement. Maintaining access to UM properties. Talk by UM about "transit center" improvements in area. Consider 2-way conversion | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2017 | 1 | 2018 | 0 | 2 | 2018 | 4 | 2018 | 390000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Removed funding - incorporated into new project Annual Street Resurfacing Program (TR-SC-13-06); added funding back and did placeholder for UM contribution'. Fall 2015 moved FY16 to FY17. Moved to FY20; updated schedule/funding. Fall 17: NC | NULL | 0 | 0 | TRSC1201.jpg | Kotlyar, Igor | Pulcipher, Connie | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 54.29 | 18 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1443 | UT-ST-11-03 | Capital Reconstruction of Structures/Resurfacing | 3100000 | NULL | Streets included in Annual Local and Major Street Resurfacing Projects | NULL | NULL | 13 | Repair or replace deteriorated structures and covers | Replace utility structures and covers as needed within the road influence during City construction projects. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2010 | 4 | 2025 | 6500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43423 | 0 | Updated funding for FY13; updated funding for FY14 and 15; then assumed work will slow down so returned to more modest amount for remaining years. Fall 2016: upped to reflect more road work. Fall 17: NC | NULL | 0 | 0 | Citywide.jpg | Hutchinson, Nick | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 25.71 | 36 | on going | Rolla, Liz | Capital book keeping item | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | Project Management | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1447 | UT-ST-11-07 | South State Street Storm Outlet at Malletts | NULL | NULL | Malletts Creek opposite Mall Drive. | NULL | NULL | 13 | NULL | Waiting for easement to move forward with construction. | NULL | NULL | 1 | 33 | 7 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2014 | 2 | 2015 | 10000 | 3 | 2015 | 3 | 2015 | 50000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Woodward, Nichole | Nichole Woodward/Deb Gosselin | 41241 | 1 | NULL | NULL | 0 | 0 | UTST1107.jpg | Woodward, Nichole | Ernst, Kevin | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Condition Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | NULL | NULL | NULL | Woodward, Nichole | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1454 | UT-ST-12-06 | State St (Kingsley to Fuller/Depot) Storm Sewer Improvements | 300000 | NULL | North State Street, between Fuller/Depot and Kingsley | NULL | NULL | 13 | Improve stormwater mgmt. coordination with pavement replacement project | Brick pavement replacement; Coordination with church. HDC. Steep slope of roadway; SRF 2013 Plan | NULL | Yes | 0 | 13 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2024 | 1 | 2024 | 25000 | 2 | 2025 | 4 | 2025 | 275000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43045 | 0 | New project; updated schedule. Costs not updated Fall 2014; Fall 2106: moved to 23 and spread costs over 2 years. Fall 17: NC | NULL | 0 | 0 | UTST1206.jpg | Nearing, Mike | Slotten, Cress | Lawson, Jennifer | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 36.82 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 2 | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
2085 | TR-SC-19-01 | State St (I-94 to Ellsworth) CPM | 690000 | NULL | State St (I-94 to Ellsworth) | NULL | NULL | 11 | Perform capital preventive maintenance to extend pavement life | Perform capital preventive maintenance to extend pavement life; | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2017 | 4 | 2017 | 0 | 2 | 2018 | 2 | 2018 | 690000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 42990 | 1 | Added utilizing funds made available by WATS | NULL | 0 | 0 | TRSC1901.jpg | Dykman, Dave | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2016-043 | 0 | NULL | 75000 | NULL | NULL | NULL | NULL | 3 | 2017 | 4 | 2017 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1.25 | 557395.5 | 2017-07-10 | 632136.78 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1451 | UT-ST-12-03 | Detroit Street Brick Rd Stormwater Management
Stormwater Management | 2100000 | NULL | Detroit Street ((Catherine to 5th and Kingsley to N Division) | NULL | NULL | 13 | Improve stormwater mgmt. coordination with pavement replacement project | HDC. Green street improvements | NULL | Yes | 1 | 12 | 8 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 90000 | 2 | 2025 | 4 | 2025 | 1210000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hancock, Jerry | Gosselin, Deb | 43423 | 0 | Updated schedule; in SRF2013 plan; Fall 2016: no SRF and moved to 23/24. Fall 17: back to SRF Fall 18: to FY25-26 per rd. | NULL | 0 | 0 | UTST1203.jpg | Pollay, Susan | Lawson, Jennifer | Hancock, Jerry | Nearing, Mike | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 35.63 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 1 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 2 | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1464 | UT-ST-12-16 | Swift Run MDOT Stormwater Management Improvements | 710000 | NULL | US-23 and Washtenaw Avenue ramps | NULL | NULL | 13 | Utilize available lands within ramp areas for stormwater management. | Included in SRF Project Plan | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 3 | 2018 | 4 | 2018 | 0 | 3 | 2022 | 4 | 2022 | 70000 | 2 | 2023 | 4 | 2023 | 640000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43424 | 0 | Fall 2016: removed SRF and spread costs, Fall 17: was spread over FY2021 and 2022; changed to single year to match capital budget as will be SRF; Fall 18; moved to FY23 | NULL | 0 | 0 | UTST1216.jpg | Lawson, Jennifer | Sheehan, Harry | Slotten, Cress | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Huron River 2010 SRF Project Plan | NULL | NULL | NULL | Programmed | Inactive | 41.82 | 20 | WCWRC Petition after July 2012 | Lawson, Jennifer | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 1 | Minimal | 1 | 1 | NULL | 7 | 1 | Systems Planning | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1477 | TR-PF-11-02 | ePark Parking Paystations | 2450000 | Central | DDA District | NULL | NULL | 10 | Customer convenience; replacement of meters at the end of useful life. | Solar powered; multiple payment options by customers; requests from Kerrytown area and others | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 1 | 2010 | 2 | 2024 | 6448755 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43433 | 0 | Updated schedule; bumped up budget per SP Fall 2015: Revised schedule and budget per DDA; all in FY17 and FY18; Fall 2016: NC. Fall 18: addded FY24 $ | NULL | 0 | 0 | TRPF1102.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1484 | TR-AT-11-04 | Ann Arbor-Saline Road/I-94 Non-Motorized Improvement: West Side | 1125000 | NULL | Ann Arbor Saline Road from Eisenhower Pkwy to Waters/Lohr Road (Pittsfield) | NULL | NULL | 6 | Provision of non-motorized crossing over interstate highway. | Sidewalk to link the City and major activity area outside of City. Project is through interchange and across I-94. Joint project w/ MDOT and Controlled by their sched.; Pittsfield Twp., WCRC & County parks. Ramp to E I-94 to be 90 degree and signalized. | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 1 | This project has been identified by the citizens and Pittsfield Township. MDOT is planning on interchange ramp construction and would like to address non-motorized system as part of their project. | 4 | NULL | 1 | NULL | 0 | 3 | 2022 | 1 | 2024 | 125000 | 2 | 2024 | 4 | 2024 | 1000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43434 | 0 | Project description and data added in 2010. MDOT ramp reconstruction will govern schedule. Moved to out years of program in 2012 .> Fall 2016: moved to 23/24. Fall 18: moved to FY25 as no aciviy by MDOt | NULL | 0 | 0 | TRAT1104.jpg | Dykman, Dave | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | Pittsfield Township | MDOT | WCRC and WC Parks | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | AnnArbor Transportation Plan Update (2009) | NULL | NULL | Programmed | Inactive | 55.63 | 13 | NULL | Cooper, Eli | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1595 | UT-WS-14-06 | Madison Place Looping Water Main | 250000 | NULL | South end of Madison Place | NULL | NULL | 14 | Loop existing dead-end water main to improve water quality and redundancy for fire protection | Crosslot 8" water main lacks easement (potentially); will need to obtain easement of new main; development potential;150 LF | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 41250 | 2 | 2023 | 2 | 2023 | 208750 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Deb Gosselin | 43424 | 0 | Fall 2016. Fall 17: moved to FY20 so don’t forget; 2018 cost confirmed | NULL | 0 | 0 | UTWS1406.jpg | Sanford, Larry | Baughman, Troy | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 16.14 | 69 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1485 | TR-AT-11-05 | Model for Mobility: Signature Transit Serv. Alternatives Analysis | 1500000 | NULL | Northeast Ann Arbor border along Plymouth Road through UM campus, Downtown and southerly along S. State Street to Ellsworth Road | NULL | NULL | 6 | Ann Arbor Connector Feasibility Study. | Conduct Alternatives Analysis to define Locally Preferred Alternative and complete environmental impact statement to support a comprehensive transit system investment. (Assumes federal funding study and AATA project lead.) | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 1 | 0 | NULL | 4 | 2011 | 1 | 2015 | 1500000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Eli Cooper | 41222 | 1 | Updated schedule | NULL | 0 | 0 | TRAT1105.jpg | NULL | NULL | NULL | NULL | NULL | 1 | University of Michigan | AATA | DDA | NULL | 1 | Capacity Analysis | Condition Analysis | Customer Level of Service | NULL | 1 | Ann Arbor Transportation Plan Update (2009) | A2D2 | UM Master Plan, Medical and North Campus | NULL | Programmed | NULL | 63.62 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1617 | TR-SC-14-02 | Stone School Rd (I-94 to Ellsworth) Road Improvements | 2050000 | NULL | Stone School Road - I-94 to Ellsworth | NULL | NULL | 11 | Pavement condition, lack of non-motorized facilities | Non-motorized improvements, 1 mid-block crossing, sidewalk gaps, stormwater BMPs, possible reforestation, AATA bus turnouts, floodplain, gravel service drive ditch needs service, missing sanitary north of Champagne. Investigate possible concrete pavement. | NULL | Yes | 1 | 10 | 2 | NULL | NULL | 1 | 0 | Scheduled to receive STPU funding for FY 2014 | 1 | 2013 | 2 | 2013 | 100000 | 1 | 2013 | 4 | 2013 | 150000 | 2 | 2014 | 4 | 2015 | 3857800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 41962 | 1 | Added new information to replace previous CIP listing; 1/14/13 upped amount coming form STP to reflect monies redirected from Pontiac Trail. | NULL | 0 | 0 | TRSC1402.jpg | Hutchinson, Nick | Hancock, Jerry | Sheehan, Harry | Lawson, Jennifer | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | NULL | NULL | NULL | Active | Construction | 62.69 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2011-029 | NULL | NULL | 249860 | NULL | 1966340 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2222520.89 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1620 | TR-SC-14-04 | Geddes Ave (Observatory to Highland) Road Improvements | 1170000 | NULL | Geddes Ave (Observatory to Highland) | NULL | NULL | 11 | Reconstruction | Crossing island issues. ADA issues. Stormwater; coordinate with water main; evaluate sanitary. | NULL | Yes | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 75000 | 2 | 2022 | 4 | 2022 | 1175000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Figuresfurnished by CC based on resurfacing with a 1.4 multiplier t. Probably will rethink this one and maybe just to a lesser treatment; Scoped as a resurfacing project; updated schedule/funding. Fall 17: NC POSSIIBLE COUNTY MILLAGE | NULL | 0 | 0 | TRSC1404.jpg | Rolla, Liz | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 58.47 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1503 | MF-CB-12-04 | Guy C. Larcom Municipal Building: Freight Elevator Replacement | 170000 | NULL | Larcom Building | NULL | NULL | 1 | Replacement of aged equipment | Examine existing elevator shaft dimensions, capacity; review existing elevator mechanical equipment room; upgrade to meet current code requirements including back-up power | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 4 | 2016 | 20000 | 4 | 2016 | 2 | 2017 | 180000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kulhanek, Matt | Gosselin, Deb | 42661 | 1 | New project; updated schedule; Fall 2015: adjusted schedule per Council budget approval Fall 2016: marked as TBC | NULL | 0 | 0 | MFCB1204.jpg | Crum, Lynn | Kulhanek, Matt | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.73 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1509 | MF-SW-12-01 | Landfill Entrance Improvements | 400000 | NULL | Platt Road entrance drive to Wheeler Center | NULL | NULL | 15 | Security improvements to reduce illegal dumping and facilitate flow and capture of load weights. In addition, there are portions of the concrete road that requires replacement. | Relocate or replace scale operation currently located at MRF; RFID card entry gate;; access road reconfiguration - review of potential habitat with NAP. | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 1 | 2018 | 80000 | 3 | 2019 | 2 | 2020 | 1200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43432 | 0 | New project. Fall 2015: Moved to FY18 Fall 2016: spread costs to FY18 and FY19. Fall17: reduced FY18 and increased FY19; Fall 18: to FY21 | NULL | 0 | 0 | MFSW1201.jpg | Elenbaas, Chris | Gomes, Christina | Fojtik, Chuck | Pennington, Kirk | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.82 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1512 | UT-SN-12-03 | Stone School Rd (I-94 to Ellsworth) Sanitary Extensions | 330000 | NULL | Stone School Rd (I-94 to Ellsworth) | NULL | NULL | 12 | Extend sanitary to s parcels that lack sanitary availability | Coordinate with road corridor need/project; see Stone School Townhomes file for past construction plan for southern section; | NULL | Yes | 1 | 10 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2013 | 1 | 2014 | 5000 | 2 | 2014 | 4 | 2017 | 75000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Troy Baughman | 41233 | 1 | Updated schedule; on 9.26.14 revised scope to keep this number to reflect only the work with TR-SC-14-02 (south o I-94) and created new UT-SN-16- | NULL | 0 | 0 | UTSN1203.jpg | Baughman, Troy | Slotten, Cress | Hutchinson, Nick | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 39.79 | 24 | NULL | Nearing, Mike | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | Project Management | NULL | NULL | 2011-029 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 30300 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1513 | UT-SN-12-04 | System Flow Monitoring in FDD Study Areas | 1000000 | NULL | NULL | NULL | NULL | 12 | Evaluate effectiveness of FDD program by quantifying flow removals; determine future FDD work area focus; and determine impact on previously identified trunkline issues | Coordinate with FDD study areas already completed and past monitoring locations; examine potential of purchasing flow monitors to allow city forces to perform future flow monitoring; use data to update and calibrate sewer model | NULL | No | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2013 | 4 | 2013 | 50000 | 1 | 2014 | 4 | 2014 | 950000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Anne Warrow | 41250 | 1 | Revised years and added funding data post CPC Action - - outside of Capital Budget (CSS; 4/1/11); new data was lost and restored on 12/7/12 | NULL | 0 | 0 | Citywide.jpg | Warrow, Anne | Baughman, Troy | Hupy, Craig | Wooden, Dan | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 51.75 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | 2013-023 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1228801.43 | 2015-08-08 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1029757.36 | 2014-06-28 | 1228801.43 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1514 | TR-BR-12-02 | East Stadium Boulevard Bridges Replacement Project | NULL | NULL | E. Stadium Boulevard - Kipke Drive to S. Industrial Highway | NULL | NULL | 7 | (Replaced former individual bridge project records) | Complete NEPA Process; coordinate project with numerous agencies; examine all utilities within project limits; coordinate project with other City work; public engagement/involvement; prepare funding applications; re-design roadway and bridges. | NULL | NULL | 1 | 38 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2006 | 2 | 2011 | 2610000 | 3 | 2011 | 2 | 2013 | 20390000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Michael G. Nearing, P.E. | 41222 | 1 | Updated project schedule, funding types and amounts, and separated bridge and utility work for the purpose of CIP programming. | NULL | 0 | 0 | TRBR1202.jpg | Cooper, Eli | Pirooz, Homayoon | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 94.48 | 1 | Received Categorical Exclusion in 9/2010; Right-of-way acquisition completed 4/2011; construction plans and specs complete 6/2011; received bids through MDOT 9/2011; begin construction 11/2011; anticipated project completion 6/2013. | Nearing, Mike | Awarded TIGER II discretionary ($13.9 M), Local Bridge Program ($1.67 M) and Transportation Enhancement funds ($1.2 M). | Held several general public meetings through the planning and design phase. Upcoming meetings to include public meetings to announce specific info; monthly open house meetings with construction team. PBM will attend and assist with meetings. | NULL | 38961 | 40025 | 40026 | 40702 | 40875 | 41426 | 1 | 1 | 1 | 1 | Severe | 1 | 1 | University of Michigan interface; multi agency coordination; traffic management | 11 | 0 | Project Management | NULL | NULL | 2006-045 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 23512773.98 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1516 | UT-WS-12-02 | Greenview (Stadium to Scio Church) Water Main Replacement | 400000 | NULL | Greenview (Stadium to Scio Church) | NULL | NULL | 14 | Address water quality issues; | Stadium to Scio Church; upsize main to 8"; coordinate with pavement treatment; consider coordination with Dunsmore/Waverley/Weldon project | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 120000 | 2 | 2024 | 4 | 2024 | 1580000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | New project. Larry brought up again 4/29/15 and see Troy's email of that date. Revised limits to include entire stretch in July 2016; cost updated Nov 2016; moved to FY23 to match road; 2018 cost updated | NULL | 0 | 0 | UTWS1202.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 22.18 | 75 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1517 | UT-WS-12-03 | Provincial (Arlington to Fairlane) Water Main Replacement | 155000 | NULL | Provincial (Arlington to Fairlane) | NULL | NULL | 14 | Address condition | Address condition; replace 500 LF with 8" main | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 25000 | 2 | 2025 | 4 | 2025 | 325000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Baughman, Troy | 42710 | 0 | 2016 - Cost Updated; assuming it will be done with road project; wait until road demands; no additional water main breaks so put on hold in CPAN in March 2018; 2019 another break east of these limits…need to monitor and consider moving fwd | NULL | 0 | 0 | UTWS1203.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 30.1 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1520 | UT-WS-12-06 | Crest/Buena Vista/West Washington Water Main Replacements | 1200000 | NULL | Crest (Huron to Buena Vista), Buena Vista, and Washington (Eighth to Crest) | NULL | NULL | 14 | Fire flow and pressure improvements | DTE needs to replace mains on Buena Vista. Coordinate with resurfacing; work with AAPS re hydrant coverage | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 2 | 2017 | 100000 | 2 | 2018 | 4 | 2018 | 1710000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Allen, Jane | 42710 | 1 | New project. Appears main in Crest btw Buena Vista & W Liberty was replaced in 90s. till need to abandon old 6" in this stretch and move any leads. Not true. Fall 2016: updated costs, moved to FY18/19 | NULL | 0 | 0 | UTWS1206.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 32.76 | 48 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | 160000 | 2018-05-01 | 1890000 | 2018-05-01 | NULL | NULL | NULL | 1 | 2018 | 1749825 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2117171.14 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1521 | UT-WS-12-07 | Dams: Barton Dam Concrete Repairs - Phase II | 1250000 | NULL | Barton Dam | NULL | NULL | 14 | Repair concrete at Barton Dam per recommendations from FERC Part 12 | Repair concrete at Barton Dam per recommendations from FERC Part 12 and per December 2010 recommendations by Stantec. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 100000 | 3 | 2022 | 4 | 2024 | 1400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Gosselin, Deb | 43437 | 0 | Adjusted schedule based on results from FERC Part 12 safety inspection; Fall 2016: GRW - delayed schedule to FY19/20//21. Fall 17: shifted back a year. Fall 18 updtaed per WTP | NULL | 0 | 0 | UTWS1207.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 50.09 | 13 | NULL | Steglitz, Brian | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1522 | UT-WS-12-08 | Dams: Superior Dam Concrete Repairs | 500000 | NULL | Superior Dam | NULL | NULL | 14 | Address recommendations from FERC Part 12 Dam Safety Inspection. | Repair deteriorated concrete at dam structure. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 2 | 2022 | 100000 | 3 | 2022 | 4 | 2024 | 850000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43438 | 0 | Updated schedule based on FERC Part 12 Safety Inspection; Fall 2016: GRW - increased funding and delayed schedule to FY19/20; 100% general funded. Fall 17: SHIFTED BACK ONE YEAR Fall 18: shifted again | NULL | 0 | 0 | UTWS1208.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.56 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1525 | MF-PR-12-03 | Farmers Market Winter Enclosure and Infrastructure Improvements | 90000 | NULL | Farmers Market, Fourth Ave | NULL | NULL | 3 | Winter use of the farmers market is curtailed by cold weather. An enclosure would allow greater use of the facility. | Examine feasibility of enclosing ex. roof structurest. DDA interest in project. Customer/vendor survey conducted to determine future improvements. Examine other enclosed structures; Utilize portion of Market fund balance; need to rescope in light of fun | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | NULL | 2013 | 2 | 2013 | 0 | 3 | 2015 | 2 | 2016 | 200000 | 3 | 2019 | 4 | 2019 | 900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | Moved project ahead, PMAC support. Design complete. Proposed solutions have changed and increased budget. Fall 2016: Updated budget and timing. Scrubbed $25K from 2015. Misc. is market fund and DDA funding; on hold Fall 2017. Moved to FY20 | NULL | 0 | 0 | MFPR1203.jpg | DeWitt, Sarah | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Active | Design | 56.2 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1528 | MF-PR-12-06 | Historic Park Structures Repair/Restoration | 600000 | NULL | Citywide - historic facilities | NULL | NULL | 3 | Staff to evaluate needs bi-annually. | HDC site considerations. Evaluate Greek revival structure and bridge at Island Park, West Park band shell | NULL | No | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2011 | 2 | 2012 | 15000 | 3 | 2024 | 2 | 2025 | 735000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kuras, Amy | Smith, Colin | 43431 | 0 | Updated funding and schedule; updated again 11/12; removed FY15 monies and moved to FY16; Fall 2105: added $150K in FY17; Fall 2106: added funds in FY21; Fall 17: shifted 19 to 22. completed Leslie Homestead. Fall 18: updated | NULL | 0 | 0 | MFPR1206.jpg | Thacher, Jill | Smith, Colin | NULL | Westhoff, Susan | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Active | Design | 47.4 | 14 | West Park Pergola, Island Park Greek Revival Shelter and bridge in design phase. Cobblestone Farm (House) under contract for evaluation. | Kuras, Amy | NULL | Cobblestone Farm Association | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | Minimal | 0 | 0 | Requires Historic District Commission approval | 1 | 0 | Parks and Recreation | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | 1 | NULL | NULL | NULL | 1 | 1 | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 0
1537 | TR-OT-12-04 | Plymouth Road Retaining Walls | 150000 | NULL | Opposite 1621 Plymouth Road between Broadway and Barton Drive | NULL | NULL | 9 | Capital maintenance for precast concrete panel retaining wall on inside of curve and wood retaining wall between road and railroad | H-pile columns are corroding; blasting & painting; near Traver Creek, approx. 100 columns , 10 sq ft face each | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 1 | 2019 | 25000 | 2 | 2019 | 4 | 2019 | 125000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Nearing, Mike | 42660 | 1 | Fall 2016: show in FY19 with 0021; approx. 100 columns , 10 sqft face each @ $50.00 sq.ft. = $50,000, Containment 12000sqft @ $4.00sqft =$48,000.00. Misc. Costs ~ $52,000. Discuss this project with a painting contractor | NULL | 0 | 0 | TROT1204.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 10.32 | 13 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 18187.62 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1557 | TR-AT-12-04 | Ellsworth at Research Park Dr. Pedestrian Crossing | 105000 | NULL | Ellsworth/Research Park Drive intersection | NULL | NULL | 6 | Pedestrian crossing at the intersection to provide safer access between Social Security and AACIL on north side and AAATA stop on the stop; | Possible Sidewalk extension, curb ramps, midblock crossing, and potential culvert installation needed. AAATA involvement and potential funding. Traffic signal study met | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 20000 | 2 | 2018 | 4 | 2018 | 100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 42894 | 0 | Name changed 12/12; switched to 0062. Assigned to Cawley spring 2013; October 2013, Pat indicated that work to be done there is limited enough to fall below 100K; Fall 2016 upped $ and showed AAATA funding; Fall 18 rolled into OT project for signal | NULL | 0 | 0 | TRAT1204.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 58.51 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 8184 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1568 | UT-ST-13-01 | Traver St/AARR Culvert Replacement | 55700 | NULL | Traver St at the Rail Road near Bowen | NULL | NULL | 13 | Replace failed pipe. Previous pipe flow filled. | Awaiting permit from RR. | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2013 | 4 | 2015 | 20000 | 2 | 2015 | 2 | 2015 | 75000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Woodward, Nichole | Gosselin, Deb | 41974 | 1 | New Project | NULL | 0 | 0 | UTST1301.jpg | Woodward, Nichole | Ernst, Kevin | Lawson, Jennifer | NULL | NULL | 1 | NULL | NULL | NULL | AARR | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 28.37 | 33 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1555 | TR-AT-12-03 | Washtenaw Ave/US-23 Underpass Shared-Use Path | NULL | NULL | Washtenaw Avenue Interchange with US 23 | NULL | NULL | 6 | Addition of non-motorized path connection to Pittsfield Township and operational improvements at interchange and adjacent intersection with Carpenter Rd to provide safe non-motorized link and improved traffic flow. | Provision of new shared-use path in MDOT ROW linking existing Ann Arbor and Pittsfield Twp. sidewalk systems. Operational improvements to freeway ramps and intersection immediately east of interchange in Pittsfield Twp. | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | Schedule provided by MDOT. | 0 | NULL | 0 | NULL | 0 | 2 | 2011 | 3 | 2011 | 0 | 2 | 2013 | 3 | 2013 | 2800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Eli Cooper (Cresson Slotten) | 41222 | 1 | Project under construction | NULL | 0 | 0 | TRAT1203.jpg | Sipowski, Les | Rampson, Wendy | Cooper, Eli | Dykman, Dave | NULL | 1 | MDOT | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | safety | 1 | Ann Arbor Non-Motorized Plan | Ann Arbor Transportation Plan Update (2009) | Transportation Improvement Plan (TIP) for Washtenaw County | NULL | Active | Design | 68.82 | 1 | NULL | Sipowski, Les | coordination with site plan development and AATA project; signalized crossing issues at Yost | MDOT lead; public open house anticipated | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | 1 | Moderate | 1 | 0 | NULL | 7 | 0 | Project Management | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1572 | UT-WS-13-02 | Seventh (Potter to Lutz) Raw Water Main 30" Upgrade | 1500000 | NULL | Seventh Street (Potter to Lutz) OR Hutchins( Potter to Princeton) and Seventh (Princeton to Lutz) | NULL | NULL | 14 | Replace and upsize existing 20" transite water main to 30" diameter consistent with previously constructed projects. | Upsize raw water main to 30" diameter: Route study needed to determine optimum location of the proposed water main due to locations of existing utilities within S. Seventh Street. Tie-in point north of Potter Avenue must be determined. May go in Hutchins | NULL | Yes | 0 | 31 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 145000 | 2 | 2024 | 4 | 2024 | 2435000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 43046 | 0 | Fall 2016: May go up Hutchins rather than 7th put left there for now. Footage is about the same; used $860 LF. Fall 17: NC. Fall 18 NC | NULL | 0 | 0 | UTWS1302.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.81 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1573 | UT-WS-13-03 | Dover Place, Riverview, and Huntington Place Water Main | 200000 | NULL | Dover Place and Riverview (Geddes to north of Dover Place) and Huntington Pl | NULL | NULL | 14 | Install water main to service parcels; create water main loop for dead-end main easterly | Install new water mains; create loop to Geddes Ridge; determine extterminus on Huntington Place | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 115000 | 2 | 2018 | 4 | 2018 | 1458200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Nearing, Mike | 43389 | 0 | Schedule to coincide with the Sanitary Sewer in the same location; 2018 cost updated | NULL | 0 | 0 | UTWS1303.jpg | Nearing, Mike | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 39.5 | 33 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2013-037 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 175939.55 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1574 | TR-AT-13-01 | Annual Sidewalk Repair and Curb Ramp Program | 2679000 | NULL | Various locations throughout City | NULL | NULL | 6 | Repair and/or replacement of deficient sidewalks. Includes repair of asphalt R/W sidewalks | Repair and/or replacement of deficient sidewalks utilizing millage monies per vote of community. Art enhancement requested 10/2016 by AC. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | Annual Program | 0 | NULL | 0 | NULL | 0 | 1 | 2013 | 2 | 2017 | 527000 | 2 | 2013 | 4 | 2023 | 14117000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 43434 | 0 | Fall 2015: reduced FY17 to $750 per NH spreadsheet (includes $600K for concrete and $150K for asphalt); Fall 2016: revised 2013-2015 to actual spend from 0062; left 2016 as not yet final; added asphalt sidewalk to figure; Fall 18: added 24-25 funds | NULL | 0 | 0 | TRAT1301.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 47.64 | 20 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2016-021 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 75 | 2014-04-01 | NULL | NULL | NULL | NULL | NULL | NULL | 821790.64 | 2017-09-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | 2017-021 | NULL | NULL | 2018-021 | 2019-06-30 | 1506404.3 | 2019-021 | 2019-06-30 | 768490.93 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1575 | UT-WS-13-04 | Stone School Rd (I-94 to Ellsworth) Water Main Replacement | 825000 | NULL | Stone School Road from I-94 to Ellsworth | NULL | NULL | 14 | Replace portions of water main in conjunction with road reconstruction | Replace portion of water main - length to depend on results of soils testing. | NULL | Yes | 1 | 10 | 2 | NULL | NULL | 1 | 0 | Schedule based on road reconstruction schedule (STP Funding) | 1 | 2012 | 2 | 2012 | 0 | 3 | 2012 | 3 | 2013 | 125000 | 2 | 2014 | 4 | 2014 | 700000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Nearing, Mike | 42661 | 1 | updated schedule | NULL | 0 | 0 | UTWS1304.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 51.62 | 13 | NULL | Nearing, Mike | Doing entire length of road project. | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | Project Management | No | NULL | 2011-029 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1036600 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1578 | MF-PR-13-01 | Gallup Park Boat Launch | 147500 | NULL | Gallup Park | NULL | NULL | 3 | Compliance with State Regulations. | Replace boat launch and connecting pathways. Improve parking. | NULL | Yes | 1 | 40 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2012 | 4 | 2024 | 7500 | 2 | 2025 | 4 | 2025 | 140000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | New project. Updated schedule 12/12. Fall 2105: Moved FY16 to FY18) Fall 2016: no changes. Fall 2017: moved to FY20 Fall 18: moved to 2025 | NULL | 0 | 0 | MFPR1301.jpg | Saam, Cheryl | Kuras, Amy | NULL | NULL | NULL | 1 | MDNR | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 56.34 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 1 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1580 | MF-PR-13-03 | Argo & Geddes Dams - Gates Coating | 600000 | NULL | Argo & Geddes Dams | NULL | NULL | 3 | Painting need to maintain structural integrity of gates. | Coat both wet and dry sides. Does not include Geddes Gate #4. Includes efforts to repair structural steel at Geddes Dam as identified by the State of Michigan. | NULL | Yes | 0 | 40 | 3 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 34000 | 3 | 2020 | 4 | 2020 | 1100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43039 | 0 | Moved from FY17 to FY18 and increased budget.; Fall 2016: GRW - Moved to FY19/20 and increased budget.. Fall 17: NC | NULL | 0 | 0 | MFPR1303.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 36.26 | 17 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1587 | TR-SC-13-07 | Annual Local Street Resurfacing Program (ASRP) | 1500000 | NULL | City-wide, various local and major streets | NULL | NULL | 11 | Prevent deterioration and extend the service life of roadways; | Millage funds to resurface/replace existing pavement, curb & gutter and utility surface structure repairs, sidewalk ramp repair/installation, .Funds shown here are primarily for local street resurfacing as most other projects are listed individually. | NULL | No | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2013 | 2 | 2023 | 36550 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43034 | 0 | Combination of former Annual Local Street Resurfacing Program (TR-SC-06-02) and Annual Major Street Resurfacing Program (TR-SC-06-03); mostly local street resurfacing; Fall 2016: increased FY16 and FY17 to $3M. Updated schedule/funding. Fall 17; updated | NULL | 0 | 0 | TRSC1307.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 41.32 | 36 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 2016 | 1 | 2016 | 5390000 | NULL | NULL | 2016-04-18 | NULL | NULL | NULL | NULL | NULL | 6449689.83 | 2018-05-12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 7355322.381 | 2019-02-16 | 0 | 319271.52 | 647749.57 | 5270230.86 | 57179.24 | 2667.45 | 152590.19 | Low Local | 2017-004 | NULL | NULL | 2018-004 | 2019-06-30 | 5271413.18 | 2019-004 | 2019-06-30 | 1659136.19 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1610 | UT-SN-14-01 | Glen/Fuller Diversion (DOM) | 300000 | NULL | Glen and Fuller Sanitary manhole 71-71813. | NULL | NULL | 12 | Construct diversion identified in Swift Run relief project. | Adjustable diversion plate desired to address necessary diversion identified in Swift Run Relief project. The area was further studied as part of the SSWWEEP and identified as Project Area F | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2014 | 2 | 2017 | 93800 | 3 | 2019 | 4 | 2019 | 550000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Baughman, Troy | 43391 | 0 | Fall 2015: recorded what was spent; added $50K in FY18 for construction work. Fall 2017: FY20 to FY19 and $500K by DOM; 2018 - updated cost to $500k. | NULL | 0 | 0 | UTSN1401.jpg | Nearing, Mike | Baughman, Troy | Hupy, Craig | Slotten, Cress | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Sanitary Sewer Capacity Audit and Model | NULL | NULL | NULL | Active | Design | 57.92 | 4 | Preliminarily reviewed by Liz and constructability questioned. | Nearing, Mike | Coordinate with Plant as this goes to implementation. Traffic control issues due to heavy traffic. Construct in dry weather. | UM and Hospital to be notified in advance. | NULL | NULL | NULL | 41640 | 41729 | NULL | NULL | 0 | 0 | 0 | 0 | Minimal | 0 | 0 | NULL | 1 | 0 | Project Management | No | NULL | 2014-027 | NULL | NULL | 90000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 195283.19 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1611 | UT-SN-14-02 | 2250 Belmont Sanitary Extension | 98000 | NULL | 2250 Belmont Rd | NULL | NULL | 12 | Provide public sewer to serve 2250 Belmont Rd. | Extend public sewer to serve 2250 Belmont Rd. Coordinate with UT-WS-08-20. Examine potential service need for landlocked parcel 09-09-34-213-023. | NULL | NULL | 1 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2013 | 3 | 2013 | 98000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slotten, Cress | Cress Slotten/Deb Gosselin | 41577 | 1 | Moved year in database on 11/19/2012 per programming. Form date is update date.; did in FY13 as owner's system was failing. | NULL | 0 | 0 | UTSN1402.jpg | Baughman, Troy | Slotten, Cress | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 35.32 | 42 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1612 | UT-SN-14-03 | Rock Creek Drive and Court, and Huntington Drive Sanitary Sewer Extension | 210000 | NULL | Rock Creek Drive, Rock Creek Ct, & Huntington Drive | NULL | NULL | 12 | Extend public sewer to serve properties currently served by private sewer. Adequately serve the area. | Dealing with private sewer. Evaluate other areas for possible extension. PW has indicated structural issues in nearby 12" pipe. Reference 1998 Utility Services Plan. Easement issues Parts of Hunitington Dr. not public). Coordinate with water project. | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 2 | 2024 | 300000 | 2 | 2025 | 4 | 2025 | 2600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Baughman, Troy | 43391 | 0 | Bumped figures up 24% in Fall 2014 because not adjusted in some time. Fall 2016: expanded project scope; adjusted costs and spread. Fall 17; advanced $250,000 into FY18. 2018 - Cost Updated. 2019 closed repair phase. | NULL | 0 | 0 | UTSN1403.jpg | Baughman, Troy | Slotten, Cress | Elenbaas, Chris | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 49.17 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 363589.88 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | 2017-036 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1614 | UT-SN-14-05 | Lift Station Repair/Replacement Program | 2000000 | NULL | Various locations throughout the City | NULL | NULL | 12 | Aging lift stations need to be repaired/replaced. Liberty Lift Station to be first | Each lift station evaluated individually. Prioritize stations; may split out each lift station as an individual CIP Project. | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 4 | NULL | 4 | NULL | 0 | 1 | NULL | 1 | NULL | 0 | 4 | 2018 | 4 | 2022 | 2650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Englet, Chris | Gosselin, Deb | 43440 | 0 | Schedule adjustments. Fall 2015. $0 in FY16; left FY17; bumped FY18 to $700K; added FY20 to replace FY15. Fall 18 updated per WWTP | NULL | 0 | 0 | UTSN1405.jpg | Amicangelo, Mike | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | Water Treatment Plant Facilities Master Plan (2006) | NULL | NULL | NULL | Programmed | Inactive | 43.05 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 1 | 1 | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1615 | UT-SN-14-06 | Sanitary Sewer Lining Projects | 3750000 | NULL | Various Locations Throughout the City | NULL | NULL | 12 | Future sewer lining projects. | Programming of funds; locations to be identified as determined. Using FY17 money for Arboretum area project and general lining | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2014 | 4 | 2020 | 13750000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 41967 | 0 | Added FY2014 monies for Springwater & others from FY13. Add Dartmoor area (high groundwater); combined w/ FY15 monies; look at 71-63323 (Stadium/Iroquois) to 71-70536 (Miller/First); Fall 2015: deducted $250K each in FY16 and 17 to allow for cleaning stu | NULL | 0 | 0 | UTSN1406.jpg | Cozart, Mark | Kotlyar, Igor | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 58.16 | 3 | $750,000 pot presently available (FY14); tech staff to discuss best use of funds; many unmet needs; Arboretum needs to be added to list | Warrow, Anne | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | Project Management | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | 2015 | 20000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 96081.39 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | 2017-032 | NULL | NULL | 2015-040 | 2018-03-31 | 937530.49 | 2016-026 | 2018-03-31 | 1471560.17 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 1 | 1 | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
1925 | TR-AT-18-04 | Green (Frederick to Glazier) Sidewalks | 560000 | NULL | Green (Frederick to Glazier; west side | NULL | NULL | 6 | Complete sidewalk system | Install approximately 2800 LF of sidewalks to fill existing gaps; some UM frontage. Difficulty Rating: 1-2 (Topography, Utility Conflict, Natural Features, Drainage) | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 37000 | 2 | 2025 | 4 | 2025 | 560000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2106: New; showed general fund as placeholder. Fall 18: showed county millage and 0062 as tentative funding and moved to FY25 | NULL | 0 | 0 | TRAT1804.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 47.24 | 21 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1607 | TR-AP-14-01 | Reconstruct Southeast and Northeast Taxiways | 1138000 | NULL | Southeast and Northeast Taxiways | NULL | NULL | 5 | Reconstruction of aged pavements | Coordination with tenants | NULL | No | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 75000 | 2 | 2025 | 3 | 2025 | 1085000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kulhanek, Matt | Deb Gosselin | 42691 | 0 | Fall 2016: updated $ | NULL | 0 | 0 | TRAP1401.jpg | Kulhanek, Matt | Crum, Lynn | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | AIP Capital Improvement Plan | NULL | NULL | NULL | Programmed | Inactive | 35.65 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
1608 | MF-SW-14-01 | Landfill Remedial Action Plan Contingency | 200000 | NULL | Boundaries of closed landfill and influence of groundwater plume | NULL | NULL | 15 | Financial assurance mechanism for MDEQ closure. Reserved project for potential issues in future for meeting compliance with Remedial Action Plan (RAP). | Potential future need. Estimate based on installation of 3-5 extraction wells and associated piping for discharge to sanitary system. NAP | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2016 | 4 | 2016 | 80000 | 3 | 2017 | 2 | 2018 | 450000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Naud, Matt | Gosselin, Deb | 42705 | 1 | Approval of Off-site RAP is anticipated by June of 2015. Fall 2016: spread costs mostly to FY18 | NULL | 0 | 0 | MFSW1401.jpg | Naud, Matt | Warrow, Anne | Borneman, Dave | NULL | NULL | 1 | MDEQ | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 32.52 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1609 | MF-SW-14-02 | Solid Waste Resources Management Plan (2019-2023) | 25000 | NULL | Citywide | NULL | NULL | 15 | Replace 2013-2017 Solid Waste Management Plan | Replace 2013-2017 Solid Waste Management Plan; provide 5 year strategic direction for all solid waste program arreas (municipal solid waste, recycling, and compost/organics) | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 1 | 0 | NULL | 2 | 2018 | 2 | 2019 | 250000 | 0 | NULL | 0 | NULL | 0 | 3 | NULL | 2 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slotten, Cress | Gosselin, Deb | 42696 | 1 | Figures are per TM. Fall 2016: Updated budget to reflect using consultant and more detailed and moved to FY18. Fall 18 marked TBC | NULL | 0 | 0 | MFSW1402.jpg | Gomes, Christina | Naud, Matt | Slotten, Cress | Maciejewski, Molly | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 21.75 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1639 | UT-ST-14-01 | Village Oaks-Chaucer Court Stormwater Improvements | 1250000 | NULL | Scio Church to Ann Arbor-Saline Road to Malletts Creek | NULL | NULL | 13 | Implement recommendations from Village Oaks-Chaucer Court Stormwater Study | project contains two components: 1) A Regional basin (petition to WCWRC); additional inlets; 2) emergency overflow/relief pipe from Village Oaks/Chaucer Area | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2014 | 2 | 2018 | 225000 | 2 | 2017 | 4 | 2017 | 613600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 43045 | 0 | Fall 2015:no action; acquire land for $175K and w/ total costs at $550k to $725K; $250K is overflow; budgeted $600K as max available; adj. FY15 to actual spent. Fall 2016: adjusted and spread costs through FY18. Fall 17: NC | NULL | 0 | 0 | UTST1401.jpg | Baughman, Troy | Slotten, Cress | Hancock, Jerry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Village Oaks-Chaucer Court Stormwater Study | NULL | NULL | NULL | Active | Design | 50.79 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 630657.86 | 2019-07-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1640 | UT-ST-14-02 | Rain Garden Installation on City Owned Property | 300000 | NULL | 10 locations throughout the City | NULL | NULL | 13 | To address water quality goals including TMDLs | Possible locations include skate park at Veterans Park, tennis court at Veterans Park, Arbor Oaks Park. PAC. Address future maintenance issues. | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hancock, Jerry | Lawson, Jennifer | NULL | 1 | 6/11/13: Arbor Oaks ($165K) and Skate Park (?) appear to be consuming the entire budget and it was not in the capital budget. | NULL | 0 | 0 | UTST1402.jpg | Lawson, Jennifer | Hancock, Jerry | Kuras, Amy | Sheehan, Harry | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Huron River 2010 SRF Project Plan | NULL | NULL | NULL | Active | NULL | 61.17 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1641 | UT-ST-14-03 | Malletts Streambank Stabilization Phase II | 2200000 | NULL | Malletts Creek from Cranbrook Park to Eisenhower | NULL | NULL | 13 | Address water quality and TMDLs | Continue Malletts Streambank Stabilization; iincludes Mallets Creek from Cranbrook Park to Eisenhower; requires WCWRC petition; complete Briarwood Pond modeling and Churchill Basin and reasses before proceeding | NULL | No | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 3 | 2013 | 4 | 2013 | 0 | 3 | 2023 | 1 | 2023 | 200000 | 2 | 2024 | 4 | 2024 | 2570000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43045 | 0 | Do not yet have easements; Fall 2015: swapped for Churchill Park basin and moved to FY19; Fall 16 moved to 22/23 and spread costs; Fall 17: put in FY19; Fall 18 moved back | NULL | 0 | 0 | UTST1403.jpg | Lawson, Jennifer | Sheehan, Harry | NULL | NULL | NULL | 1 | Washtenaw County Water Resources Commission | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Huron River 2010 SRF Project Plan | NULL | NULL | NULL | Programmed | Inactive | 52.62 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1645 | UT-ST-14-07 | Storm Sewer Rehabilitation and Lining Projects | 1200000 | NULL | Citywide | NULL | NULL | 13 | Provide a cost-effective means of addressing deteriorating stormwater pipes. | Llining of deteriorating storm pipe in various locations throughout the City. This mechanism allows for cost efficiency by bidding the needed work in larger contracts | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2014 | 4 | 2025 | 2700000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Deb Gosselin | 43024 | 0 | Include Plaza Drive with County project?? Awixia is still a need. Fall 2015: Fall 2015: zeroed pot to cover Village Oaks. Fall 2016: shifted funds and renamed. Fall17: increased FY18 to $300K per budget | NULL | 0 | 0 | UTST1407.jpg | Ernst, Kevin | Lawson, Jennifer | Kotlyar, Igor | Warrow, Anne | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 42.54 | 18 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | 2015 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 56371.77 | 2016-09-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | 2013-019 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | 1 | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1593 | UT-WS-14-04 | Geddes Road (Huron Pkwy to Windy Crest) Water Main Replacement | 1381600 | NULL | Geddes Road (Huron Parkway to Windy Crest) | NULL | NULL | 14 | Aging water main. Numerous breaks. | Replace main presently out of service. | NULL | No | 1 | NULL | 2 | NULL | NULL | 0 | 0 | NULL | 3 | 2013 | 3 | 2013 | 0 | 1 | 2024 | 4 | 2024 | 95000 | 2 | 2025 | 4 | 2025 | 1205000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43438 | 0 | On hold; showed in FY16 and FY17 for now (4/3/13); costs not updated in Fall 2014. Fall 17: added design phase FY18-19; Fall 18 - deleted study phase per discuissions with WTP, assume do with road; pushed out | NULL | 0 | 0 | UTWS1404.jpg | Wooden, Dan | Sanford, Larry | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 35.05 | 45 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1651 | UT-ST-14-13 | Scio Church (Main to Seventh) Stormwater Improvements | 750000 | NULL | Scio Church (Main to Seventh) | NULL | NULL | 13 | Contribute towards stormwater management in Upper Malletts area | Coordinate with road project.; review Upper Mallelts study; implement stormwater improvements as acheivable within the confins of a resurfacing project | NULL | Yes | 1 | NULL | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2016 | 2 | 2017 | 15000 | 3 | 2018 | 4 | 2018 | 210000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Nelson, Jenn | 43045 | 1 | Cots bumped up in Fall 2014. $220,000 for Stormwater imps granted 8/8/16. Fall 17: NC | NULL | 0 | 0 | UTST1413.jpg | Lawson, Jennifer | Sheehan, Harry | Baughman, Troy | Rolla, Liz | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 34.63 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 153946.15 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1594 | UT-WS-14-05 | Dicken Drive Looping Water Main | 255000 | NULL | From Dicken Drive to either Carol or Maple | NULL | NULL | 14 | Loop dead-end main. | Potential loop to Maple and/or Carol. Evaluate hydrant coverage for Dicken School. Engage with Friends of Dicken Woods, Construct approximately 550 LF of new water main; Will require an easement thru Dicken Woods and restoration | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 4 | 2025 | 50000 | 2 | 2026 | 2 | 2026 | 242000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 42710 | 0 | Scheduled added. Fall 2016: moved to beyond 23. Fall 18: costs not updated; moved to FY26 | NULL | 0 | 0 | UTWS1405.jpg | Sanford, Larry | Baughman, Troy | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 21.19 | 76 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1655 | TR-TR-14-01 | Ann Arbor Station NEPA/PE | 2750000 | NULL | TBD | NULL | NULL | 16 | High speed intercity passenger rail program. | Environmental review and preliminary engineering associated with proposed Ann Arbor Station. Planning study. | NULL | No | 0 | 0 | 4 | NULL | NULL | 1 | 0 | NULL | 4 | 2012 | 2 | 2017 | 2386000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Cooper, Eli | 42690 | 0 | Begun in FY13 and carrying forward with contractor efforts scheduled for FY14/15 fro NEPA and FY15/16 for PE work. Fall 2016: additional general funds to be requested | NULL | 0 | 0 | TRAT1401.jpg | Cooper, Eli | Dykman, Dave | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Transportation Plan Update (2009) | NULL | NULL | NULL | Active | Planning | 72.37 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2013-024 | 1200000 | 2017-06-21 | 2308000 | 2017-06-21 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Adjusted | Adjusted | NULL | NULL | NULL | NULL | 692205.31 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1658 | TR-AT-14-04 | Washtenaw Ave (Pittsfield to Huron Pkwy) Shared Use Path | 80000 | NULL | Service drive along south side of Washtenaw Ave | NULL | NULL | 6 | Provision of non-motorized facility to link MDOT provided path with City non-motorized network. Part of reimagining Washtenaw Corridor; figures assume using existing parking area as a major segment of the path. | ADA compliant driveway crossings and parking blocks/restriping of parking areas within City ROW. Explore adding miblock crossing of Washtenaw (per Eli) - cost estimage will need to be updated to reflect this. | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 3 | 2012 | 4 | 2012 | 0 | 3 | 2019 | 4 | 2019 | 20000 | 2 | 2020 | 4 | 2020 | 150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43433 | 0 | Seeking MDOT TAP Grant Funding for FY2013 funds; eliminate for presentation only as less than 100K per CH. Put back based on updated costs. Fall 17: NC Fall 18: upped $ and show STP and 0062 as source | NULL | 0 | 0 | TRAT1404.jpg | Cawley, Pat | Rampson, Wendy | Cooper, Eli | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 50.02 | 18 | NULL | Warrow, Anne | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1596 | UT-WS-14-07 | Liberty (1501 W Liberty to Seventh) Water Main Replacements | 489000 | NULL | W Liberty (1501 W Liiberty to Seventh), and Crest (Liberty to Buena Vista) | NULL | NULL | 14 | Condition of mains | Replace steel water main in Liberty and on Crest; replace domestic mains per limits stated; examine the need to connect Crest to Huron (this may be needed to supply dual source of gravity water to the area). Eval. 12" main fr. 1501 W Liberty to Crest | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2014 | 1 | 2015 | 125000 | 2 | 2015 | 4 | 2015 | 1465000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Baughman, Troy | 43439 | 0 | 2016 - expanded scope of project dramatically; will do following Crest/Buena Vista work | NULL | 0 | 0 | UTWS1407.jpg | Wooden, Dan | Sanford, Larry | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 32.08 | 54 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1597 | UT-WS-14-08 | Westgate Shopping Center Water Main Replacement | 347000 | NULL | Westgate Shopping Center - in front of Play it Again Sports | NULL | NULL | 14 | Replace and relocate aging water main | New easements. Coordinate with property owners and merchants. | NULL | No | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2024 | 4 | 2024 | 29000 | 2 | 2025 | 2 | 2025 | 318000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Nichole Woodward (Deb Gosselin) | 41239 | 0 | Fall 2106: pushed to beyond 23. Fall 17: NC Fall 18 NC to cost but moved back | NULL | 0 | 0 | UTWS1408.jpg | Wooden, Dan | Sanford, Larry | Slotten, Cress | Baughman, Troy | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 24.16 | 72 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1688 | TR-SC-14-21 | Seventh (Scio Church to Greenview) Road Improvements | 1390000 | NULL | S Seventh (Scio Church to Greenview) | NULL | NULL | 11 | Deteriorated pavement. Storm water improvements. | Investigate reducing pavement width. Evaluate active transportation facilities if road narrows. Coordinate with Upper Malletts Creek Study. Coordinate with Scio Church resurfacing. Water. | NULL | Yes | 0 | 0 | 7 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 1 | 2019 | 80000 | 2 | 2019 | 3 | 2019 | 1220000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Hutchinson, Nick | 43418 | 0 | Project cost is total cost; design not yet broken out. Will be a reconstruct with narrowed lanes. Updated schedule/funding. Fall 2016: updated. Fall 17: moved to FY21 per NH | NULL | 0 | 0 | TRSC1421.jpg | Rolla, Liz | Cooper, Eli | Lawson, Jennifer | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.19 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1637 | TR-OT-14-01 | S Main St Street Light Poles, William to Huron | 600000 | NULL | Main Street | NULL | NULL | 9 | Poles rusting and failing. | Coordinate with DDA. Determine extent of replacement. | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 1 | 2014 | 4 | 2014 | 580000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Fojtik, Chuck | Deb Gosselin | 41957 | 1 | Per Susan Pollay, amount to be funded from DDA is $300,000. Per Marti, General fund to contribute $280K; updated accordingly; then Susan changed to all DDA | NULL | 0 | 0 | TROT1401.jpg | Fojtik, Chuck | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 19.95 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1690 | MF-PR-14-08 | Urban Park/Plaza Improvements | 175000 | NULL | Downtown public parks | NULL | NULL | 3 | Design improvements and repairs as needed. | Potential work at Liberty Plaza. Coordinate with DDA | NULL | No | 0 | 0 | 8 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2013 | 1 | 2014 | 10000 | 3 | 2021 | 2 | 2022 | 165000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | PAC suggests that programming be explored prior to redesign. Coordinate with Library Lot. Fall 2016:moved to FY22 as no activity. Fall 18 NC | NULL | 0 | 0 | MFPR1408.jpg | Kuras, Amy | Smith, Colin | Pollay, Susan | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Programmed | Inactive | 27.12 | 20 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | 1 | 2 | 2 | 1 | NULL | 1 | 2 | 1 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1695 | UT-ST-14-22 | Seventh (Scio Church to Greenview) Stormwater Improvements | 650000 | NULL | S Seventh (Greenview to Scio Church) | NULL | NULL | 13 | coordinate with road project. Must address Chapter 63 requirements | Provide stormwater per Chapter 63 if reconstructed to remove pavement | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 50000 | 2 | 2022 | 4 | 2022 | 600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43045 | 0 | Costs not updated Fall 2014. Fall 2016; spread costs but did not adjust; will design to this $; not SRF. Fall 17: moved to match street and back to SRF | NULL | 0 | 0 | UTST1422.jpg | NULL | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | Washtenaw County Water Resources Commission | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 42.14 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | 3 | 1 | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1605 | UT-WS-14-16 | Main St (RR Bridge to Huronview Blvd) Water Main Upsizing | 800000 | NULL | North Main, Railroad bridge to Huronview Blvd. | NULL | NULL | 14 | Undersized main. | Possible upsizing of main. MDOT driven. Peter Allen developments. North Main corridor study. High groundwater. | NULL | Yes | 1 | 43 | 2 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 0 | 2 | 2022 | 4 | 2022 | 2100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: MDOT paved area w/o giving notice so moved to beyond 23; Fall 17: advanced design to FY19 for MDOT to do but then assumption was billed later; need to revisit as Finance says have to bill in yer costs incurred. Fall 18 updated $ and to FY2 | NULL | 0 | 0 | UTWS1416.jpg | Baughman, Troy | Cooper, Eli | Pulcipher, Connie | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.06 | 25 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1606 | UT-WS-14-17 | Water Meter and MTU Replacement Program | 1250000 | NULL | Citywide | NULL | NULL | 14 | Establish replacement program for MTUs and water meters. | Evaluate condition of existing MTUs and meters. Run bench test on sample meters from system for evaluation. Smart meter issue. Public engagement needed. | NULL | No | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 850000 | 3 | 2017 | 4 | 2021 | 9400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Matthews, Paul | Deb Gosselin | 43438 | 0 | Input numbers from programming meeting. Skipped FY2014 as oversubscribed. Fall 2015: reduced FY 16 and FY17 to 25K each to evaluate; then anticipate that later years will rise considerably; loaded 250K each into FY20-FY21 and FY22 to keep total for now | NULL | 0 | 0 | UTWS1417.jpg | Matthews, Paul | Steglitz, Brian | NULL | Wingle, Aimee | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 9.11 | 87 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1616 | TR-SC-14-01 | Stone School Rd (Packard to Eisenhower) Resurfacing | 2240000 | NULL | Stone School Road - Packard to Eisenhower | NULL | NULL | 11 | Pavement condition | Sanitary missing from Packard to Ticknor. | NULL | Yes | 1 | 10 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 10000 | 2 | 2018 | 4 | 2018 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 1 | New CIP entry - split apart from the I-94 to Ellsworth section. In Fall 2014, changed to resurface and split Eisenhower to I-94 out as CMP. Moved to FY19; updated schedule/funding. Fall 17: to FY18 | NULL | 0 | 0 | TRSC1401.jpg | Hutchinson, Nick | Slotten, Cress | Lawson, Jennifer | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | NULL | NULL | NULL | Programmed | Inactive | 50.73 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1622 | TR-SC-14-06 | State St (Huron to S University) Resurfacing | 675000 | NULL | S State - Huron to S University | NULL | NULL | 11 | Pavement condition | Resurfacing; Sanitary main issues, lining or replace. Coordinate with DDA streetscape work; UM Coordination; bike connections William to North U on State and State to Thayer on North U; IT also would like to add conduit | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 0 | 2 | 2020 | 4 | 2020 | 1930000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Hutchinson, Nick | 43410 | 0 | Added funds from DDA for streetscape. Updated schedule/funding. Fall17: Moved FY19-20 to FY20-21 | NULL | 0 | 0 | TRSC1406.jpg | Dykman, Dave | Miller, Amber | Rolla, Liz | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 59.12 | 13 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1623 | TR-SC-14-07 | Fifth Ave (Kingsley to Catherine) Road Reconstruction | 2000000 | NULL | Fifth Ave (Kingsley to Catherine) and Detroit (Fifth to Kingsley) | NULL | NULL | 11 | Poor road condition. | Historic brick pavers. Examine possible use of permeable brick pavers. ADA issues. Drainage issues. Detroit Street crossing. DDA Streetscape. Research Council involvement on traffic direction on Detroit St. Examine utilities. H20. Building foundations | NULL | Yes | 1 | 12 | 2 | NULL | NULL | 1 | 0 | NULL | 4 | 2012 | 0 | NULL | 0 | 3 | 2015 | 4 | 2017 | 500000 | 2 | 2018 | 4 | 2019 | 4632185 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Slizewski, Brian | 42688 | 1 | Moved construction back a year per NH (4/2/13); water and storm construction needed with this project; Fall 2015 added design money in FY16 and FY17 to coordinate with DDA. | NULL | 0 | 0 | TRSC1407.jpg | Rolla, Liz | Pollay, Susan | Thacher, Jill | Hancock, Jerry | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 55.88 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2015-037 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 2018 | 1 | 2018 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1426891 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1625 | TR-SC-14-09 | Scio Church (Main to Seventh) Road Improvements | 1000000 | NULL | Scio Church from Main to Seventh | NULL | NULL | 11 | Deteriorated pavement condition. | Sidewalk gaps. Examine storm water management. Upper Malletts Drainage Improvements Study. Concern with soils. Check township parcels on the south side (sanitary/water availability). Investigate crash history at Main based on WATS comments. | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 2 | 2017 | 175000 | 2 | 2018 | 4 | 2016 | 1699250 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Nelson, Jenn | 43038 | 1 | Put in 2016 to match storm funds. Fall 2104: Moved to FY18 to avoid doing at same time as Stadium; Fall 2105: corrected funding from $2M to $1M. Fall 2016: using STP money and spread costs. Fall 17: addedd $100K of 0062 per Nick | NULL | 0 | 0 | TRSC1409.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 40.42 | 13 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2014-034 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 766063.78 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1626 | TR-SC-14-10 | ASRP - Green Rd (Nixon to Burbank)
ASRP - Green Road (Nixon to Burbank) | 1720000 | NULL | Green Road (Nixon to Burbank) | NULL | NULL | 11 | Deteriorated pavement. | HMA path issue. Resurface.. Coordinate with development. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2012 | 1 | 2013 | 0 | 2 | 2016 | 4 | 2016 | 1565000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 42300 | 1 | Fall 2015: Move back from FY17 to FY16 to do before intersection project | NULL | 0 | 0 | TRSC1410.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 21.24 | 39 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1628 | TR-SC-14-12 | Pauline (Stadium to Seventh) Road Improvements | 1150000 | NULL | Pauline from Stadium to Seventh | NULL | NULL | 11 | Deteriorated pavement condition | Multiple water main breaks. Investigate water main upsizing. Probable reconstruction; Be sure to check signals on Seventh; add to SCOOT; also will need a storm project if this goes to reconstruction. | NULL | Yes | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 1 | 2018 | 150000 | 2 | 2018 | 4 | 2018 | 1000150 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 43038 | 1 | Figures are for resurfacing. Changed schedule Fall 2013. Fall 17: updated $ | NULL | 0 | 0 | TRSC1412.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 50.31 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | 240000 | 2018-05-01 | 2087700 | 2018-05-01 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2960429.6 | 2018-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1631 | TR-SC-14-15 | Miller - Newport Intersection Improvements | 1410000 | NULL | Miller/Newport Intersection | NULL | NULL | 11 | Desire for a roundabout identified through the Miller Road public engagement process. | ROW acquisition will be required. | NULL | No | 1 | 9 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 100000 | 2 | 2024 | 4 | 2024 | 700000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43038 | 0 | Updated year of construction. Fall 2015: NC but Nick shows $800k in FY18; edit next fall. Fall 17: NC | NULL | 0 | 0 | TRSC1415.jpg | Hutchinson, Nick | Carson, Chris | Sipowski, Les | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 39.78 | 38 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1633 | MF-CB-14-02 | 2000 South Industrial Site Evaluations | 425000 | NULL | 2000 South Industrial | NULL | NULL | 1 | Evaluate site use | Evaluate future use of site; Housing Commission in place for 3-5 more years; evaluate condition of existing structures; Phase 1 and 2 (if needed) of site, structures & hazardous wastes in building; site use analysis following ESA; deed restrictions | NULL | No | 0 | NULL | 4 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 2 | 2021 | 75000 | 4 | NULL | 3 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Stults, Missy | Gosselin, Deb | 43432 | 0 | Figures per programming meeting; updated funding and schedule to reflect latest. Fall 2016: moved to FY18. Fall17: moved to FY20. Fall 18: moved to 21 as no one is claiming this project | NULL | 0 | 0 | MFCB1402.jpg | Kulhanek, Matt | Crum, Lynn | Hupy, Craig | Hancock, Jerry | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 18.33 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 3 | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 1
1635 | MF-CB-14-04 | Fire Stations 1 and 6 Rehabilitation Program | 68000 | NULL | Fire Stations 1 and 6 | NULL | NULL | 1 | Rehabilitate aging structures | Basic renovations needed at both facilities.; Fire Station 1 also includes elevator and mechanical units | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 3 | 2017 | 221000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Taylor, Ellen | Gosselin, Deb | 42661 | 1 | Figures furnished by Facilities/Fire; upped budget on 4/2/13; funds revised Fall 2014 to include elevator at Station 1 and mechanical units at both: Fall 2015 moved to FY17 per Council Fall 2016: marked as TBC | NULL | 0 | 0 | MFCB1404.jpg | Taylor, Ellen | Kulhanek, Matt | Crum, Lynn | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 47.54 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1636 | MF-CB-14-05 | 415 West Washington | 300000 | NULL | 415 W Washington | NULL | NULL | 1 | Determine reuse of site | Potential scope: limited work to secure buiildings; structural determination if chimney can be retained when buildings are demolished as approved by Historic District Commission; complete environmental site investigation; | NULL | Yes | 1 | 18 | 5 | NULL | NULL | 1 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 1 | 2016 | 133000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Deb Gosselin | 43431 | 0 | Budget rev. 4/2/13 based on Finance decision; figure is per doing minimal health, safety, welfare work for now (12/13); Fall 2015 revised budget per Council. Fall 17: NC Fall 18: funds not changesd as already approved; spent down partially | NULL | 0 | 0 | MFCB1405.jpg | Gosselin, Deb | Naud, Matt | Thacher, Jill | Warba, Matt | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 32.7 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | 2 | NULL | NULL | NULL | 1 | 1 | NULL | NULL | 1 | 1 | 0 | NULL | NULL | 1
1976 | TR-OT-18-05 | Stadium, Maple, Fuller, Huron Pkwy SCOOT Expansion | 450000 | NULL | Stadium (Pauline to Maple), Maple (Pauline to Miller), Glen/Fuller Rd (W Huron to Huron Pkwy) Glazier Way (Fuller to Huron Pkwy), Huron Pkwy (Huron River Dr to Hubbard) | NULL | NULL | 9 | Expand SCOOT system for critical corridors | Interconnect traffic signal at Maple & Pauline; Expand SCOOT system along Maple & W. Stadium; MDOT involvement at Huron/Jackson; CMAQ; | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 0 | NULL | 120000 | 4 | 2019 | 2 | 2019 | 1087500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Liu, Luke | 42674 | 0 | Fall 2016: new; used zmiscellaneous for IT funds. Fall 17: Per LL, grant sought is $530K and local needed is $50K. Fall 18 updated $ and funding; Glazier Waty removed per LL June 2019 | NULL | 0 | 0 | TROT1805.jpg | Liu, Luke | Fojtik, Chuck | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.88 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1662 | MF-PR-14-01 | Whitewater Amenities at Argo | 300000 | NULL | Argo | NULL | NULL | 3 | Recreational opportunities expansion | Part of DTE remediation project. Schedule dependent on resolution of any environmental issues. | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 2 | 2025 | 300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | Moved back to FY17 in Fall 2013 per PR. Fall 2015: moved FY17 to FY18; Fall 2016: moved to FY23; Fall 18: to FY25 | NULL | 0 | 0 | MFPR1401.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.37 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | 2 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1663 | MF-PR-14-02 | Leslie Science and Nature Center Master Plan Implementation | 200000 | NULL | LSNC | NULL | NULL | 3 | Provide barrier-free access and improve parking efficiency. | First phase completed, including paths in upper area connecting facilities and raptor enclosure. Stormwater improvements, replace paths, improve parking area. Requires grant funding. | NULL | No | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 4 | 2012 | 3 | 2015 | 0 | 2 | 2012 | 3 | 2016 | 0 | 3 | 2021 | 4 | 2021 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 42688 | 0 | Moved from FY2016 to FY2017 Fall 2106: moved to FY22. Fall 18 NC | NULL | 0 | 0 | MFPR1402.jpg | Kuras, Amy | Westhoff, Susan | Landefeld, Josh | Borneman, Dave | NULL | 0 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Programmed | Inactive | 67.84 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | 1 | NULL | NULL | 1 | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 1
1664 | MF-PR-14-03 | Leslie Park Golf Course Cart and Other Storage | 150000 | NULL | LPGC | NULL | NULL | 3 | Security and storage. | Golf cart storage and potential conversion to electric carts. Stormwater improvements. Investigate green roof/solar potential. Will require site plan review. Investigate potential for other equipment storage/solid waste cart storage. | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 3 | 2015 | 20000 | 2 | 2016 | 1 | 2016 | 230000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 42688 | 1 | Move project and funding to FY2016 - current gas cart lease goes through 2015. Fall 2015:Increased budget to $250k Fall 2016: marked as to be completed | NULL | 0 | 0 | MFPR1403.jpg | Warba, Matt | Smith, Colin | Kelly, Doug | Hancock, Jerry | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Programmed | Design | 52.19 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1682 | TR-TR-14-06 | Ann Arbor Station Phase 1 Final Design | 2600000 | NULL | South side of Fuller Rd east of East Medical Center Drive | NULL | NULL | 16 | Train station replacement project due to the inadequacies of current station. | Design of Phase 1 train station including 1) intermodal structure for transit operations and station vehicular parking; 2) elevated train station, platform, and elevators; 3) retaining wall at UM Hospital area; 4) connecting bridge to UM medical campus | NULL | No | 0 | 0 | 6 | NULL | NULL | 1 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2020 | 2 | 2023 | 14700000 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Nearing, Mike | 43413 | 0 | Moved back a year per Council (changed her 4/2/13). Fall 2016: moved to FY18 per Eli, Fall 17: moved to 19; Fall 18: updated costs per PE effort | NULL | 0 | 0 | TRAT1406.jpg | Cooper, Eli | Dykman, Dave | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Transportation Plan Update (2009) | NULL | NULL | NULL | Programmed | Inactive | 72.37 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1683 | TR-TR-14-07 | Ann Arbor Station Phase 1 Construction | 44500000 | NULL | TBD | NULL | NULL | 16 | Project identified in 2009 Master Plan update. Preliminary engineering and final design must precede. | Construction of train station, platforms, intermodal facility, parking. Dependent on citizen vote. Additional funding partners to be investigated. General funds shown would be lowered accordingly. Art enhancement requested. | NULL | No | 0 | 0 | 6 | NULL | NULL | 1 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2020 | 86068000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 42996 | 0 | Fall 2016: moved back one year per Eli and edited to 65M; added art request 6/2017. Fall 17: moved to 20 | NULL | 0 | 0 | TRAT1407.jpg | Cooper, Eli | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Transportation Plan Update (2009) | NULL | NULL | NULL | Programmed | Inactive | 72.37 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 2 | 2 | 2 | 2 | NULL | NULL | NULL | 1 | 2 | 2 | 1 | 2 | 2 | 1 | NULL | NULL | 1 | 1 | 1 | 2 | 650000 | 1
1697 | UT-ST-14-24 | Briarwood Mall Pond | 700000 | NULL | Behind Briarwood Mall; inline on Malletts Creek | NULL | NULL | 13 | Provide regional stomwater storage | Provide regional stomwater storage;in SRF 2017-2021 Plan; if private owner dredges and adds pretreatment, City may take over pond and expand for regional storage | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 85000 | 3 | 2022 | 4 | 2022 | 1115000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43045 | 0 | Fall 2016: $ not updated; Fall 17:NC Fall 18: revised scope and booked all to 2022 as County run SRF | NULL | 0 | 0 | UTST1424.jpg | Sheehan, Harry | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.57 | 24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 2 | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1706 | TR-AT-14-08 | Border to Border Trail: Bandemer to Barton Connection | 2800000 | NULL | Bandemer and Barton Parks shared boundary | NULL | NULL | 6 | Create safe and legal non-motorized access route from Bandemer Park to W Huron River Drive. Border to Border connection. | Review 2005 study for RR crossing and determine best alternative and construction cost estimate; potential paved path in Barton Nature Area | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2007 | 50000 | 3 | 2019 | 4 | 2019 | 362500 | 2 | 2020 | 4 | 2020 | 4150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kuras, Amy | Gosselin, Deb | 43433 | 0 | Mimics elimi. MF-PR-10-03;. Past amount spent for study was 50K ;(Fall 2016: Budget adjusted up per County; county millage as part funding; general fund. Fall 17: moved to FY20/21 per DD Fall 18: assumes TAP and GF | NULL | 0 | 0 | TRAT1408.jpg | Kuras, Amy | Cooper, Eli | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | Ann Arbor Non-Motorized Plan | NULL | Programmed | Inactive | 72.71 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1708 | UT-WS-14-19 | Pauline (Stadium to Seventh) Water Main Replacement | 1200000 | NULL | Pauline (Seventh to Stadium) | NULL | NULL | 14 | History of water main breaks. Present 6" main is undersized per current standards. Main should be 12" to complete the Russett/Redeemer/Eberwhite school loop. | Evaluate condition of main and upsize to accommodate current design standards and address needed capacity. Coordinate with road project. Cost based on being done with road project | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | 0 | NULL | 0 | 3 | 2017 | 1 | 2018 | 115000 | 2 | 2018 | 4 | 2018 | 1285000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 43046 | 1 | Shifted back one year due to street construction change per Fall 2103 CIP modifications. Fall 2016: spread costs. Fall 17: NC | NULL | 0 | 0 | UTWS1419.jpg | Baughman, Troy | Rolla, Liz | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Condition Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 41.81 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1722 | MF-CB-15-08 | Housing Commission: Green Baxter Court | 6325000 | NULL | 1701 Green Rd | NULL | NULL | 1 | Rehabilitate aging facilities and improve energy efficiency | Renovate units as needed; LED exterior and CFL interior lights, ecobee thermostats, energy star windows, low-VOC paint | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2013 | 2 | 2014 | 0 | 3 | 2014 | 4 | 2014 | 5000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hall, Jennifer | Gosselin, Deb | 41905 | 1 | Updated cost and indicated as to be complete by end of FY15 | NULL | 0 | 0 | MFCB1508.jpg | Hall, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1747 | TR-SC-15-02 | Annual Capital Street Maintenance Program | NULL | NULL | Citywide | NULL | NULL | 11 | Capital maintenance to extend pavement life for financial efficiency | Utilize techniques other than resurfacing and reconstruction to maintain city street systems; integrate in pavement asset management program | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2014 | 2 | 2023 | 10320000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43038 | 0 | Fall 2015: reduced FY16 because added County Millage projects as separate item; need to modify FY19 on at next Fall's CIP. Updated schedule/funding. Fall 17: reduced FY18 as STP funds directed to specfic projects | NULL | 0 | 0 | TRSC1502.jpg | Hutchinson, Nick | Pennington, Kirk | Rolla, Liz | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 45.06 | 32 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | 2014-041 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 4690019.26 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2016-020 | NULL | NULL | 2017-023 | 2018-03-31 | 614894.81 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
1781 | UT-ST-16-02 | Allen Creek Railroad Berm Opening | 4305000 | NULL | Railroad Berm between Depot Street and the Huron River. | NULL | NULL | 13 | Preferred alternative selected in the completed Allen Creek Railroad Berm Opening Feasibility Study. 6.5 feet reduction in flood elevation reduces risk to around 30 structures and the transportation system. Pedestrian access to the Huron River corridor. | Phase 1 - Preliminary engineering, easement acquisition, and grant applications. Phase 2 - Construction plans and installation. Coordinate with DTE/Michcon, MDOT, adjacent property owners; possible TAP funds, brownfield, FEMA funds; art | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 3 | 2015 | 2 | 2016 | 0 | 3 | 2016 | 2 | 2018 | 612650 | 1 | 2019 | 4 | 2019 | 5615420 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43045 | 0 | Fall 2016: Updated numbers re FEMA grant; art enhancemetn requested 10/2016 as coveyed June 2017. Fall 17: updated figures per cost estimates | NULL | 0 | 0 | UTST1602.jpg | Hancock, Jerry | Cooper, Eli | Nearing, Mike | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | Allen Creek Railroad Berm Opening Feasibility Study | 1 | Flood Mitigation Plan | NULL | NULL | NULL | Active | Design | 69.44 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 105795.34 | 2018-03-31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | 2 | NULL | 2 | 1 | 1 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1760 | UT-SN-16-01 | Mulholland Murray Crosslot Sanitary Mains | 500000 | NULL | 307 Mulholland crosslot to Murray | NULL | NULL | 12 | Sewer goes under house at 307 Mulholland. Evaluate re-routing of crosslot sewers. 8" sewer at 307 was damaged during foundation repair on northeast corner of the house. House at 303 also connects to this main. Cost estimate is a guess until fix is known. | Possible relocation of sewer to get out from under house. In the floodplain. High ground water. Storm main in the area. SWM recommendation for this area as well (may need to coordinate). See 2018 FTCH memo on relcoation feasibility | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 2 | 2019 | 50000 | 2 | 2019 | 2 | 2019 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43413 | 0 | Fall17: chnaged to be a design study only to determine what the feasible alternatives are.; 2018 - see FTCH memo, results show not feasible to relocate (they propose to reinforce with structural liner) | NULL | 0 | 0 | UTSN1601.jpg | Heatley, Alison | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 29.18 | 31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2231 | UT-WS-20-23 | Nixon (Huron Pkwy to S of Bluett) Phase 1 Water Improvements | 790000 | NULL | Nixon (Huron Pkwy to S of Bluett) | NULL | NULL | 14 | Upsize water main | Upsize 12" water maim to 16"; coordinate with raod and stormwater improvements | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2025 | 4 | 2025 | 790000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43417 | 0 | Added Fall 18; | NULL | 0 | 0 | UTWS2023.jpg | Baughman, Troy | Wall, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 45.32 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1927 | TR-AT-18-06 | Jones (Plymouth to Broadway) Sidewalks | 765000 | NULL | Jones (Plymouth to Broadway) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 3400 LF of sidewalks to fill existing gaps; consider one side only due to limited right of way. Difficult Rating N side - 3 (Topography, Natural Features), S side - 2 (Util. Conflict, Nat Features, ROW) | NULL | No | 0 | NULL | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 55000 | 2 | 2024 | 4 | 2024 | 710000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Hutchinson, Nick | 42656 | 0 | Fall 2016: new; general fund as placeholder. Fall 18: NC | NULL | 0 | 0 | TRAT1806.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 46.01 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
2061 | UT-WS-18-51 | Medford (Manchester to Dorchester & Needham to St. Frances) Water Main | 1100000 | NULL | Medford (Manchester to Dorchester and Needham to St. Frances) | NULL | NULL | 14 | Replace aging water main | Replace approximately 2660 LF of aging main; coordinate with resurfacing | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 112000 | 2 | 2025 | 4 | 2025 | 1488000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new. Fall 17: NC; 2018 cost updated and moved back as resurfacin not scheduled | NULL | 0 | 0 | UTWS1851.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 30.1 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1719 | MF-CB-15-06 | Housing Commission: 3565 - 3585 Oakwood Rehabilitation | 201000 | NULL | 3565 -3585 Oakwood | NULL | NULL | 1 | Rehabilitate aging facilities and improve energy efficiency | Renovate units: rubber flooring, hard-wood flooring, LED Exterior and CFL interior lights, energy star appliances and windows, energy star exhaust fan, air sealing, energy efficient furnace, low-flow fixtures, steel roof, | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 4 | 2013 | 4 | 2013 | 240000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hall, Jennifer | Gosselin, Deb | 41905 | 1 | Updated costs and indicated as to be complete in FY15 per Jen Hall at Fall 2014 CIP mtg. | NULL | 0 | 0 | MFCB1506.jpg | Hall, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1720 | MF-CB-15-05 | Housing Commission: Maple Meadows Rehabilitation | 4544000 | NULL | 800-890 S. Maple | NULL | NULL | 1 | Rehabilitate aging facilities and improve energy efficiency | Renovate units: utilize solar heat in common areas, LED Exterior and CFL interior lights, air ceiling, add insulation, energy star appliances, ecobee thermostat, solar common electric, low VOC paint | NULL | No | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 4 | NULL | 0 | NULL | 0 | 4 | 2013 | 2 | 2014 | 0 | 3 | 2014 | 4 | 2014 | 4000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hall, Jennifer | Gosselin, Deb | 41905 | 1 | Updated budget and indicated to be completed by end of FY15 | NULL | 0 | 0 | MFCB1505 | Hall, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1730 | TR-OT-15-02 | South University (E Univ. to Washtenaw) Streetscape | 1500000 | NULL | South University from East University to Washtenaw | NULL | NULL | 9 | Enhance streetscape and create more walking space | Remove tree planters to gain back more active sidewalk space; create new under- walk planters and replace trees. free up valuable sidewalk space for pedestrians and cafes; address paver drainage problems | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 2 | 2016 | 175000 | 3 | 2016 | 2 | 2017 | 1787900 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 43038 | 1 | Fall 2015: Moved design to FY16 and construction to FY17. Had all been in FY18; Fall 17 marked as TBC and updated numbers per AM | NULL | 0 | 0 | TROT1502.jpg | Pollay, Susan | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1741 | MF-CB-15-09 | Housing Commission: Baker Commons | 4195000 | NULL | 106 Packard | NULL | NULL | 1 | Rehabilitate aging facilities | Rehabilitate aging 64 unit facility: LED exterior and CFL interior lights , ecobee thermostats, energy star windows, low-VOC paint | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2014 | 4 | 2014 | 5000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hall, Jennifer | Gosselin, Deb | 41874 | 1 | Updated cost and indicated as to be complete by end of FY15 | NULL | 0 | 0 | MFCB1509.jpg | Hall, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1732 | TR-PF-15-01 | 4th and William Parking Structure Stairs, Elevators,and Lobby | 2500000 | NULL | Fourth and William Parking Structure | NULL | NULL | 10 | Upgrade stairwell and elevator and gain lobby area; also upgrade equipment | Add new stairwell at SW corner and demolish existing; add new elevator; replace existing; upgrade parking equipment; expand lobby; investigate vehicle charging station | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 4 | 2017 | 4372430 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 42262 | 1 | Fall 2015: Used dollar from DDA chart; elevators probably moved to Elevator category | NULL | 0 | 0 | TRPF1501.jpg | Pollay, Susan | Morehouse, Joe | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1734 | TR-PF-15-02 | Vehicle Charging Stations | 100000 | NULL | Parking structures in DDA | NULL | NULL | 10 | Growing demand for vehicle charging stations | NULL | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2013 | 2 | 2019 | 146200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 42989 | 0 | Fall 2016: left in but charging stations are being revisited for better management of user stream. Fall 2017: zeroes out FY18. Fall18: added $ per DDA | NULL | 0 | 0 | TRPF1502.jpg | Pollay, Susan | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1742 | MF-CB-15-10 | Housing Commission: Hikone | 1367000 | NULL | 2702-2760 Hikone | NULL | NULL | 1 | Rehabilitation of aging facilities | Rehabilitate 29 unit building; on-demand water, Energy star exhaust & appliances, high efficiency furnaces, LED exterior and CFL interior lights, solar common, air sealing, add insulation, low-VOC paint | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2014 | 4 | 2014 | 4000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hall, Jennifer | Gosselin, Deb | 41905 | 1 | Updated cost and indicated as to be complete by end of FY15 | NULL | 0 | 0 | MFCB1510.jpg | Hall, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1721 | MF-CB-15-07 | Housing Commission: Miller Manor | 4800000 | NULL | 727 Miller | NULL | NULL | 1 | Rehabilitate aging units and add 3 new ADA units | Renovate units; add 3 ADA units, LED exterior and CFL interior lights, ecobee thermostats, solar hot water and common electric, energy star windows, Low VOC paint | NULL | No | 0 | 0 | 7 | NULL | NULL | 0 | 0 | NULL | 3 | NULL | 2 | NULL | 0 | 4 | 2013 | 2 | 2014 | 0 | 3 | 2014 | 4 | 2014 | 12000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hall, Jennifer | Gosselin, Deb | 41905 | 1 | Updated cost and indicated as to be complete by end of FY15 | NULL | 0 | 0 | MFCB1507.jpg | Hall, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2047 | UT-WS-18-42 | State St (Eisenhower to UM Tennis Ct Entrance) Raw Water Main 30" Upgrade | 2863800 | NULL | State St (Eisenhower to UM Tennis Ct Entrance) | NULL | NULL | 14 | Replace aging raw water main | Replace and upsize approximately 3330 LF aging raw water main; coordinate with road treatment; may modify limits based on cost | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2025 | 200000 | 2 | 2026 | 4 | 2026 | 2663800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43437 | 0 | Fall 2016: new split form bigger project. Assume $860 per LF based on info from MN for Stadium. Fall 17: NC Fall 18: NC | NULL | 0 | 0 | UTWS1842.jpg | Sanford, Larry | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.26 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2179 | TR-AT-20-06 | Downtown/Near Downtown Bikeway Connections | 2000000 | NULL | Downtown/Near Downtown | NULL | NULL | 6 | Provide critical neighborhood connections to the First and William Street Bikeway, increasing safety and access between downtown and residential neighborhoods | Utilize the 2019 Transportation Master Plan findings and partner with street resurfacing and other capital projects to provide connections in a meaningful and cost-effective way. | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 1 | 2021 | 600000 | 2 | 2021 | 4 | 2021 | 1400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43425 | 0 | Fall 18: new | NULL | 0 | 0 | TRAT2006.jpg | Miller, Amber | Hess, Raymond | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.25 | 24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2093 | UT-SN-19-01 | Huron/West Park Sanitary SSWWEP Improvements (DOM) | 5000000 | NULL | Huron West Park Sanitary Trunkline from Arbana to Dexter Ave (just west of Lyn Anne Ct) | NULL | NULL | 12 | Implement recommendations of SSIPE Area A preliminary design efforts; See OHM SSIPE Report for addressing wet weather sanitary sewer capacity constraints (and lack of maintenance access) | Upsize 12"/18" to 21" from Arbana to Dexter Ave (just west of Lyn Anne Ct); 4250 LF; Research existing easements | NULL | No | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 2 | 2019 | 350000 | 3 | 2019 | 4 | 2020 | 4650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Baughman, Troy | 43390 | 0 | Fall 17: created as first SWWP project to advance using DOM funds; 2018 cost confirmed | NULL | 0 | 0 | UTSN1901.jpg | Slizewski, Brian | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 59.17 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1817 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1846 | UT-SN-16-15 | WWTP: Asset Management Plan | 400000 | NULL | WWTP | NULL | NULL | 12 | required by NPDES permit | Asset Management of all facilities and systems at the WWTP. | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 3 | 2019 | 4 | 2020 | 400000 | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 4 | 2016 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Lawson, Jennifer | 41926 | 0 | Fall 18: timing per WWTP | NULL | 0 | 0 | UTSN1615.jpg | Sanders, Keith | Lawson, Jennifer | Kenzie, Earl | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | MDEQ Discharge Permit | 1 | Capacity Analysis | Condition Analysis | Customer Level of Service | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 46.22 | 10 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2063 | UT-WS-18-53 | Barton (Northside to Pontiac Trail) Water Main Replacement | 400000 | NULL | Barton (Northside to Pontiac Trail) | NULL | NULL | 14 | Replace undersized domestic water main | Replace undersized domestic water main; coordinate with road resurfacing project TR-SC-18-03 | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 0 | 2 | 2020 | 4 | 2020 | 700000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Baughman, Troy | 43388 | 0 | Fall 2106: new; 2018 cost updated | NULL | 0 | 0 | UTWS1853.jpg | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 25.15 | 71 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 14436.43 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2050 | TR-PF-18-02 | First and Washington Parking Structure Capital Maintenance | 1616450 | NULL | First and Washington | NULL | NULL | 10 | Capital maintenance | Deck coating; joint and cove sealants; concrete repairs; miscellaneous repairs | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 2 | 2023 | 1732181 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43433 | 0 | Fall 2017: updated dollars. Fall 18 per DDA | NULL | 0 | 0 | TRPF1802.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1928 | TR-AT-18-07 | Independence (Victoria to E. of Powell) Sidewalks | 495000 | NULL | Independence (Victoria to E. of Powell) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 2200 LF of sidewalks to fill existing gaps; consider one side only initially. Difficulty Rating - S side - 1 (Natural Features), N side - mostly 3 (Topography, Natural Features) plus ex retaining walls and landscaping | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 35000 | 2 | 2025 | 4 | 2025 | 460000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2106: new: showed general fund as placeholder. Fall 18 to FY25 | NULL | 0 | 0 | TRAT1807.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 41.41 | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
2046 | UT-WS-18-41 | State St (I-94 to Eisenhower) Raw Water Main 30" Upgrade | 2175800 | NULL | State St (!-94 to Eisenhower) | NULL | NULL | 14 | Replace aging raw water | Replace and upsize approximately 2530 LF of aging raw water main; coordinate with road reconstruction | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2026 | 4 | 2026 | 150000 | 2 | 2027 | 4 | 2027 | 2025800 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 42662 | 0 | Fall 2016: split from larger project. Assume $860 per LF based on info from MN for Stadium. Fall 17: NC. Fall 18 to FY28 to match road | NULL | 0 | 0 | UTWS1841.jpg | Baughman, Troy | Sanford, Larry | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.26 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1823 | UT-SN-16-08 | Barton Dr (east of M-14 ramp) Sanitary Sewer Extension | 300000 | NULL | Barton Dr. just east of M-14 ramp | NULL | NULL | 12 | Extend sanitary sewer to service three parcels (about 400'). | Extend approx. 320 LF of sanitary to service 135, 151, 169 Barton Drive; grinder pumps likely; close physical proximity of water mains; confirm three addresses. Investigate ROW. Traffic control. Ground water. Coordinate with road paving. | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 0 | 2 | 2022 | 4 | 2022 | 450000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Baughman, Troy | 43390 | 0 | Fall 2016: align with road work. Fall 17: NC; 2018 cost updated. 90day notices will need to be sent once sewer is installed. | NULL | 0 | 0 | UTSN1608.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 38.69 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 9343.47 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1793 | UT-SN-16-04 | High Level/1st Street Sanitary: SSWWEP Project Area B | 100000 | NULL | 1st Street area : SSWWEP Project Area B | NULL | NULL | 12 | Identified by SSWWEP as an area where model shows pipe capacity issues | Preliminary engineering phase with televising, hydrant testing, and other analysis; specific improvements to be designed as warranted based on preliminary engineering; previous UT-SN-08-12 replaced with this project; | NULL | NULL | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 3 | 2015 | 2 | 2016 | 0 | 1 | 2016 | 1 | 2017 | 110500 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 42331 | 1 | Fall 2015: increased to $110,500 per bid | NULL | 0 | 0 | UTSN1604.jpg | Hutchinson, Nick | Slotten, Cress | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | SSWWEP CAC | 1 | Capacity Analysis | NULL | NULL | Sanitary Sewer Wet Weather Evaluation Program Report | 0 | NULL | NULL | NULL | NULL | Active | Design | 62.38 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 120368.39 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1794 | UT-SN-16-05 | High Level/State & Hoover: SSWWEP Project Area C | 100000 | NULL | Sanitary sewers in vicinity of Hoover and State: SSWWEP Project Area C | NULL | NULL | 12 | Identified by SSWWEP as an area where model shows pipe capacity issues | Preliminary engineering phase with televising, hydrant testing, and other analysis; specific improvements to be deigned as warranted based on preliminary engineering; previous UT-SN-08-12 replaced with this project; improvements to be pt. of UT-SN-02-11 | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 2 | 2016 | 95000 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 42331 | 1 | Fall 2015: decreased budget $5000 | NULL | 0 | 0 | UTSN1605.jpg | Hutchinson, Nick | Slotten, Cress | Baughman, Troy | NULL | NULL | 1 | NULL | NULL | NULL | SSWWEP CAC | 1 | Capacity Analysis | NULL | NULL | Sanitary Sewer Wet Weather Evaluation Program report | 0 | NULL | NULL | NULL | NULL | Active | Design | 65.28 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 102507 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2049 | UT-WS-18-44 | UM Golf Course (State to Stadium) Raw Water Main 30" Upgrade | 946000 | NULL | UM Golf Course from east end of Stadium Bridge to railroad right of way at State | NULL | NULL | 14 | Replace and upsize aging raw water main | Replace approximately 1100 LF of raw water main and upsize; requires close coordination with UM | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2026 | 4 | 2026 | 65000 | 2 | 2027 | 4 | 2027 | 881000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43437 | 0 | Fall 2016: split from larger project. Assume $860 per LF based on info from MN for Stadium. Fall 17: NC Fall 18 to 28 | NULL | 0 | 0 | UTWS1844.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.26 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1750 | TR-BR-16-01 | Island Drive Bridge Rehabilitation | 300000 | NULL | Island Drive Bridge over Traver Creek | NULL | NULL | 7 | Address capital maintenance issues as identified in bridge inspection report | Install new 6" concrete deck; place rip-rap upstream and downstream as scour counter measure; approach work; add sidewalk on north side of Island Drive from apartments to Island Park shelter; seek funding; MDEQ; WCWRC | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 45000 | 2 | 2021 | 4 | 2021 | 468000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 43039 | 0 | Fall 2015: moved to FY19; will package with painting of Fuller and Maiden Lane and Rehab. Of EMC Drive bridges. Fall 2016: moved to 2021. Fall 17; moved to 21. Fall 18: NC | NULL | 0 | 0 | TRBR1601.jpg | Nearing, Mike | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 47.94 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2035 | UT-SN-18-S2 | Northside Interceptor Condition Assessment | 280000 | NULL | Northside Interceptor | NULL | NULL | 12 | Assess condition of aging trunkline located in difficult terrain | Assess condition using innovative inspection techniques; challenging access | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 3 | 2017 | 2 | 2018 | 0 | 3 | 2017 | 4 | 2017 | 30000 | 2 | 2018 | 2 | 2018 | 250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Elenbaas, Chris | 42716 | 1 | Fall 2016: new | NULL | 0 | 0 | UTSN18S2.jpg | Hupy, Craig | Slotten, Cress | Elenbaas, Chris | Baughman, Troy | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 22.94 | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1753 | TR-AT-16-02 | Wheeler Center Area Sidewalks | 1747500 | NULL | Ellsworth and Stone School in area around Wheeler Service Center | NULL | NULL | 6 | Add sidewalks and safety paths along Ellsworth and Stone School Rd to meet intent of Wheeler Center site plan approval | Sidewalks along Ellsworth in front of Wheeler Center and landfill; safety path on Stone School along Wheeler Center. Investigate potential environmental issues with development near landfill. | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 175000 | 0 | NULL | 0 | NULL | 1572500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 41957 | 1 | NULL | NULL | 0 | 0 | TRAT1602.jpg | Hupy, Craig | Slotten, Cress | Dykman, Dave | Coleman, Kayla | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | WSC Site Plan Approval Condition | 1 | Ann Arbor Non-Motorized Plan | NULL | NULL | NULL | Active | Construction | 57.93 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | 2015 | 2 | 2016 | 1370405 | NULL | NULL | 2016-06-20 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1729748.8 | 2019-06-30 | NULL | 138949.04 | 73821.1 | 1346960.07 | 8647.65 | 3829.01 | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2051 | UT-WS-18-45 | Arlington (Geddes to Heatherway) Water Main Improvements | 1100000 | NULL | Arlington (Geddes to southern intersection with Heatherway) | NULL | NULL | 14 | Complete water loop and replace and upsize aging main | Install main from stub at Geddes to present termination; replace existing main from Geddes to southern intersection with Heatherway; this segment to receive thin mill and fill road treatment in FY17 and then be slated with this water project for later res | NULL | Yes | 1 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 120000 | 2 | 2024 | 4 | 2025 | 1580000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2106: new. Fall 18 costs updated | NULL | 0 | 0 | UTWS1845.jpg | Baughman, Troy | Elenbaas, Chris | Dykman, Dave | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Condition Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 25.15 | 71 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1907 | UT-WS-18-07 | South University (E Univ. to Washtenaw) Water Main Replacement | 200000 | NULL | S Univ. (E Univ. to Washtenaw) | NULL | NULL | 14 | Eliminate pipe redundancy and transfer service leads | Coordinate with DDA streetscape project and with development activity; transfer leads from 6" to 12" main | NULL | Yes | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2017 | 2 | 2017 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43046 | 1 | Fall 2016: new. Fall 17: completed; need to complete close-out costs so marked TBC | NULL | 0 | 0 | UTWS1807.jpg | Baughman, Troy | Elenbaas, Chris | Dykman, Dave | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 12 | 88 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1754 | TR-AT-16-03 | Federal Blvd (Stadium west through 2030 Commerce) Sidewalks | 202500 | NULL | Federal Blvd (Stadium west through 2030 Commerce) on north side | NULL | NULL | 6 | Sidewalk gap elimination requested through Commission on Disability Issues. | Request to fill sidewalk gap on north side of Federal-Commerce Blvd, from Stadium Blvd. west approximately 900'; ADA ramps. Potential conflict with parking lot encroaching ROW. Possible special assessment, but most frontage is USPS | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 3 | NULL | 3 | NULL | 0 | 3 | 2018 | 4 | 2018 | 12000 | 2 | 2019 | 3 | 2019 | 190500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 42689 | 1 | Fall 2016: revised schedule to do sooner based on STP funds; Nick's cost figure; Deb edited schedule and revenue sources | NULL | 0 | 0 | TRAT1603.jpg | Slizewski, Brian | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 41.01 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 526594.9 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1758 | UT-WS-16-02 | Heatherway (Arlington to Geddes) Water Main Replacement | 350000 | NULL | Heatherway Water Main (Arlington/Devonshire to Geddes) | NULL | NULL | 14 | Water quality issues | Investigate additional connections. Cost estimate is based on being done with road project. Install approx. 1175 LF of main | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 55000 | 2 | 2024 | 4 | 2024 | 745000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: left in 21 but dependent on road being paved; 2018 cost updated | NULL | 0 | 0 | UTWS1602.jpg | Sanford, Larry | Baughman, Troy | Wooden, Dan | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 22.18 | 75 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1755 | TR-AT-19-01 | Seventh Street Transportation (Scio Church to Huron) | 200000 | NULL | 7th Street from Scio Church to Huron | NULL | NULL | 6 | Citizen request to address pedestrian needs along Seventh Street | Traffic speed issues; need for add. pedestrian crossing & improved bike lanes identiified in 7th Str. Transportation eval. efforts; ped. crossings installed N of Jefferson and at Lutz in 2015: safety funds obtained for protected bike lanes in FY18 | NULL | No | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2018 | 2 | 2018 | 640000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 42983 | 1 | Long-term, interest in crosswalk at Jefferson subject to grade change (NIS); changed to AT per Trans. Comm.; additional study in spring 2017; Fall 2017: changed limits to Scio Church to Huron and add a CPM treatmetn from Scio Church to 7th | NULL | 0 | 0 | TROT1601.jpg | Coleman, Kayla | Pulcipher, Connie | Cooper, Eli | Redininger, Cynthia | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Planning | 29.84 | 10 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 702927.65 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1759 | UT-ST-16-01 | Fifth Ave (Kingsley to Catherine) Stormwater Improvements (AC) | 450000 | NULL | Fifth Ave (Kingsley to Catherine) and Detroit (Fifth to Kingsley) | NULL | NULL | 13 | Address stormwater issues as part of Complete Streets and Green Streets policy in conjunction with proposed road reconstruction | Address stormwater issues as part of Complete Streets and Green Streets policy in conjunction with proposed road reconstruction; also including Detroit from Fifth to Kigsley; partially in Allen Creek Watershed | NULL | Yes | 0 | 0 | 6 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2017 | 3 | 2017 | 102600 | 2 | 2018 | 4 | 2018 | 688000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43025 | 1 | Used 4th Avenue infiltration treatment as cost guideline. $450,000 est. on 8/8/16. Fall 2016: spread costs. Fall 17: latest estimate is $790.600 to be spent in FY18/FY19. Drawing from Allen Creek funds for FY19 component | NULL | 0 | 0 | UTST1601.jpg | Nelson, Jenn | Lawson, Jennifer | Hutchinson, Nick | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 41.09 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 698336 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2097 | UT-ST-19-02 | Hoover and Greene St Stormwater Improvements (AC)
Allen Creek Watershed: Hoover and Greene St Stormwater Improvements | 700000 | NULL | Hoover (Main to State) and Greene (Kipke to Hill) | NULL | NULL | 13 | Create additional storrmwater storage within the total Allen Creek ("AC") watershed on an incremental basis over time for the benefit of the Lower Allen Creek portion of that watershed as recommendended in the SWMM study | Coordiinate with associated streets projects (TR-SC-16-07 and TR-SC-13-07); utlize available funds to create additional stormwater storage | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 38000 | 2 | 2018 | 4 | 2018 | 662000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43025 | 1 | Fall 17: added; funded from Lower Allen Creek stormwater funds which were allocated to this | NULL | 0 | 0 | UTST1902.jpg | Dykman, Dave | Baughman, Troy | Lawson, Jennifer | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | Programmed | Design | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2056 | MF-PR-18-01 | Gallup Pond Dredging | 150000 | NULL | Gallup Pond | NULL | NULL | 3 | Dredge pond to restore capacity | Dredge Gallup Pond | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 2 | 2022 | 150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | Fall 18: moved to FY22 | NULL | 0 | 0 | MFPR1801.jpg | Smith, Colin | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 28.07 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1762 | TR-SC-16-02 | W Huron Alley Repair and Improvements | 300000 | NULL | Alley behind 420 W Huron | NULL | NULL | 11 | Repair alley and address storm water and lighting issues. | Consider one-way on Huron St entrance. Assess flood status. Consider lighting. Consider loading access for 410 W Huron. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 43038 | 0 | Fall 17: NC | NULL | 0 | 0 | TRSC1602.jpg | Pollay, Susan | Pennington, Kirk | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.5 | 31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1766 | TR-SC-16-06 | Hill St (Fifth to State)
to State) | 392000 | NULL | Hill St (Main to State) | NULL | NULL | 11 | Resurface street | Add minor mid-block crossing between Main and Fifth Ave. Investigate storm water improvements. Check against wet weather study for sanitary/storm issues. Coordinate with University and WCWRC. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 2 | 2016 | 121000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43017 | 1 | Fall 2015: Moved FY18 to FY16 to do a CPM treatment; Fall 17: marked TBC but need to add a resurfacing project when water is done. | NULL | 0 | 0 | TRSC1606.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 33.71 | 35 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1767 | TR-SC-16-07 | Hoover (Main to State) and Greene Resurfacing | 700000 | NULL | Hoover (Main to State) and Greene (Hill to Keech) | NULL | NULL | 11 | Address street condition | Add minor mid-block crossing between Main and Division. Investigate storm water improvements. Check against wet weather study for sanitary/storm issues. Coordinate with University and WCWRC. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2018 | 100000 | 2 | 2019 | 3 | 2019 | 850000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Hutchinson, Nick | 43411 | 0 | Updated schedule/funding.. Fall 17: advanced 100k design money to FY18; Costs updated to include Greene St. Resurfacing (nsh) | NULL | 0 | 0 | TRSC1607.jpg | Cooper, Eli | Lawson, Jennifer | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 50.55 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1769 | TR-SC-16-09 | Boardwalk (Eisenhower north to end) Resurfacing
ASRP - Boardwalk (Eisenhower to end) | 756000 | NULL | Boardwalk St (E Eisenhower Pkwy northerly to dead end) | NULL | NULL | 11 | Street condition | Bike lane Eisenhower to Oakbrook. Sidewalk gaps | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 1 | 2019 | 0 | 2 | 2020 | 4 | 2020 | 765000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43411 | 0 | Moved from FY18 to FY19; updated schedule/funding. Fall 17: NC | NULL | 0 | 0 | TRSC1609.jpg | Cooper, Eli | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 41.98 | 35 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 2 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1770 | TR-SC-16-10 | Broadway (Plymouth to Plymouth) Resurfacing | 1300000 | NULL | Broadway (Plymouth to Plymouth) | NULL | NULL | 11 | Street condition. | Potential for sidewalk addition. Review pressure boundary and water quality issues. Review speed humps - Fire Dept. may want to convert them to speed tables. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 2 | 2020 | 0 | 3 | 2021 | 4 | 2021 | 1560000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43412 | 0 | Updated schedule/funding. Fall17: NC Fall 18: moved back to match water | NULL | 0 | 0 | TRSC1610.jpg | Baughman, Troy | Cooper, Eli | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.57 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1771 | TR-SC-16-11 | Main St (Huron to William) Resurfacing | 429000 | NULL | Main (Huron to William) | NULL | NULL | 11 | Street condition. | Consider Downtown Streetscape Framework Plan. Coordinate with special events. Water valve replacements. Sidewalk vaults. Potential for infiltration. All crock inlets. Coordinate with Violin Monster. Coordinate with Kerry Gray - Dean Promenade. See below | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 1 | 2020 | 30000 | 2 | 2020 | 4 | 2020 | 445000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Updated schedule/funding. Some buildings are served out back to private san in alley. Do we stub out leads from Main St for service? Fall 17: NC | NULL | 0 | 0 | TRSC1611.jpg | Lawson, Jennifer | Miller, Amber | Pulcipher, Connie | Baughman, Troy | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.57 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1773 | TR-SC-16-13 | Division Ave (Hoover to Madison) CPM
Division (Hoover to Madison)
Division (Hoover to Madison) | 1100000 | NULL | Division (Hoover to Madison) | NULL | NULL | 11 | Street condition. | Bike lane - one side.. Per UM (P Spence) coordinate/include repair of FO conduit on the SE quad of the Hiil St intersection with their ITS group (Contact - Lewis Hehnlin; lhehnlin@umich.edu). CPM treatment | NULL | Yes | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 1 | 2020 | 0 | 2 | 2019 | 2 | 2019 | 185000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43277 | 0 | NC; Need to reconfig the 12" sanitary connection at the Division/Hill intersection (12" connects to 30" at flow line causing backup to 12"). Discuss if consolidating parallel san mains in this area is desirable/feasible Fall 18 changed to CPM | NULL | 0 | 0 | TRSC1613.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.52 | 21 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | 3 | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1774 | TR-SC-16-14 | Pontiac, Moore, Swift Area Resurfacing | 425000 | NULL | Moore (Broadway to Pontiac), Pontiac (Moore to Swift), and Swift (Broadway to north of bend) and Wright (N of Kellogg) | NULL | NULL | 11 | Street condition. | Bike lane addition. Investigate improvements Pontiac/Swift/Moore configuration. Consider adding on street parking and road diet for Pontiac (Moore to Swift). Potential water service improvements. Investigate abandoning water services on 6" main on Moore. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 1 | 2022 | 0 | 2 | 2023 | 4 | 2023 | 570000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Moved from FY18 to FY21; updated schedule/funding. Fall17: NC | NULL | 0 | 0 | TRSC1614.jpg | Baughman, Troy | Cooper, Eli | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 51.87 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1775 | TR-SC-16-15 | Traverwood (Plymouth to Huron Pkwy) Resurfacing
ASRP - Traverwood (Plymouth to Huron Pkwy) | 740000 | NULL | Traverwood (Plymouth to Huron Pkwy) | NULL | NULL | 11 | Street condition. | On street parking at the library. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 1 | 2019 | 50000 | 2 | 2019 | 2 | 2019 | 760000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Moved from FY18 to FY19; updated schedule/funding. Fall 17: NC exc. Use Cty millage | NULL | 0 | 0 | TRSC1615.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 40.66 | 37 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1776 | TR-SC-16-16 | Ann (First St to Fifth Ave) Resurfacing | 167000 | NULL | Ann St (First to Fifth Ave) | NULL | NULL | 11 | Street condition. | Bike facilities. Coordinate with Street Design Team and DDA. Improvements at parking area for Main St Party Store. Possible brick or concrete base. Opportunities for storm water improvements. Water main project; coord with parking structure project | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 1 | 2021 | 0 | 2 | 2021 | 4 | 2021 | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43410 | 0 | Moved from FY20 to FY21; updated funding/schedule. Fall 17: NC; Moved to calendar year 2023 (nsh) NEED TO UPDATE COST TO REFLECT CHANGED LIMITS | NULL | 0 | 0 | TRSC1616.jpg | Hutchinson, Nick | Cooper, Eli | Baughman, Troy | Miller, Amber | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 55.38 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1783 | UT-ST-16-04 | Millers Creek Channel Modification - Reach 5 | 650000 | NULL | Glazier Way to Lake Haven Drive, Oakridge Park | NULL | NULL | 13 | Sediment load reduction project identified in the Management of Millers Creek Sediment Accumulation Study (December 2013). | Must be county drain first; USACOE joint permit; potential location for sediment traps | NULL | No | 0 | 0 | 7 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 45000 | 2 | 2024 | 4 | 2024 | 605000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hancock, Jerry | Gosselin, Deb | 43423 | 0 | Fall 2016: removed SRF; moved back. Fall 17: NC Fall 18; booked in a single year | NULL | 0 | 0 | UTST1604.jpg | Hancock, Jerry | Borneman, Dave | Ernst, Kevin | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | Millers Creek Sediment Accumulation Study (December 2013) | 1 | Huron River 2010 SRF Project Plan | NULL | NULL | NULL | Programmed | Inactive | 29.29 | 34 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1923 | TR-AT-18-02 | Dexter (Maple to Rosewood/Ironwood) Sidewalks | 1575000 | NULL | Dexter (Maple to Rosewood/Ironwood) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 7000 LF of sidewalks to fill existing gaps; consider breaking into two projects for fiscal reasons. Difficulty Rating: 1-3 (Topography, Natural Features, Drainage) | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 90000 | 2 | 2025 | 4 | 2025 | 1485000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 42697 | 0 | Fall 2016: New; Deb spread Nick's number from Oct. | NULL | 0 | 0 | TRAT1802.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.65 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1782 | UT-ST-16-03 | Millers Creek Channel Modification - Reach D (Pepper Pike) | 1362000 | NULL | Glazier Hill Park - Pepper Pike to Glazier Way | NULL | NULL | 13 | Top priority sediment load reduction project identified in the Management of Millers Creek Sediment Accumulation Study (December 2013). | Must be county drain first; access easement; natural features affected; USACE joint permit; investigate extending limits south of Glazier Way | NULL | No | 0 | 0 | 7 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2017 | 2 | 2019 | 120000 | 3 | 2019 | 4 | 2019 | 1380000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hancock, Jerry | Gosselin, Deb | 43013 | 0 | Increased funding 10.20.14 to roll in cost of eliminated Miller Creek Drainage District creation (UT-ST-08-05) project. Fall 2016: removed from SRF and spread costs; Fall 17: back in SRF and in capital budget fro FY18 | NULL | 0 | 0 | UTST1603.jpg | Hancock, Jerry | Gray, Kerry | Borneman, Dave | Ernst, Kevin | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | Millers Creek Sediment Accumulation Study (December 2013) | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.1 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1780 | MF-PR-16-03 | Dog Park | 75000 | NULL | To be determined | NULL | NULL | 3 | Centrally located site to complement existing sites. | Master plan report with public outreach and citizen engagement to determine feasible sites. | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | NULL | 2014 | 0 | NULL | 0 | 3 | 2016 | 4 | 2016 | 0 | 1 | 2017 | 2 | 2017 | 75000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Gosselin, Deb | 41946 | 1 | Fall 2105: Moved from FY16 to FY17 | NULL | 0 | 0 | MFPR1603.jpg | Kuras, Amy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Parks & Recreation Open Space (PROS) Plan | NULL | NULL | NULL | Programmed | Planning | 39.12 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1819 | UT-WS-16-24 | Traver Rd (Barton to S of Moore) Watermain Upsizing | 2200000 | NULL | Traver Rd Watermain (Barton to S of Moore) | NULL | NULL | 14 | Water quality. Upsizing of main. | RR Crossing. High groundwater. Water quality issues at 1503 Traver. Cost estimate assumed it will not be done as part of road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 200000 | 2 | 2024 | 4 | 2024 | 2500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: spread to FY22/23; road is in. Fall 17: NC; 2018 cost updated and moved out | NULL | 0 | 0 | UTWS1624.jpg | Baughman, Troy | Sanford, Larry | Lawson, Jennifer | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Condition Analysis | Capacity Analysis | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 51.28 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2039 | UT-WS-18-39 | Lutz/Eberwhite/Elder/Crest Raw Water Main 30" Upgrade | 1806000 | NULL | Lutz (7th to Eberwhite); Eberwhite (Lutz to Elder); Elder (Eberwhite to Crest); Crest (Eberwhite to Liberty) | NULL | NULL | 14 | Replace and upsize aging raw water main | Replace approximately 2100 LF of raw water main; upsize to 30"; coordinate with road resurfacing as possible Replace and upsize aging raw water main | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 125000 | 2 | 2024 | 4 | 2024 | 1681000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new split from bigger project. Assume $860 per LF based on info from MN for Stadium; Fall 18; NC | NULL | 0 | 0 | UTWS1839.jpg | Baughman, Troy | Sanford, Larry | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.26 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1894 | TR-SC-17-02 | State & Ellsworth Roundabout Improvements | 180000 | NULL | State & Ellsworth | NULL | NULL | 11 | Make improvements to functionality and safety of existing roundabout | Joint project with Washtenaw County; examine and upgrade signage and pavement markings; possible additional physical improvements | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 1 | 2015 | 30000 | 3 | 2016 | 4 | 2016 | 150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43017 | 1 | Fall 2105: added to CIP, Fall 17: marked TBC | NULL | 0 | 0 | TRSC1702.jpg | Hutchinson, Nick | Dykman, Dave | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1784 | UT-ST-16-05 | Huron Hills Golf Course Stormwater Improvements | 1220000 | NULL | Huron Hills Golf Course | NULL | NULL | 13 | Stabilize eroding streambanks and manage stormwater on Back 9 | Coordinate with golf; in 2013 SRF Plan; need inland lakes & streams permit (USACE joint permit); drainage district TBD; daylight drainage from Hunting Valley subs; Evaluate sanitary | NULL | No | 0 | 0 | 7 | NULL | NULL | 1 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 85000 | 2 | 2021 | 4 | 2021 | 1135000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43423 | 0 | Fall 2016: pushed out. Fall 17: NC Fall 18; Moved to Fy21-22 | NULL | 0 | 0 | UTST1605.jpg | Lawson, Jennifer | Spooner, Scott | Sheehan, Harry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Huron River 2013 SRF Project Plan | NULL | NULL | NULL | Programmed | Inactive | 49.84 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1785 | UT-ST-16-06 | Stormwater Asset Management Plan | 900000 | NULL | City wide | NULL | NULL | 13 | Long range planning of stormwater system needs; | Capture physical condition of stormwater system elements as needed component of long term asset management system; Include manhole condition assessment; Include updating all photos for manhole inspection | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 3 | 2015 | 4 | 2017 | 600000 | 3 | 2015 | 2 | 2017 | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43045 | 1 | FY 2015: Spread budget over three years to reflect Council approved budget of Spring 2015 (DG) Fall 2016: NC Fall 17: NC | NULL | 0 | 0 | UTST1606.jpg | Woodward, Nichole | Baughman, Troy | Ernst, Kevin | Hancock, Jerry | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Condition Analysis | Customer Level of Service | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 46.39 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2087 | TR-AT-19-02 | William (Third to State) Protected Bike Lane | 2000000 | NULL | William (Third to State) | NULL | NULL | 6 | Fulfill Non-motorized Plan identifed need to add bike lanes as a bicycle key entry point into the DDA | DDA project; Protected bike lane on William from Third to State; coordinated with protected bike lane on First St | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2018 | 4 | 2018 | 200000 | 2 | 2019 | 4 | 2019 | 1800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 42996 | 0 | Added Fall 17 by DDA. Fall 18: showed DDA street contribution with our street project so backed out. | NULL | 0 | 0 | TRAT1902.jpg | Miller, Amber | Liu, Luke | Cooper, Eli | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Customer Level of Service | NULL | NULL | NULL | 0 | Ann Arbor Non-Motorized Plan | NULL | NULL | NULL | Programmed | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1787 | UT-ST-16-08 | Churchill Park/Eisenhower ROW Basin | 2100000 | NULL | Churchill Park/Eisenhower ROW | NULL | NULL | 13 | Flood mitigation; water quality improvements | Coordinate with Parks & Rec, WCWRC, MDOT; natural features impacts; noise mitigation; add 2nd basin at Oak Valley | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 2 | 2019 | 350000 | 3 | 2018 | 4 | 2018 | 2850000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43423 | 0 | Fall 2015: Discussed swap with Malletts Creek Stream. Stab.; HS indicated neighborhood told it would be FY2017; swapped; Fall 2016: left SRF and in FY8. Fall 17: moved const. to FY19 as project design is being rescoped; upped $ per J Fall 18: NC | NULL | 0 | 0 | UTST1608.jpg | Sheehan, Harry | Lawson, Jennifer | Gray, Kerry | Hanzel, Hillary | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | Upper Malletts Stormwater Conveyance Study | 0 | NULL | NULL | NULL | NULL | Active | Design | 48.41 | 10 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1790 | UT-ST-16-11 | Sister Lakes Stormwater Improvements | 250000 | NULL | Sister Lakes in Dolph Park | NULL | NULL | 13 | Water quality improvements | Evaluate treatment options and construct improvements to address water quality as affected by City stormwater outfalls with focus on high scour area at Lakewood; Parks; USACOE joint permit; seasonal impact of bird migration; assess for T&E species; | NULL | No | 0 | 0 | 7 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2015 | 2 | 2016 | 30000 | 2 | 2018 | 2 | 2018 | 220000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Slizewski, Brian | 42681 | 1 | Fall 2016: pushed construction back to FY19 due to study questions | NULL | 0 | 0 | UTST1611.jpg | Lawson, Jennifer | Smith, Colin | Sheehan, Harry | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | LimnoTech 1997 Report/Strassberg 2014 Report | 0 | NULL | NULL | NULL | NULL | Active | Design | 40.48 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | 592 | NULL | 43511 | NULL | 367897 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 335947 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1807 | UT-WS-16-12 | Monroe (State and Packard Area) Water Main Upsizing | 160000 | NULL | Monroe between Packard and State Street | NULL | NULL | 14 | Replace 6" pieces of main with 12" main. A portion of this stretch was upsized as part of the UM S. Quad renovations project in 2014. | Upsize approximately 420 LF of 6" main to 12" main. Cost estimate assumes this water main upsizing would occur as part of a road project | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 45000 | 2 | 2021 | 4 | 2021 | 555000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2106: left in FY21; costs not updated or spread and may or may not go with road, Fall 17: NC; 2018 cost updated and pushed out as no rd. work planned | NULL | 0 | 0 | UTWS1612.jpg | Heatley, Alison | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.31 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1812 | UT-WS-16-17 | WTP: Plant 1 Replacement Project | 33000000 | NULL | Water Treatment Plant - 919 Sunset Rd. | NULL | NULL | 14 | Implement recommendations from WTP Alternatives Analysis Project. Replace 1938 treatment basins that are in disrepair and not meeting current performance standards for water treatment flocculation and settling basins. | Replacing 1938 treatment basins with more efficient technology that meets Ten States Standards for Water Treatment. Ten States Standards are water treatment performance standards adopted by the State of Michigan. Public art enhanced. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 1 | NULL | 1 | 2018 | 3 | 2020 | 125000 | 4 | 2020 | 4 | 2023 | 7950000 | 2 | 2023 | 2 | 2029 | 75200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43437 | 0 | New Project. GRW - schedule and budget updates. Fall 17: NC, Fall 18 updated $ and timing | NULL | 0 | 0 | UTWS1617.jpg | Robinson, Molly | Steglitz, Brian | Sanford, Larry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Condition Analysis | Capacity Analysis | NULL | 1 | Water Treatment Plant Facilities Master Plan (2006) | NULL | NULL | NULL | Active | Planning | 87.91 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1813.66 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 150000 | 0
1808 | UT-WS-16-13 | Prairie St Water Main Replacement | 900000 | NULL | Prairie St | NULL | NULL | 14 | Frequent breaks. However, road was just resurfaced in 2013 | Cost estimate assumed it will be done with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 140000 | 2 | 2024 | 4 | 2024 | 1860000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: moved back due to cost restraints; cots spread but not updated; 2018 cost updated | NULL | 0 | 0 | UTWS1613.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 25.15 | 71 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1809 | UT-WS-16-15 | Hampshire Rd (Canterbury to Cranbrook) Water Main Replacement | 700000 | NULL | Hampshire Rd (Canterbury to Cranbrook). | NULL | NULL | 14 | condition/based on break history. | Cost estimate based on being done with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 100000 | 2 | 2022 | 4 | 2022 | 1400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | 2016 - Cost updated and spread; 2018 cost updated and pushed out as no road work planned | NULL | 0 | 0 | UTWS1615.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 22.18 | 75 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1810 | UT-WS-16-14 | Sunrise Ct Water Main Replacement | 150000 | NULL | Sunrise Ct | NULL | NULL | 14 | Condition/based on break history. Suggest waiting until road resurfacing is needed. | Cost estimate based on being done with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 0 | 2 | 2025 | 2 | 2025 | 300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | 2016 - Cost updated. Fall 17: NC; 2018 cost updated and moved out | NULL | 0 | 0 | UTWS1614.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 25.15 | 71 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1811 | UT-WS-16-16 | Glendaloch Rd (Glendaloch Cir to Londonderry) Water Main Replacement | 200000 | NULL | Glendaloch Rd (Glendaloch Cir to Londonderry) | NULL | NULL | 14 | condition/based on break history | Cost estimate assumed it will be done with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 50000 | 2 | 2025 | 2 | 2025 | 250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 42710 | 0 | 2016 - Cost updated and moved to FY23 Fall 18: costs not updated; moved to FY25 | NULL | 0 | 0 | UTWS1616.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 22.18 | 75 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1813 | UT-WS-16-18 | WTP: Residuals Handling Project | 2000000 | NULL | WTP and Residuals Pond | NULL | NULL | 14 | Implementation of recommendations from WTP Alternatives Analysis Project re removal of solids from residuals pond and implementation of filter press improvement recommendations. | Remove solids from the residual pond to ensure sufficient back up capacity for solids handling. Under normal operation, this would provide approximately 10 years of capacity. Consider construction of bird observation platform. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2018 | 50000 | 2 | 2019 | 4 | 2019 | 1950000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43437 | 0 | Fall 2016; updated budget and schedule. Fall 18 updated per WTP. Put on Hold, Spring 2019 due to lack on funds. | NULL | 0 | 0 | UTWS1618.jpg | Robinson, Molly | Steglitz, Brian | Sanford, Larry | Borneman, Dave | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Planning | 51.88 | 11 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 91349 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1824 | UT-SN-16-09 | Scio Twp. Pump Station | 200000 | NULL | Liberty | NULL | NULL | 12 | Rehabilitate aging pump station | Scio Twp. managing project; funds shown reflect City cost only | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 3 | 2016 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | 41968 | 1 | Fall 2015: City share only reflected | NULL | 0 | 0 | UTSN1609.jpg | Hupy, Craig | Kenzie, Earl | NULL | NULL | NULL | 1 | Scio Township | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Construction | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1814 | UT-WS-16-19 | WTP: Programmable Logic Controllers Replace. & Dam Security Upgrades | 1500000 | NULL | Water Treatment Plant- 919 Sunset Rd. | NULL | NULL | 14 | Replace existing equipment which has exceeded its life expectancy; improve security at Barton & Superior dams | Replace programmable logic controllers and Supervisory Control and Data Acquisition equipment at the WTP; security update at Barton and Superior per FERC requirements and reconfigure control room as a part of the SCADA modernization. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 2 | 2017 | 300000 | 4 | 2018 | 4 | 2020 | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 42684 | 0 | Fall 2016: Expanded scope to include dam security improvements; revised schedule and budget. Fall 18 update per WTP | NULL | 0 | 0 | UTWS1619.jpg | Robinson, Molly | Steglitz, Brian | Sanford, Larry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 65.93 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 84214 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1815 | UT-WS-16-20 | WTP: HVAC Improvements | 750000 | NULL | Water Treatment Plant - 919 Sunset Rd. | NULL | NULL | 14 | Replacement of aging HVAC system to address temperature control problems in several locations; including laboratory where temperature control is critical | Replace HVAC components including 60-ton chiller in ozone building; address ventilation issues in the chemical feed rooms; lab air handling unit. Units were installed over 20 years ago and have exceeded their life expectancy. Phased project. | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 3 | NULL | 2 | NULL | 0 | 3 | 2017 | 3 | 2018 | 40000 | 1 | 2019 | 1 | 2023 | 1850000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43437 | 0 | Fall 2015: Moved design out of FY16; increased total budget to $1M in FY17; Fall 2016: GRW - increased budget, added design phase, updated schedule. Project has been split into 2 phases. The first FY18/19 is the 60 ton chiller, phase 2 is all else. Fall | NULL | 0 | 0 | UTWS1620.jpg | Robinson, Molly | Steglitz, Brian | Sanford, Larry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 49.2 | 14 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 42402 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2042 | TR-OT-18-07 | State St (Washington to William) Streetscape | 1000000 | NULL | State St (Washington to William) | NULL | NULL | 9 | Enhance streetscape | DDA project; Streetscape; consider street lights; bike facilities connecting State to North U; conduit; coordinate with City resurfacing (Huron to S University); no work during Art Fair | NULL | Yes | 1 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 100000 | 2 | 2021 | 3 | 2022 | 900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | 43437 | 0 | Fall 2016: new Fall 18: moved to FY21-22 to go with street | NULL | 0 | 0 | TROT1807.jpg | Miller, Amber | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 10000 | 0
1816 | UT-WS-16-21 | Bird Rd Water RPZ Valve Replacement & Redundant Valve Addition | 200000 | NULL | Bird Rd at Newport Rd | NULL | NULL | 14 | Old RPZ needs replacing and install redundant valve. | Old RPZ needs replacing and install redundant valve. | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Woodward, Nichole | Gosselin, Deb | 43439 | 0 | Cost estimate needs work. Fall 2016: pushed to FY22. Fall 18 to 21 | NULL | 0 | 0 | UTWS1621.jpg | Woodward, Nichole | Wooden, Dan | Steglitz, Brian | Baughman, Troy | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | System reliability | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 23.36 | 73 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2088 | TR-PF-19-01 | Ann Ashley Parking Structure Expansion | 18000000 | NULL | Ann-Ashley Parking Structure | NULL | NULL | 10 | Increase parking capacity in the DDA | Increase Ann-Ashley parking structure height by 3 levels to add up to 375 additional spaces. Includes added elevator, suicide deterrent fencing, electrical and EV capactiy, LED lighting, stormwater detention, new stairs | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2017 | 2 | 2018 | 200000 | 4 | 2018 | 4 | 2019 | 21300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 42990 | 0 | Dependent upon DDA Board and Council approval Fall 17: New | NULL | 0 | 0 | TRPF1901.jpg | Pollay, Susan | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 100000 | 0
1817 | UT-WS-16-22 | Washtenaw Ave (Stadium to County Farm Park) Water Main Replacement | 5000000 | NULL | Washtenaw (Stadium to County Farm Park) | NULL | NULL | 14 | Replace aging watermains | High PAN. Examine both mains and consider upsizing. Enviro sensitivity. Coord w/ WCWRC/Cnty Park/MDOT. Close proximity to franchise utilities. Cost assumed replacing both mains and assumes it will be done as road project | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 280000 | 2 | 2024 | 4 | 2024 | 3720000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | 2016 - Split previous project (stadium to H. Pkwy) into 3 different projects due to cost and updated cost figures. Fall 17: NC; 2018 cost updated (doubled!) | NULL | 0 | 0 | UTWS1622.jpg | Baughman, Troy | Wooden, Dan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 16.24 | 83 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1821 | TR-AT-16-04 | Non-Motorized Connection under E Medical Center Dr Along S Side of Fuller | 220000 | NULL | Non-Motorized Connection under E Medical Center Dr. Along S Side of Fuller | NULL | NULL | 6 | Provide alternative non-motorized link through the Fuller Rd and East Medical Center Drive intersection area | Request by WBWC; utilize railroad platform area; create ped. & bicycle link to take non-motorized traffic away from busy intersection. Evaluate on a cost-benefit basis as surface link already exists. Potential train station site nearby. Art enhancement | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 2 | 2026 | 220000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43434 | 0 | Fall 2016: no change; added art enhancemetn 6/2017. Fall 18: moved to 2026 to match EMC project. | NULL | 0 | 0 | TRAT1604.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 51.75 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1818 | UT-WS-16-23 | Needham, Medford, Buckingham Water Main Replacement | 3500000 | NULL | Medford (Needham to Manchester); Needham (all); Buckingham (all) and Buckingham Ct, | NULL | NULL | 14 | Replace aging watermains. | High number of watermain breaks. Cost estimate assumed it will not be done as part of road project, but consider deferring until roads justify resurfacing or CPM. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 130000 | 2 | 2025 | 4 | 2025 | 1720000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: broke part of Medford out into new project based on size of project plus differing road conditions. Fall 17: NC; 2018 no cost change but moved back | NULL | 0 | 0 | UTWS1623.jpg | Baughman, Troy | Sanford, Larry | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 30.1 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1788 | UT-ST-16-09 | Lawton Park Stormwater Basin | 5155000 | NULL | Lawton Park | NULL | NULL | 13 | Flood mitigation; water quality improvements | Coordinate with Parks & Rec, AAPS, WCWRC; pipe improvement at 7th and Malletts Creek crossing; reroute storm sewer in Winsted, Mershon, Scio Church | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 375000 | 2 | 2024 | 4 | 2024 | 4780000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43423 | 0 | Fall 2016: removed SRF and spread costs. Fall 17: NC Fall 18; showed as all FY204 as County run | NULL | 0 | 0 | UTST1609.jpg | Sheehan, Harry | Lawson, Jennifer | Kuras, Amy | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | Upper Malletts Stormwater Conveyance Study | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 47.22 | 11 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1792 | UT-SN-16-03 | Huron/West Park Sanitary: SSWWEP Project Area A | 100000 | NULL | Sanitary sewers near Maple, Miller, and Dexter: SSWWEP Project Area A | NULL | NULL | 12 | Identified by SSWWEP as an area with wet weather pipe capacity issues | Preliminary engineering phase with additional physical investigation and engineering analysis; specific improvements to be designed as warranted based on preliminary engineering; previous UT-SN-91-15 and -16 eliminated and replced this and 16-04 | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 1 | 2016 | 1 | 2017 | 0 | 1 | 2016 | 2 | 2017 | 103000 | 3 | 2019 | 4 | 2020 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 42331 | 1 | Fall 2015: increased budget $3000; put overage in FY17 | NULL | 0 | 0 | UTSN1603.jpg | Hutchinson, Nick | Slotten, Cress | Baughman, Troy | NULL | NULL | 1 | NULL | NULL | NULL | SSWWEP CAC | 1 | Capacity Analysis | NULL | NULL | Sanitary Sewer Wet Weather Evaluation Program | 0 | NULL | NULL | NULL | NULL | Active | Design | 45.35 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 112322.63 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1789 | UT-ST-16-10 | Pioneer High Stormwater Basin | 1170000 | NULL | North of Scio Church Rd between 7th and Marra Dr. | NULL | NULL | 13 | Flood mitigation; water quality improvements | Coordinate with AAPS, WCWRC, Scio Church street project; maintain pedestrian access affected by trail removal; reroute storm sewer on Scio Church and at 7th intersection | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 80000 | 2 | 2025 | 4 | 2025 | 1090000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Sheehan, Harry | Gosselin, Deb | 43045 | 0 | Fall 2106: removed SRF and pushed back pending rate increase. Fall 17: NC but evaluate next fall Fall 18: booked into single year of FY25 | NULL | 0 | 0 | UTST1610.jpg | Sheehan, Harry | Lawson, Jennifer | Carson, Chris | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | Upper Malletts Stormwater Conveyance Study | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.24 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1795 | UT-SN-16-06 | Pittsfield Valley Sanitary: SSWWEP Project Area D | 100000 | NULL | Sanitary sewers near Platt Rd: SSWWEP Project Area D | NULL | NULL | 12 | Identified by SSWWEP as an area where model shows pipe capacity issues | Preliminary engineering analysis; specific improvements to be designed as warranted based on preliminary engineering; previous UT-SN-01-25 and UT-SN-93-26 replaced with this project | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 2 | 2016 | 209000 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 42663 | 1 | Fall 2015: increased budget by $109,000 | NULL | 0 | 0 | UTSN1606.jpg | Hutchinson, Nick | Slotten, Cress | Baughman, Troy | NULL | NULL | 1 | NULL | NULL | NULL | SSWWEP CAC | 1 | Capacity Analysis | NULL | NULL | Sanitary Sewer Wet Weather Evaluation Report | 0 | NULL | NULL | NULL | NULL | Active | Design | 51.46 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 325170 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2032 | MF-SW-18-04 | MRF & Transfer Station Bldg. and Site Evaluation & Repairs | 750000 | NULL | MRF | NULL | NULL | 15 | Address aging facilities | Overall building evaluation (electrical, roof, insulation,) evaluate sanitary and drainage discharge systems; evaluate access to buildings; address repairs identified | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2018 | 750000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gomes, Christina | Gosselin, Deb | 43039 | 1 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | MFSW1804.jpg | Gomes, Christina | Warba, Matt | Slotten, Cress | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 30.93 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1874 | UT-ST-16-18 | State St Area Stormwater Detention | 300000 | NULL | State Street in 1600 block area | NULL | NULL | 13 | Surface water drainage issues | Evaluate possible detention area to address surface drainage issues; do preliminary engineering first and then evaluate construction cost; UM to talk with nearby owner(s) abutting golf course; Referred to UM (John Kosco) | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 2 | 2023 | 25000 | 3 | 2024 | 4 | 2024 | 275000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43045 | 0 | Fall 2016: moved out. Fall 17: NC Fall 18: $ not updated NC | NULL | 0 | 0 | UTST1618.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 27.46 | 35 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1877 | TR-SC-16-18 | Nixon/Dhu Varren/Green Intersection Improvements | 1250000 | NULL | Nixon/Dhu Varren/Green Intersection | NULL | NULL | 11 | Motorized and non-motorized improvements needed in response to present and predicted traffic growth | Design roundabout per the preferred alternative chosen in the Nixon and Dhu Varren Intersection Study (TR-SC-15-01); non-motorized improvements; wetlands and trees to be considered in design; FY17 scheduling is dependent upon developer contribution | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2016 | 4 | 2016 | 200000 | 2 | 2018 | 4 | 2018 | 1925460 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 42984 | 1 | Fall 2015: Moved FY18 to FY17 and adjusted revenues to reflect developer contribution; Fall 17: marked TBC | NULL | 0 | 0 | TRSC1618.jpg | Kotlyar, Igor | Hutchinson, Nick | Slotten, Cress | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 53.72 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | 112769 | 2018-05-01 | 637146 | 2018-05-02 | 2145725 | 2018-05-02 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 3567439.51 | 2019-07-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1796 | UT-SN-16-07 | Glen Leven Sanitary: SSWWEP Project Area E | 20000 | NULL | Glen Leven: SSWWEP Project Area E | NULL | NULL | 12 | Identified by SSWWEP as an area where model shows pipe capacity issues | Determine surcharge level that impacts basements; televise and inspect sewers and perform additional analytics; evaluate replacement versus I/I removal | NULL | No | 0 | 0 | 7 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 2 | 2016 | 100000 | 3 | 2015 | 2 | 2016 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 42331 | 1 | Fall 2015: increased budget to $100K per bid; added overage in FY17 | NULL | 0 | 0 | UTSN1607.jpg | Hutchinson, Nick | Slotten, Cress | Baughman, Troy | NULL | NULL | 1 | NULL | NULL | NULL | SSWWEP CAC | 1 | Capacity Analysis | NULL | NULL | Sanitary Sewer Wet Weather Evaluation Report | 0 | NULL | NULL | NULL | NULL | Active | Design | 52.26 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 104778.55 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1798 | UT-WS-16-03 | Washtenaw Ave (Wayne St to North End of Tappen School) Water Main | 1700000 | NULL | Washtenaw Avenue (Wayne St to north end of Tappen School property) | NULL | NULL | 14 | Possible replacement due to main break/leak frequency | Also assess Fair Oaks water main for possible inclusion, consider upsizing, MDOT, concrete base, trolley tracks?, parallel water mains between Toumy and Birkshire (consolidate?), high PAN score.; cost estimate is: 2400 LF x $475/FT x 1.46 | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 125000 | 2 | 2024 | 4 | 2024 | 1575000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Baughman, Troy | 43046 | 0 | Fall 2016: moved to beyond 23: need to decide plan for all Washtenaw projects.Fall 17: NC Fall 18: NC, costs not updated | NULL | 0 | 0 | UTWS1603.jpg | Wooden, Dan | Baughman, Troy | Hupy, Craig | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 26.14 | 69 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1985 | UT-WS-18-17 | Dams: Barton Dam Hydroelectric Turbine Rebuild | 400000 | NULL | Barton Dam | NULL | NULL | 14 | Perform 10-year preventative maintenance overhaul of hydroelectric turbine and generator at Barton Dam Powerhouse. | 10-year preventative maintenance overhaul of hydroelectric turbine and generator at Barton Dam Powerhouse. Requires stop log installation and dewatering of intake/forebays. | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | 0 | 3 | 2017 | 1 | 2019 | 600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Gosselin, Deb | 43027 | 1 | Added Fall 2016: 100% General Funded. Fall17: increased to $600K in FY18; marked to be done by end of FY19 in Fall 2018 | NULL | 0 | 0 | UTWS1817.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 36.76 | 39 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 31440 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1799 | UT-WS-16-04 | State St (Granger to Stimpson) Water Main Upsizing | 760000 | NULL | S State Water Main Upsizing (Granger to Stimpson) and Henry from S State to White St. | NULL | NULL | 14 | Undersized Water Mains (1.5 and 2 inch) parallel to transmission main. | Upsize and complete loop. Examine leads from 20" transmission main. Consider zoning for sizing main. AAATA and UM bus routes. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 90000 | 2 | 2025 | 4 | 2025 | 1160000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 42711 | 0 | Fall 2016; spread 20/21 but previous costs seem too low. Fall 17: NC Fall 18: move way out until road needs work | NULL | 0 | 0 | UTWS1604.jpg | Heatley, Alison | Nearing, Mike | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.94 | 20 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1804 | UT-WS-16-09 | Longshore, Indianola, Ottawa, Argo & Amherst Water Main Replacement | 2700000 | NULL | 2000 Longshore Dr. to Argo, all of Amherst, Argo, Indianola, and Ottawa. | NULL | NULL | 14 | Replace aging water main, water quality and pressure issues. | Consider upsizing main. Environmentally sensitive area. Examine cause of water quality complaints (circulation?). Cost estimate is assuming it will not be done as part of road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 120000 | 2 | 2019 | 4 | 2019 | 4260000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 43438 | 0 | Fall 2016: spread costs to 18 and 19. Fall 17: moved to 19-20 Fall 18 $update | NULL | 0 | 0 | UTWS1609.jpg | Sanford, Larry | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 36.83 | 42 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1601330.73 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1800 | UT-WS-16-05 | Mosely (Main to 3rd), 3rd (Mosley to Madison) & Wilder Pl Water Main Upsizing | 450000 | NULL | Mosely (Main to 3rd), 3rd (Mosley to Madison) & Wilder Pl | NULL | NULL | 14 | Condition and capacity | Upsize to 12" main to First on Mosley; upsize to 8" for remainder of Mosley/Third; Add 8" main on Wilder Pl to complete loop; coordinate with ASRP; Leave stub towards Wurster Park for future loop to Turner Ct. Cost based on being done with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 50000 | 2 | 2019 | 4 | 2019 | 1275000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Baughman, Troy | 43424 | 0 | Scope increased; Cost updated Nov. 2016. Fall 17: NC Fall 18: updated costs | NULL | 0 | 0 | UTWS1605.jpg | Baughman, Troy | Heatley, Alison | Sanford, Larry | Rolla, Liz | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 45.94 | 20 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 130000 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1801 | UT-WS-16-06 | Fifth Ave (515 N Fifth to Catherine) Water Main Upsizing | 300000 | NULL | N Fifth Ave (515 N Fifth to Catherine) | NULL | NULL | 14 | Replace undersized and aging pipe | Coordinate with Street reconstruction project; DDA; cost estimate based on project being done with a road project. | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2017 | 2 | 2017 | 28000 | 2 | 2018 | 4 | 2018 | 986000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43011 | 1 | Fall 2106: edited Jenn's numbers up based on previous information. Fall 17: increased FY18 budget to 900k due to increased scope | NULL | 0 | 0 | UTWS1606.jpg | Rolla, Liz | Baughman, Troy | NULL | UT-WS-16-06 | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Condition Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 42.19 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 895212 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1803 | UT-WS-16-08 | Baldwin (Washtenaw to Wells) Water Main Replacement | 1100000 | NULL | Baldwin (Washtenaw to Wells) | NULL | NULL | 14 | Replace aging and undersized main | Upsize pipe; Consider zoning for sizing and hydrant coverage. Coordinate with Washtenaw main replacement in this area. Student area. High PAN score. Cost estimate assuming not being associated with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 0 | 2 | 2024 | 4 | 2024 | 1600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: spread costs; 2018 cost updated and moved back | NULL | 0 | 0 | UTWS1608.jpg | Baughman, Troy | Wooden, Dan | NULL | NULL | NULL | 1 | NULL | NULL | NULL | Mayor | 1 | Capacity Analysis | Condition Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 30.1 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1805 | UT-WS-16-10 | Pontiac, Swift, Wright, New Water Mains | 400000 | NULL | Pontiac (Swift to Moore); Swift (Pontiac to Wright); Wright St (Kellogg northerly to dead-end) | NULL | NULL | 14 | Add water mains to create loops and improve water quality (in Pontiac/Swift); Replace main in Wright (north of Kellogg) due to freezing issues | Install mains on Pontiac (Swift to Moore) and Swift (Pontiac to Wright) | Examine general area; Coordinate w/ ASRP. Wright St N. of Kellogg has freezing issues (hist. stormwater features); see 6C861 re: shared 4" san lead for multiple properties | NULL | Yes | 0 | 29 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 70000 | 2 | 2023 | 4 | 2023 | 930000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: cost updated; Wright St (north of Kellogg) was added due to freezing issues raised by WTP. Fall 17: NC; 2018 cost updated | NULL | 0 | 0 | UTWS1610.jpg | Heatley, Alison | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 34.06 | 49 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1806 | UT-WS-16-11 | Hubbard (Murfin to 600' West) Water Main Replacement | 300000 | NULL | Hubbard (Murfin to 600 West) | NULL | NULL | 14 | Upgrade main | Replace" the existing 12" water main in Hubbard from Murfin, westerly 600’. Coordinate with UM water main and road project. Work out agreements for design and construction. Cost estimate based on coordination with UM's project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 0 | 3 | 2023 | 3 | 2023 | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Baughman, Troy | 43389 | 0 | Fall 2016: 2018 cost updated and schedule moved | NULL | 0 | 0 | UTWS1611.jpg | Baughman, Troy | Heatley, Alison | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 33.07 | 53 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2034 | TR-OT-18-S1 | Intelligent Transportation System (ITS) Master Plan | 250000 | NULL | Systemwide | NULL | NULL | 9 | Master Plan ITS System for maximum customer service, safety, and system flexibility | Overall master plan for ITS system including primary component of communication system (cables, conduits) as well as traffic signals, system operations, and interagency partnerships. Integrate Transportation Plan recommendations | NULL | No | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2021 | 2 | 2022 | 250000 | 3 | 2018 | 2 | 2019 | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Gosselin, Deb | 43437 | 0 | Fall 2016: added. Fall 2018 moved to FY22 to be after Transporation Plan update | NULL | 0 | 0 | TROT18S1.jpg | Liu, Luke | Fojtik, Chuck | Matthews, Paul | Cooper, Eli | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 55.05 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1827 | MF-CB-16-02 | 721 N Main Demolition and Site Stabilization | 300000 | NULL | 721 N Main | NULL | NULL | 1 | Demolish obsolete and aging structure per N Main Task Force recommendation | Environmental issues; disposal of contents; in floodplain; FEMA determined not fund elgible for demolition. | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hancock, Jerry | Hancock, Jerry | 42676 | 0 | Fall 2016: shifted to FY20 to allow time to determine environmental cleanup needs per FEMA and also cannot request funds until when and if FEMA funds are replenished. Cost estimete includes $200,000 for environmental cleanup and $200,000 for demolition. | NULL | 0 | 0 | MFCB1602.jpg | Hancock, Jerry | Pulcipher, Connie | Crum, Lynn | Fales, mary | NULL | 1 | NULL | NULL | NULL | N Main Task Force Building Assessment Report | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 32.7 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 1 | 1 | NULL | NULL | 1 | 1 | 0 | NULL | NULL | 1
1828 | UT-WS-16-26 | Dams: Barton Dam Embankment Rehabilitation | 1600000 | NULL | Barton Dam | NULL | NULL | 14 | Address FERC mandated repairs | Repair seepage through right embankment. Alternatives for repair have not yet been determined. Install additional piezometers and monitor. Fill pond at toe of embankment. | NULL | No | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 3 | 2016 | 2 | 2019 | 180000 | 3 | 2019 | 2 | 2020 | 250000 | 3 | 2021 | 2 | 2022 | 1600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Gosselin, Deb | 43438 | 0 | Fall 2016: Rolled in piezometers (formerly UT-WS-18-18) and Filling Pond at Toe of Embankment (originally UT-WS-20); updated funding to reflect additional scope from UT-WS projects. Fall 17; revised time and $. Fall 18 NC | NULL | 0 | 0 | UTWS1626.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 67.72 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 285063 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2188 | MF-CB-20-01 | Fire Station 1 Remodel | 400000 | NULL | Fire Station 1 | NULL | NULL | 1 | Renovate third floor to accommodate Emergency Operations Center, Fire Prevention Bureau, achieve ADA complaine and facility gender equity | Demolition of 3rd floor facilities; abate asbestos; create Emergency Operations Center & Fire Prevention Bureau space, achieve ADA compliance; achieve facility gender equity by creating locker room, restroom, and dorms; install fire suppress; elim. Sta 2 | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 40000 | 1 | 2020 | 3 | 2020 | 360000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kennedy, Mike | Gosselin, Deb | 43431 | 0 | Fall 18: new | NULL | 0 | 0 | MFCB2001.jpg | Kennedy, Mike | Kulhanek, Matt | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 1 | Fire Station Master Plan | NULL | NULL | NULL | Programmed | Inactive | 75.1 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 2 | NULL | 1 | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 0
1829 | UT-SN-16-10 | WWTP Bridge
WWTP Bridge | 475000 | NULL | WWTP | NULL | NULL | 12 | Rehab aging bridge | Rehabilitate pier; consider deck patching; clearing and brush removal for access improvement; temporary coffer dam needed; coordinate with WWTP operations after renovation complete | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 2 | 2016 | 528000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Amicangelo, Mike | Gosselin, Deb | 42331 | 1 | Fall 2015: bumped up to $528K per Plant | NULL | 0 | 0 | UTSN1610.jpg | Amicangelo, Mike | Nearing, Mike | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | Consultants report | 0 | NULL | NULL | NULL | NULL | Active | Design | 40.83 | 23 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1830 | UT-SN-16-11 | Sanitary Sewer Collection System Asset Management Plan | 1200000 | NULL | Citywide | NULL | NULL | 12 | Comprehensive Asset Management and Maintenance Plan for Sanitary Sewer system necessary. Rehab and Replacement needs. Future Planning. | Include pipe & manhole condition assessment; Include updating all photos for manhole inspection; Phase 2 would include metering; capture conflicts with structures (risk of collapse). See 2014 SAW application, including estimates from engineer. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 1 | 2016 | 2 | 2018 | 864500 | 1 | NULL | 2 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 42663 | 1 | Fall 2015: Adjusted funding and schedule to reflect the Spring 2015 Council budget that spread the costs over three fiscal years; Fall 2106: adjusted to actual progress; in FY 18 need $237,100 for contract; balance to inspection | NULL | 0 | 0 | UTSN1611.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Condition Analysis | Customer Level of Service | NULL | 0 | NULL | NULL | NULL | NULL | Active | Planning | 50.95 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1878 | TR-SC-16-19 | State St (Packard to Hoover) Resurfacing | 330300 | NULL | State Street (Packard to Hoover) | NULL | NULL | 11 | Pavement condition | Base failure at Hoover; soil borings needed; determine resurface versus reconstruct; stormwater needed if reconstructed; evaluate water main condition; through Hoover intersection; evaluate bike lanes; Evaluate sanitary; UM coordination and priority | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2018 | 0 | NULL | 80000 | 2 | 2018 | 4 | 2018 | 270000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 1 | Fall 2016: edited costs, Fall 17: NC | NULL | 0 | 0 | TRSC1619.jpg | Hutchinson, Nick | Elenbaas, Chris | NULL | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.97 | 24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1879 | MF-CB-16-05 | Guy C. Larcom Municipal Building: Exterior Shell Energy Improvements Study | 50000 | NULL | Guy C. Larcom Municipal Building | NULL | NULL | 1 | Improve energy efficiency of Guy C. Larcom Municipal Building superstructure | Structural and energy efficiency study of exterior shell (windows and walls); evaluate cost-benefit ratios for identified improvement options | NULL | No | 0 | 0 | 4 | NULL | NULL | 1 | 0 | NULL | 3 | 2021 | 2 | 2022 | 50000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Geisler, Nate | Gosselin, Deb | 43003 | 0 | Fall 2016: NC; Fall17: moved to FY19 (not funded for FY18) | NULL | 0 | 0 | MFCB1605.jpg | Kulhanek, Matt | Geisler, Nate | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Capacity Analysis | Customer Level of Service | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 14.23 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 2 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | NULL | NULL | 0
1880 | UT-ST-16-19 | Geddes Ave ((Observatory to Highland) Stormwater Improvements | 2500000 | NULL | Geddes (Observatory to Highland) | NULL | NULL | 13 | Provide stormwater improvements per Complete Streets policy | Coordinate with street reconstruction project | NULL | Yes | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 15000 | 2 | 2022 | 2 | 2022 | 235000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Gosselin, Deb | 43423 | 0 | Fall 2016: no longer reconstruction; left in modest amount in case or rain garden opportunities. Fall 17: NC Fall18: NC but if not reconstruction, will be eliminated | NULL | 0 | 0 | UTST1619.jpg | Lawson, Jennifer | Hutchinson, Nick | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 39.76 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 3 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1862 | UT-ST-16-14 | Street Tree Planting (FY2016-FY2025) | 2070000 | NULL | City Wide | NULL | NULL | 13 | Implement UCFMP and 2013 SRF Street Tree Planting Program | Plant trees (750 trees per year). Should include stump removals and tree removals. ($414,000) per year, which includes 10% contingency. | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 4 | 2024 | 4091000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gray, Kerry | Gosselin, Deb | 43424 | 0 | Fall 2015: Edited FY2016 budget to match SRF (DG). Fall 2016: did not add anything past FY20. Fall 17: NC but will add funds past FY20 next fall. Fall 18: changed to title to extend to 2025 and added $ in outer years | NULL | 0 | 0 | UTST1614.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 1 | Urban Forest Management Plan | 2013 SRF | NULL | NULL | Active | Planning | 44.37 | 14 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 1 | 1 | 1 | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
2090 | TR-PF-19-03 | Parking Facilities General Capital Maintenance | 1199629 | NULL | City parking structures | NULL | NULL | 10 | Maintian facilities in safe and convenient manner | Address repair, service enhancement, or regulatory complaince issues as they arise. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2025 | 1002364 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43433 | 0 | Added Fall 2017. Fall 18: updated per DDA | NULL | 0 | 0 | TRPF1903.jpg | Pollay, Susan | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2083 | TR-AT-18-26 | Border to Border: Connection Under Fuller Rd. | 200000 | NULL | Under Fuller Rd. (connecting north and south portions of Fuller Park) | NULL | NULL | 6 | Provide connection under Fuller Road for the north and south components of the Border to Broder Trail in Fuller Park | Provide connection under Fuller Road for the north and south components of the Border to Broder Trail in Fuller Park | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 2 | 2026 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kuras, Amy | Gosselin, Deb | 43434 | 0 | Fall 18: moved to 26 to go with Fuller Rdimprovements; probably use funds other than GF but left that way for now. | NULL | 0 | 0 | TRAT1826.jpg | NULL | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Parks & Recreation Open Space (PROS) Plan | NULL | Ann Arbor Non-Motorized Plan | NULL | Programmed | Inactive | 45.25 | 24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1889 | MF-CB-17-01 | Housing Commission: 701 Henry | 8000000 | NULL | 701 Henry Street White/State/Henry | NULL | NULL | 1 | Replace aging facilities; | Obtained site plan approval for removal of existing facilities; currently 28 public housing apartments. New construction will include 32 apartments for low-income residents | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2017 | 2 | 2018 | 200000 | 3 | 2018 | 3 | 2019 | 8800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | 42996 | 0 | Added Fall 2015 Fall 2016: Changed name to 701 Henry per JH and moved to FY 18 start. Fall 17: moved to FY19 per JH as funding not obtained but added $200K in FY18 using County brownfield funds | NULL | 0 | 0 | MFCB1701.jpg | Hall, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1892 | MF-SW-17-01 | Organics Management Study | 100000 | NULL | Citywide | NULL | NULL | 15 | Minimization of waste and the conservation of natural resources | Create a comprehensive organics management plan | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2015 | 2 | 2016 | 100000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gomes, Christina | Gosselin, Deb | 42299 | 1 | NULL | NULL | 0 | 0 | MFSW1701.jpg | Gomes, Christina | Naud, Matt | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | City Council | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1893 | TR-SC-17-01 | County Millage Street Capital Preventive Maintenance
Street Capital Preventive Maintenance | 2400000 | NULL | Citywide | NULL | NULL | 11 | Increase capital preventive maintenance ("CPM") improvements on City streets | Utilize county millage monies for CPM improvements. FY16 target streets are Dexter Ave (Maple to City Limits), Pauline Blvd (Maple to Stadium), Huron River Dr. (Main to City Limits), Pontiac St (John A Woods to Skydale), and Dhu Varren (Pontiac to RR). | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2016 | 4 | 2016 | 2400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 42300 | 1 | Fall 2105: added project; edited limits in Fall 2016 to reflect that Stadium project will take main up Prescott to Potter to 7th and thereby allow the main on 7th from Potter to Stadium and on Stadium from 7th to Prescott to be eliminated | NULL | 0 | 0 | TRSC1701.jpg | Hutchinson, Nick | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1831 | UT-SN-16-12 | Sanitary Manhole Lid and Casting Sealing Program | 600000 | NULL | Sanitary manholes in flood prone areas. | NULL | NULL | 12 | Reduce inflow to sanitary system via manhole covers. | Identify locations. Prioritize. Consider manhole condition. Update manhole photos at time of inspection. Evaluate H2SO4 gas production. Coordinate with street construction. Balanced over 2 years. Hire out to a contractor. | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 4 | 2017 | 84000 | 2 | 2018 | 4 | 2018 | 1450000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43440 | 0 | Fall 2016: adjusted down and spread costs. Fall 17: switched funding to Dom for improvement phase. Fall 18 updated figures | NULL | 0 | 0 | UTSN1612.jpg | Baughman, Troy | Cozart, Mark | Lawson, Jennifer | Woodward, Nichole | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 41.67 | 18 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 83332.04 | 2017-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | 2015-039 | NULL | NULL | 2015-039 | 2019-03-30 | 405639 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | NULL | 0
1832 | UT-SN-16-13 | High Level Trunkline Sanitary Sewer Rehabilitation | 3000000 | NULL | High level trunkline from Stadium/Packard to Miller/First. 30" and 24" Sanitary | NULL | NULL | 12 | CCTV inspection performed by Field showed pipe needs lined (I/I, mineral buildup, tree roots, etc.). | Review CCTV and determine worst sections for phasing purposes (downtown had most I/I). Start with segments not impacted by proposed SWWP projects. 2018: Very bad encrustation starting at Ashley/Jefferson heading upstream (this should be priority) | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 100000 | 2 | 2019 | 4 | 2021 | 3650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Gosselin, Deb | 43440 | 0 | 13,650 LF x $200LF x 1.35 = $3.7M. Use $3.75M $150/LF is based on 2014 Lining prices from Lanzo contract. Dom funds. Ph 1: Fall 18 | NULL | 0 | 0 | UTSN1613.jpg | Baughman, Troy | Woodward, Nichole | Cozart, Mark | Slotten, Cress | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 61.2 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 5248.26 | 2019-07-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | 2 | 2 | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
1934 | UT-ST-18-10 | Placid Way Culvert and Headwall Replacement | 250000 | NULL | Placid Way at Tuebingen | NULL | NULL | 13 | Replace aging culvert and headwall, downstream erosion, and streambank stabilization | Rehab twin 42" culverts; reconstruct intakes; remove and replace outlet headwall; MDEQ permit; steep banks; WCWRC permit; Foxfire 1 detention impacted; sanitary sewer beneath and high pressure gas main above; coordinate with stream stabilization; in park | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 40000 | 2 | 2020 | 2 | 2020 | 250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43045 | 0 | Fall 2016: new; used $ per CE. Fall 17: moved to FY20 | NULL | 0 | 0 | UTST1810.jpg | Elenbaas, Chris | Lawson, Jennifer | Sheehan, Harry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 55.87 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1837 | UT-WS-16-37 | E University (619 E University to Monroe) Water Main Upsizing | 100000 | NULL | E University (619 E University to Monroe) | NULL | NULL | 14 | Complete upsizing from S University to 619 E University (Zaragon). Wait until road resurfacing is needed. | Abandon 6" main south of Monroe to Hill St. U of M. Potential storm improvements (SWM project). Cost estimate assumed it will be done with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 15000 | 3 | 2023 | 3 | 2023 | 185000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: spread to 23/24; waiting for road; 2018 cost updated | NULL | 0 | 0 | UTWS1637.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.31 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1833 | MF-CB-16-03 | Housing Commission: 701-749 N Maple | 12250000 | NULL | 701-749 N Maple | NULL | NULL | 1 | Upgrade housing complex | Demolish 20 units; rehabilitate 4 units; construct 42 new units; utility replacement | NULL | No | 0 | 0 | 8 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 1 | 2016 | 0 | 2 | 2016 | 4 | 2016 | 13500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | 42262 | 1 | Fall 2015: Revised budget per JH email. Fall 2106: TBC | NULL | 0 | 0 | MFCB1603.jpg | Hall, Jennifer | Heatley, Alison | McDonald, Kevin | Mitchell, Lance | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | Condition Analysis | Housing Commission | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1834 | MF-CB-16-04 | Housing Commission: 3401-3481 Platt | 9000000 | NULL | 3401-3481 Platt | NULL | NULL | 1 | NULL | Demolish 6 units; construct 32 new units; floodplain; new curb cut across from Sharon Dr.; new utilities onsite; redo or relocate existing driveway; Stone School Road construction | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 1 | 2019 | 0 | 2 | 2019 | 3 | 2020 | 9000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | 43003 | 0 | Fall 2105: Modified budget per JH email. Fall 2106: moved to FY18 start per JH. Fall 17:moved to FY19 as funding not yet obtainednper JH. | NULL | 0 | 0 | MFCB1604.jpg | Hall, Jennifer | Mitchell, Lance | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1838 | UT-WS-16-29 | Fifth Ave (Jefferson to Packard) Water Main Upsizing | 100000 | NULL | S Fifth Ave (Jefferson to Packard) | NULL | NULL | 14 | Complete upsizing from City Place apartments to Packard. | Coordinate with road resurfacing. Cost estimate based on being done with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 0 | 2 | 2024 | 4 | 2024 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: left alone but check road schedule as it gets closer; 2018 cost updated | NULL | 0 | 0 | UTWS1629.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.31 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1835 | UT-WS-16-27 | Liberty (318 W Liberty to Main St) Water Main Replacement
Liberty Water Main Upsizing (318 W Liberty to Main St) | 400000 | NULL | W Liberty (318 W Liberty to Main St) | NULL | NULL | 14 | Aging and undersized watermain. Developer upsizing main from Third to 318 W Liberty. | RR bore. Allen Creek. Coordinate with road resurfacing. DDA. Cost estimate assumed it will be done as part of road project. | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 4 | 2016 | 40000 | 3 | 2025 | 4 | 2025 | 488000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43439 | 0 | Fall 2016: spread costs. 11-17-17 closed out design. Fall 18: to 26 to mastch rd | NULL | 0 | 0 | UTWS1627.jpg | Baughman, Troy | Sanford, Larry | Pollay, Susan | Heatley, Alison | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 48.31 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1836 | UT-WS-16-28 | Maynard St (Nickels Arcade to Liberty) Watermain Replacement | 100000 | NULL | Maynard St (Nickels Arcade to Liberty) | NULL | NULL | 14 | Upsizing to complete project from William to Nickels Arcade. | Parking structure. DDA. Alley access. Cost estimate assumed it will be done as part of road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 10000 | 2 | 2019 | 2 | 2019 | 290000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43424 | 0 | Fall 2016; left in FY19. Fall 17: NC; March 2018, put on hold in CPAN until road condition warrants; 2018 Cost Updated | NULL | 0 | 0 | UTWS1628.jpg | Baughman, Troy | Heatley, Alison | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.31 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1864 | TR-AT-16-05 | Morehead-Delawdunare Pedestrian Bridge | 450000 | NULL | Between Morehead Ct. and Delaware Drive; crosses Malletts Creek in dedicated pedestrian walkway strip which is 10' wide | NULL | NULL | 6 | Reestablish pedestrian crossing over Malletts Creek | Existing bridge sat on weir controlled/owned by Lans. Basin; weir was repaired; new bridge will not use it as superstructure; 80' span; access very difficult due to limited access and staging areas; construction easements needed; design-build; $ unknown | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2015 | 1 | 2017 | 45000 | 2 | 2017 | 4 | 2017 | 405000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Kotlyar, Igor | 42690 | 1 | Fall 2015: moved from FY20 to FY16 per Council at capital budget in Spring 2015; Fall 2016: changed to design-build after public engagement; balance of money $300,000 after $150,000 switched to Driving Culture Study | NULL | 0 | 0 | TRAT1605.jpg | Dykman, Dave | Hupy, Craig | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 26.35 | 33 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 34434.39 | 2016-12-24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2069 | UT-SN-18-08 | Springwater Phase IV Sanitary Sewer | 160000 | NULL | Cardinal | NULL | NULL | 12 | Replace aging sanitary sewer | Transfer leads from houses on east side to newer sanitary main constructed by condominium project and reconstruct any remaining old main | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 11000 | 2 | 2024 | 4 | 2024 | 149000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 42717 | 0 | Fall 2016: new | NULL | 0 | 0 | UTSN1808.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.1 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1865 | TR-BR-16-02 | East Medical Center Drive Bridge Rehabilitation | 1112500 | NULL | East Medical Center Drive Bridge | NULL | NULL | 7 | Rehabilitate aging bridge | Repair pier two; hydro demolition and overlay on deck; joint removal/eplacement; steel repair as needed; guardrail repairs and upgrades as needed; zone painting at a minimum; explore painting all; coordinate w/intersection; widen bridge as option; rescope | NULL | Yes | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 1 | 2017 | 4 | 2017 | 0 | 3 | 2026 | 4 | 2026 | 100000 | 2 | 2027 | 4 | 2027 | 1818000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 43432 | 0 | Split off Fall 2014 from TR-BR-10-06 due to NFC funding class. added to FY2016-FY2021 CIP. Fall 2015: if intersection project is moves up, then this needs to too; Fall 2016: revised schedule and funds; Fall 17 revised schedule. Fall 18 to beyond 25 | NULL | 0 | 0 | TRBR1602.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 86.7 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 2 | NULL | 1 | 2 | NULL | 2 | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2091 | TR-AT-19-03 | School Safety Improvements | 200000 | NULL | School zones | NULL | NULL | 6 | Evaluate safety needs and implement projects to increase safety in school zones | Evaluate safety issues and implement projects to address them in school zones including pedestrian crossing and signalization issues, sidewalk gaps, etc. | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 25000 | 2 | 2018 | 2 | 2025 | 775000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43433 | 0 | Fall 17: added project per Tran. Comm. Request to make more visible. Fall 18: NC | NULL | 0 | 0 | TRAT1903.jpg | Redinger, Cynthia | Hutchinson, Nick | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 69.38 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2075 | TR-OT-18-08 | Huron East (Division to State) Streetscape | 660000 | NULL | Huron (Division to State) | NULL | NULL | 9 | Improve the connection to campus while also improving the crossing experience north to south | DDA project. Possible elements to supplement those done by private development: new sidewalks, street trees, lighting, decorative paving, stormwater infiltration, and crossing treatments | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 180000 | 2 | 2023 | 4 | 2023 | 1320000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43437 | 0 | Fall 2016 new. Fall 18 upped $ per DDA | NULL | 0 | 0 | TROT1808.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 15000 | 0
1939 | UT-SN-18-04 | Lafayette - Lenawee Sanitary | 330000 | NULL | Lafayette and Lenawee | NULL | NULL | 12 | Eliminate back-flowing sewer | Reconfigure sanitary to flow to Lenawee | NULL | NULL | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 30000 | 0 | NULL | 0 | NULL | 300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Elenbaas, Chris | 42716 | 1 | Fall 2016: new; Deb spread Chris's costs | NULL | 0 | 0 | UTSN1804.jpg | Elenbaas, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 30.38 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 637000 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2048 | UT-WS-18-43 | State St (UM Tennis Ct Entrance to Railroad ROW) Raw Water Main 30" Upgrade | 2236000 | NULL | State St (UM Tennis Ct Entrance to Railroad ROW) | NULL | NULL | 14 | Replace and upsize aging raw water main | Replace and upsize approximately 2600 LF raw water main to 30" ; coordinate with road treatment | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 4 | 2025 | 155000 | 2 | 2026 | 4 | 2026 | 2081000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43437 | 0 | Fall 2016: split from bigger project. Assume $860 per LF based on info from MN for Stadium. Fall 17: NC Fall 18: moved out | NULL | 0 | 0 | UTWS1843.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.26 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2060 | UT-WS-18-50 | Hill St (Adams to Fifth) Water Main Upsizing | 500000 | NULL | Hill St (Adams to Fifth) | NULL | NULL | 14 | Replace aging & undersized water main | Increase to 12'; replace under RR tracks; connect to transmission main at Fifth; potential development site is in planning stages west of Adams | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 30000 | 2 | 2019 | 2 | 2019 | 470000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43045 | 0 | Fall 2016: New. Fall 17: moved to FY19 Fall 18 NC | NULL | 0 | 0 | UTWS1850.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 33.96 | 50 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2012 | TR-SC-18-08 | State St (S University to Packard) Resurfacing | 540000 | NULL | S State St - S University to Packard | NULL | NULL | 11 | Pavement condition | Resurfacing; coordinate with UM; geotechnical near Hill; Allen Creek watershed; Proposed major mid-block crossing at Monroe; shared road identification; transfer water leads | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 35000 | 2 | 2022 | 4 | 2022 | 505000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2106: new. Fall 17: NC | NULL | 0 | 0 | TRSC1808.jpg | Dykman, Dave | Pennington, Kirk | Cooper, Eli | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 59.78 | 11 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2076 | TR-OT-18-09 | First and Ashley (Kingsley to Madison) Two Way Restoration and Streetscape | 4840000 | NULL | First and Ashley (Kingsley to Madison) | NULL | NULL | 9 | Recommended priority by Nelson/Nygaard and Streetsense as a way to provide significant benefits from increased business access and visibility, as long as bike facilities remain or are improved. | Restore streets to 2-way, encourage pedestrian scale development; landscaping, lighting and signals, sidewalk replacement, street furnishing; protected bike lane on 1st (Treeline), water main upsizing (funded by DDA); water consolidation (funded by City); | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2018 | 850000 | 3 | 2020 | 2 | 2021 | 6930000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43437 | 0 | Fall 2016: new; rolled in the streetscape projects (18-10 and 18-11) pe DDA on 9/1/2017 and renamed accordingly. Updated dollars. Fall 18: moved contributions to water and paving to City projects and adjusted to spends to date | NULL | 0 | 0 | TROT1809.jpg | Miller, Amber | Rolla, Liz | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | NULL | 0
1839 | UT-WS-16-30 | Hill St (Fifth to State) Water Main Upsizing | 1000000 | NULL | Hill St (Fifth to State) | NULL | NULL | 14 | Aging and undersized main | Coord w/road work & san improvements (target area from SSWWEP). UM. Expect dewatering. $ estimate based on assumption it will be done as part of rd project. This stretch has multiple sanitary sewers; investigate if consolidation is desirable/feasible. | NULL | Yes | 0 | 29 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 90000 | 2 | 2024 | 4 | 2024 | 1210000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Baughman, Troy | 43388 | 0 | Needs to align with street project; $ updated Nov 2016 so push out to beyond pending Nick's decision on Hill; 2018 cost updated; Need to reconfig 12" san connect at Division/Hill (12" connects to 30" at flow line causing backup to 12") | NULL | 0 | 0 | UTWS1630.jpg | Baughman, Troy | Hutchinson, Nick | Rolla, Liz | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 48.31 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1840 | UT-WS-16-31 | Hoover (Main to State) Water Main Upsizing | 1000000 | NULL | Hoover Watermain Replacement (Main to State) and Greene (Keech to Hill) | NULL | NULL | 14 | Aging and undersized mains. | Coordinate with road work and sanitary improvements (target area from SSWWEP). RR crossing. U of M. Expect dewatering. | NULL | Yes | 0 | 29 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2018 | 70000 | 2 | 2019 | 4 | 2019 | 930000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43438 | 0 | Fall 2016: spread costs 19/20. Fall 19 NC | NULL | 0 | 0 | UTWS1631.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 48.31 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1841 | UT-WS-16-32 | Broadway (Baits to Jones) Water Main Replacement | 1100000 | NULL | Broadway Watermain Replacement (Baits SW to Plymouth) | NULL | NULL | 14 | Water quality issues. Cost estimate based on being done with road project. | Multiple pressure zones. Abandon 6" watermain from Jones to Plymouth. Coordinate with road project TR-SC-16-10 | NULL | Yes | 0 | 29 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 0 | 2 | 2021 | 4 | 2021 | 2100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: spread costs over two fiscal years; 2018 cost updated | NULL | 0 | 0 | UTWS1632.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 34.45 | 47 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1842 | UT-WS-16-33 | Main St (William to Huron) Water Main Replacement | 500000 | NULL | S Main St Watermain Replacement (Huron to William) | NULL | NULL | 14 | Identified during road resurfacing check. Aging main. | Coordinate with road work. Concrete base. DDA. Historic district. Cost estimate based on being done with road project. Project proceeding is subject to further discussion with DDA. Per Field Op, need to rehab san MH at Liberty/Main | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 70000 | 2 | 2022 | 4 | 2022 | 930000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | cost updated in 2016; 2018 cost updated | NULL | 0 | 0 | UTWS1633.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 29.5 | 62 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1843 | UT-WS-16-34 | Ann (First to Main) Water Main Upsizing | 300000 | NULL | Ann St. water main Replacement (First to Main) | NULL | NULL | 14 | Aging and undersized mains. | Complete upsizing begun by First Martin development on Huron and Ashley. Coordinate with road work. | NULL | Yes | 0 | 37 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 35000 | 2 | 2023 | 4 | 2023 | 465000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43388 | 0 | Fall 2016: spread costs to FY 20/21; 2018 Cost updated and matched to road schedule | NULL | 0 | 0 | UTWS1634.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 40.89 | 31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1845 | UT-SN-16-14 | Stone School Rd (Packard to Eisenhower) Sanitary Extension | 250000 | NULL | Stone School (Ticknor to Packard) | NULL | NULL | 12 | Provide sanitary sewer service where parcels are not served | Install approx. 750 LF of sanitary sewer to serve parcels north of Tichnor Ct; Coordinate with road resurfacing. | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 20000 | 2 | 2018 | 2 | 2018 | 230000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43045 | 1 | Project broken out from UT-SN-12-03; number not thoroughly evaluated in Fall 2014. Fall 17: Fy19 to FY18 | NULL | 0 | 0 | UTSN1614.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 41.65 | 11 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 567000 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1849 | TR-PF-16-04 | Maynard Parking Structure Capital Maintenance | 735750 | NULL | 324 Maynard | NULL | NULL | 10 | Perform capital maintenance | Concrete repair; deck coating; | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2016 | 2 | 2024 | 3398525 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 43433 | 0 | Fall 2015: spread from FY17 to FY16,17, and 18; note need for a later phase to add next fall; Fall 2106: added funds in FY2023; Fall 17, | NULL | 0 | 0 | TRPF1604.jpg | Pollay, Susan | Morehouse, Joe | NULL | NULL | NULL | 1 | NULL | NULL | NULL | DDA | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1848 | TR-PF-16-03 | Liberty Square Parking Structure Capital Maintenance | 1216700 | NULL | 510 E Washington | NULL | NULL | 10 | Address delamination | Re-waterproof outside brick; maintain structure use; pedestrian protection; possible deck waterproofing | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 2 | 2025 | 2275478 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 43413 | 0 | Fall 2015 Split into two years (FY17 and FY18), and adjusted budget per SP Fall 2016: rolled in TR-PF-16-07 and added funds in FY22: Fall 2017:updated $ | NULL | 0 | 0 | TRPF1603.jpg | Pollay, Susan | Morehouse, Joseph | NULL | NULL | NULL | 1 | NULL | NULL | NULL | DDA | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1898 | TR-AT-17-01 | Stone School Sidewalks (Clinton and Stone School Parks Area) | 256000 | NULL | Stone School Road (Clinton and Stone School Park areas) | NULL | NULL | 6 | Improve sidewalk network | Install sidewalks in front of Clinton Park; remove deteriorated asphalt sidewalk on and near Stone School Park frontage and install new concrete walks further from roadway | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 70000 | 1 | 2017 | 3 | 2017 | 186000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Nelson, Jenn | 43038 | 1 | Used Slizewski spreadsheet for figures; showed the combined SAD/General Fund as all general fund 1/11/16 until the breakdown is made. Fall 17:NC | NULL | 0 | 0 | TRAT1701.jpg | Slizewski, Brian | Hutchinson, Nick | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 42.37 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2015-033 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 4 | 2016 | 4 | 2016 | 146064.97 | NULL | NULL | 2016-12-05 | NULL | NULL | 1 | 2019 | 0 | 295060.71 | 2019-04-13 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1.4 | 146064.97 | NULL | 320314.5 | 2018-03-31 | 0 | 60402.49 | 71323.26 | 183170.8 | 0 | 0 | 8467.16 | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1897 | UT-WS-17-02 | Geddes Ave (Huntington to Hickory) Water Stubs | 105550 | NULL | Geddes Ave (Huntington to Hickory) | NULL | NULL | 14 | Provide water main stubs for future main expansions | While reconstructing Geddes Ave (TR-SC-10-09), run water main stubs to adjacent side streets which do not presently have water mains to allow for future expansion without further disruption to Geddes | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 3 | 2016 | 0 | 3 | 2015 | 4 | 2016 | 71000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 42321 | 1 | Added Fall 2015 as was not in budget | NULL | 0 | 0 | UTWS1702.jpg | Rolla, Liz | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 110949 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2065 | UT-WS-18-54 | Ivydale Ave, Ivywood Dr and Peppermill Way Water Main Replacement | 1000000 | NULL | Ivydale Ave, Ivywood Drive and Peppermill Way | NULL | NULL | 14 | Replace aging water main | Replace water main due to break history prior to road resurfacing. Road is driver | NULL | No | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 100000 | 2 | 2024 | 4 | 2024 | 1400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; 2018 cost udpdated | NULL | 0 | 0 | UTWS1854.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 26.14 | 69 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1899 | TR-PF-17-01 | Parking Structure Elevators Capital Maintenance | 615500 | NULL | Parking Structures Maintained by DDA | NULL | NULL | 10 | Ongoing capital maintenance on parking structure elevators | Ongoing capital maintenance on parking structure elevators | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 2 | 2025 | 1498002 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 42989 | 0 | Fall 2015: added to CIP including phases for outer years Fall 2016: added funds in FY23 and dropped DDA as prefix to project name; Fall 2017: updated all $ | NULL | 0 | 0 | TRPF1701.jpg | Pollay, Susan | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | DDA | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Construction | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1883 | UT-WS-16-40 | Seventh (Scio Church to Greenview) Water Main Replacement | 285000 | NULL | Seventh (Scio Church to Greenview) | NULL | NULL | 14 | Replace aging water main | Coordinate with road project; 1100 LF of 12" water main | NULL | Yes | 0 | 29 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 65000 | 2 | 2022 | 4 | 2022 | 835000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Added after prioritization; 2016 - Cost updated and spread; Fall 17: moved to FY20/21 to match street timing shift; 2018 cost updated | NULL | 0 | 0 | UTWS1640.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 34.06 | 49 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1885 | TR-SC-16-20 | Stone School Rd (Eisenhower to I-94) Resurfacing | 150000 | NULL | Stone School Rd (Eisenhower to I-94) | NULL | NULL | 11 | Street Condition | Mill & Overlay; bus turnouts; Parks parking lot; bike lanes | NULL | Yes | 0 | 10 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 1 | 2019 | 35000 | 2 | 2019 | 4 | 2019 | 515000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Split from TR-SC-14-01. Moved from FY18 to FY19; updated schedule/funding. Fall17: NC | NULL | 0 | 0 | TRSC1620.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 60.44 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1886 | MF-CB-16-S1 | Commercial Corridors (Non-DDA) Street Framework Plan | 800000 | NULL | Commercial corridors citywide | NULL | NULL | 1 | Create streets framework plan for commercial corridors similar to the DDA plan | Create streets framework plan for commercial corridors similar to the DDA plan; corridor locations and costs to be more fully scoped in Fall 2015; cost figures are "placeholder" and reflect doing four corridors at a cost similar to the DDA plan | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2021 | 4 | 2022 | 800000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Rampson, Wendy | Gosselin, Deb | 43039 | 0 | Fall 2016: moved out to FY22 and FY23 as no active interest at this point; BL to have input; is a study so changed to an S1 designation. Fall 17: NC Fall 18: NC consider eliminating? | NULL | 0 | 0 | MFCB16S1.jpg | Rampson, Wendy | Pulcipher, Connie | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Planning Commission request | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 9.02 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 2 | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1853 | TR-PF-16-08 | Library Lane Parking Structure Capital Maintenance | 439900 | NULL | 343 S Fifth Avenue | NULL | NULL | 10 | Capital maintenance | Replace sealants; deck coating | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2016 | 2 | 2020 | 2281070 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 43433 | 0 | Fall 2016: Moved funds to FY20 and slightly decreased. Fall 17: NC in cycle; updated outer years per DDA. Fall 18 per DDA | NULL | 0 | 0 | TRPF1608.jpg | Pollay, Susan | Morehouse, Joe | NULL | NULL | NULL | 1 | NULL | NULL | NULL | DDA | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1854 | TR-PF-16-09 | 4th and Washington Parking Structure Capital Maintenance | 261500 | NULL | 123 E Washington | NULL | NULL | 10 | Capital Maintenance | Concrete repairs; waterproofing; deck coating; general repairs | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2018 | 0 | 3 | 2015 | 2 | 2024 | 2756553 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43433 | 0 | Fall 2015: moved to FY16 and FY17 per DDA and revised budget; removed from FY2020; added in FY19 and FY21 so that represents total net shift: Fall 2016: NC; FAll17: added design $ in FY18 and upped FY19 dollars | NULL | 0 | 0 | TRPF1609.jpg | Pollay, Susan | Morehouose, Joe | NULL | NULL | NULL | 1 | NULL | NULL | NULL | DDA | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1855 | TR-PF-16-10 | Forest Ave. Parking Structure Capital Maintenance | 534600 | NULL | NULL | NULL | NULL | 10 | NULL | Stain ceiling; concrete repair and other general repair | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2015 | 2 | 2025 | 3054007 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 43433 | 0 | Fall 2015: Moved FY20 to FY16 and revised budget for remaining years per DDA Fall 2016: NC Fall 17: added money to FY18 and revosed all per DDA. Fall 18: updated per DDA | NULL | 0 | 0 | TRPF1610.jpg | Pollay, Susan | Morehouse, Joe | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1856 | TR-PF-16-11 | Ann Ashley Parking Structure Capital Maintenance Phase 2 | 563625 | NULL | 210 N Ashley | NULL | NULL | 10 | Capital maintenance on aging structure | New sealer; deck coating and sealants; concrete and general repair | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2023 | 1706600 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pollay, Susan | Gosselin, Deb | 43433 | 0 | Fall 2016: added funds in FY19 and FY20 and increased funds in FY21: fall 17: updated costs and added design money in FY18. Fall 18: updated $ | NULL | 0 | 0 | TRPF1611.jpg | Pollay, Susan | Morehouse, Joe | NULL | NULL | NULL | 1 | NULL | NULL | NULL | DDA | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1857 | TR-PF-16-12 | 4th and William Parking Structure Capital Maintenance | 1795500 | NULL | 115 E William | NULL | NULL | 10 | Capital maintenance | Deck coating; beam and joist repairs; spandrel repairs; general repair | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2023 | 2580914 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43433 | 0 | Fall 2016: added funds in FY18, FY19, FY22, and changed FY2021 and dropped "Phase 2" from title: Fall17: updated $ for FY18 and FY19. Fall 18 updated $ | NULL | 0 | 0 | TRPF1612.jpg | Pollay, Susan | Miorehouse, Joe | NULL | NULL | NULL | 1 | NULL | NULL | NULL | DDA | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1881 | MF-CB-16-06 | Allen Creek Greenway Master Plan | 250000 | NULL | Part of Allen Creek watershed | NULL | NULL | 1 | Master Plan for Allen Creek Greenway | Master Plan for Allen Creek Greenway; high citywide community engagement effort; evaluate data from past efforts; determine how City asset groups will be involved in implementation and long-term greenway mgt. (Parks, Stormwater; Alt Trans); cost estimate | NULL | No | 0 | 0 | 5 | NULL | NULL | 1 | 0 | NULL | 3 | 2015 | 1 | 2018 | 300000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Pulcipher, Connie | Gosselin, Deb | 42262 | 1 | Fall 2015: Adjusted budget per Council budget and schedule per CP | NULL | 0 | 0 | MFCB1606.jpg | Bahl, Sumedh | Slotten, Cress | Slotten, Cress | Lawson, Jennifer | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 41.69 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2054 | UT-WS-18-47 | 8th St (Liberty to Jefferson) Water Main | 400000 | NULL | 8th St (Liberty to Jefferson) | NULL | NULL | 14 | Replace aging undersized water main | Replace aging 6" with 8" water main; explore easement to tie dead end to Jefferson Ct. Cost assumes it will be done with as part of road project. | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 42000 | 0 | NULL | 0 | NULL | 558000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; 2018 cost updated and left for now | NULL | 0 | 0 | UTWS1847.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 39.4 | 34 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2031 | MF-SW-18-01 | Northside Methane Collection System Upgrades | 120000 | NULL | Landfill (s of Ellsworth) | NULL | NULL | 15 | Rehabilitate aging system | Evaluate blowers, skid, carbon tank, and electrical system; repair or replace as needed; study completed; need to replace fencing and address other O and M issues | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 3 | 2018 | 8000 | 2 | 2019 | 3 | 2019 | 112000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Warrow, Anne | 43039 | 0 | Fall 2016: New. Fall 17: NC Fall 18: study completed but need to do some O and M; spread in FY19 and FY20 | NULL | 0 | 0 | MFSW1801.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 36.9 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | 1 | 0 | NULL | NULL | 1
2103 | TR-AT-20-02 | Washington Bicycle Boulevard | 250000 | NULL | W Washington (S Revena to S First) | NULL | NULL | 6 | Low stress alternative to biking on Huron | Extensive up front community engagement for conceptual design. DDA coordination; Treeline connection (First St); Coordinate with street project; Evaluate potential utility needs; assumes street diverters, signage, And pavement marking | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 50000 | 2 | 2025 | 2 | 2025 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43434 | 0 | Fall 18: new | NULL | 0 | 0 | TRAT2002.jpg | Cooper, Eli | Redinger, Cynthia | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Transportation Plan Update (2009) | NULL | NULL | NULL | Programmed | Inactive | 60.77 | 11 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 2 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
2105 | TR-AT-20-04 | Bicycle Network Gaps | 100000 | NULL | Citywide | NULL | NULL | 6 | Address bicycle network gaps identified in (Non-Motorized) Transportation Plan | Address bicycle network gaps identified in (Non-Motorized) Transportation Plan | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2022 | 4 | 2022 | 100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Cooper, Eli | 43437 | 0 | Fall 18: new | NULL | 0 | 0 | TRAT2004.jpg | Cooper, Eli | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Ann Arbor Non-Motorized Plan | NULL | NULL | NULL | Programmed | Inactive | 39.93 | 31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1869 | MF-SW-16-02 | Landfill Plume Remediation | 1500000 | NULL | Landfill | NULL | NULL | 15 | Remediate vinyl chloride and 1,4 dioxane | Reduce ongoing monitoring costs required by MDEQ; utilize findings of 2014-2015 pilot study; installation of monitoring and injection wells for in-situ bioremediation; also program ongoing injection costs | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2015 | 2 | 2016 | 73000 | 2 | 2017 | 4 | 2017 | 1427000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Warrow, Anne | 43039 | 1 | Fall 2015: Changed FY16 to pilot study only; moved everything else - pilot cost to FY17. Fall 2016: spread costs to FY17/FY18 and added ongoing injection cost. Fall 17: NC | NULL | 0 | 0 | MFSW1602.jpg | Warrow, Anne | Naud, Matt | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 26.32 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 80358.39 | 2017-09-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2092 | TR-AT-19-04 | Treeline Initial Implementation | 0 | NULL | N Main to Stimson per Treeline Master Plan | NULL | NULL | 6 | As funds are obtained, begin progress toward implementation of Treeline Master Plan | As funds are obtained, begin progress toward implementation of Treeline Master Plan | NULL | NULL | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 3 | 2018 | 2 | 2020 | 110000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Seyfarth, Heather | Gosselin, Deb | 43433 | 0 | Fall 17: added per CH | NULL | 0 | 0 | TRAT1904.jpg | Pulcipher, Connie | Coleman, Kayla | Cooper, Eli | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | Programmed | Design | 74.38 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | 2 | NULL | NULL | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1904 | UT-WS-18-05 | Washington Heights Water Main (East Medical Center south to bend) | 450000 | NULL | Washington Heights (East Medical Center south to Bend) | NULL | NULL | 14 | Re-establish water loop for reliability/redundancy purposes | Construct 16'"main on private portion of Washington Heights to tie together mains on E Medical Center Dr. & E-W public portion of Washington Heights; on UM property; | NULL | No | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 20000 | 2 | 2024 | 4 | 2024 | 430000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43046 | 0 | Fall 2016: new. Fall 17: NC Fall 18: NC | NULL | 0 | 0 | UTWS1805.jpg | Baughman, Troy | Elenbaas, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 27.92 | 66 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1901 | UT-WS-18-02 | Sycamore Place Water Main Replacement | 175000 | NULL | Sycamore Place | NULL | NULL | 14 | Replace and upsize main; improve hydrant coverage | Replace 2" galvanized main with new 8" main; explore looping to main on E Park Place; Coordinate with SSIPE project nearby if needed; lacking hydrant coverage | NULL | NULL | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 25000 | 0 | NULL | 0 | NULL | 150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Elenbaas, Chris | 43046 | 1 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | UTWS1802.jpg | Elenbaas, Chris | Matthews, Paul | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 36.57 | 40 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 409762 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1903 | UT-WS-18-04 | Bucholz Ct Water Main Replacement | 140000 | NULL | Bucholz Ct | NULL | NULL | 14 | Upsize and replace aging main | Upsize .75" & 1" galvanized main; coordinate with paving; constricted ROW; if possible, loop dead-ends together; expand scope to include Willow and Bath if those are resurfaced; evaluate sanitary sewers; consider dir. Drill; evaluate water on Bath stub | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Humphriss, Tesha | Gosselin, Deb | 43389 | 0 | Fall 2016: new; Fall 18 updated $ | NULL | 0 | 0 | UTWS1804.jpg | Baughman, Troy | Elenbaas, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Condition Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 43.96 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 5966.65 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1905 | UT-WS-18-06 | Cedar Bend (Upper) Water Main Replacement | 740000 | NULL | Cedar Bend (Broadway south to end of public road) | NULL | NULL | 14 | Water quality issues and aging main | Water quality filter at 1540 Cedar Bend; determine limit of project; terminus is on UM property; verify ownership limits and ROW; evaluate district to see if dead end can be looped | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 55000 | 2 | 2024 | 4 | 2024 | 685000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Elenbaas, Chris | 42717 | 0 | Fall 2016: new. Fall 18 NC costs not updated | NULL | 0 | 0 | UTWS1806.jpg | Baughman, Troy | Sanford, Larry | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 28.51 | 63 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1906 | MF-CB-18-01 | Housing Commission: 1504-1508 Broadway | 1300000 | NULL | 1504-1508 Broadway | NULL | NULL | 1 | Renovate aging facilities | Renovate 20 existing apartments | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 1 | 2019 | 100000 | 2 | 2019 | 4 | 2019 | 1900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | 42996 | 0 | Fall 2106: new. Fall 17: moved to FY19 as funding not yet obtained. | NULL | 0 | 0 | MFCB1801.jpg | Hall, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1908 | UT-WS-18-08 | Brookwood (White to Packard) Water Main Replacement | 290000 | NULL | Brookwood (White to Packard) | NULL | NULL | 14 | Address water/sanitary sewer conflict and replace aging main | Eliminate conflict between water and sanitary sewer at intersection of Brookwood and White; replace water main on Brookfield; coordinate with paving; consider other nearby streets; consider coordinating with Sycamore project | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 40000 | 2 | 2018 | 4 | 2018 | 250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Elenbaas, Chris | 42676 | 1 | Fall 2016: new | NULL | 0 | 0 | UTWS1808.jpg | Elenbaas, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 30.86 | 54 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 566000 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1909 | UT-WS-18-09 | Platt (S of Oakwood to S of Williamsburg) Water Main Replacement | 1600000 | NULL | Platt Rd (350' S of Oakwood to 500' S of Williamsburg); west end of Oakwood | NULL | NULL | 14 | Replace aging main with frequent break history | Main experiencing frequent breaks; coordinate with paving treatment; Packard/Platt intersection work; remove 3" main in alley at SE corner and relocate leads; consider alternate construction methods and materials; coordinate with SSIPE | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 250000 | 2 | 2022 | 4 | 2022 | 1650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Elenbaas, Chris | 43438 | 0 | Fall 2016: new Fall 18 NC | NULL | 0 | 0 | UTWS1809.jpg | Elenbaas, Chris | Wooden, Dan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.41 | 38 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1911 | UT-ST-18-01 | Edgewood/Snyder SWMM Area Stormwater | 2100000 | NULL | Edgewood and Snyder Area | NULL | NULL | 13 | Flooding issues at intersection. | Preliminary eng. analysis of identified alternatives; define proj. limits; advance design and refine cost on chosen alternative; address both structure & street flooding; Possible AAPS; explore voluntary prop. Acquisition; 2019 - Need to add WM to project | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2018 | 4 | 2021 | 425000 | 2 | 2022 | 4 | 2022 | 1675000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 43395 | 0 | Fall 2016: new. Fall 17: advanced to FY18 design and then spread money across FY19 and FY20 for construction; 2018 no change to cost.. Construction re-programmed to FY 21 and FY 22 by SPU pending project re-prioritization - MGN 7/1/19. | NULL | 0 | 0 | UTST1801.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | SWMM Study | 1 | Stormwater Modeling Recommendations | NULL | NULL | NULL | Active | Inactive | 51.19 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 86626.72 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 1 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1912 | UT-ST-18-02 | Park Place Apartments SWMM Stormwater Improvements | 1000000 | NULL | Park Place Apartment Complex, Pauline Blvd. | NULL | NULL | 13 | Flooding issues near Park Place Apartments; | Evaluate conveyance and detention alternatives from SWMM project. Design and construct chosen alternative; Easements may be needed; Structure flooding; Private property involvement | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 70000 | 2 | 2024 | 4 | 2025 | 930000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43395 | 0 | Fall 2016: new project Fall 17: NC; 2018 no change to cost | NULL | 0 | 0 | UTST1802.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | SWMM Study | 0 | Stormwater Modeling Project | NULL | NULL | NULL | Programmed | Inactive | 45.24 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1913 | UT-ST-18-03 | South University / E. University SWMM Area Stormwater Improvements | 1000000 | NULL | East University and Monroe. | NULL | NULL | 13 | Address stormwater issues in this area. | Evaluate feasibility of constructing storage facilities as recommended in the SWMM project. Good soils; evaluate infiltration; UM loading docks at risk; Green streets upstream; Eval. pipe capacity; UM built storage in Monroe Mall which may reduce need | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 3 | 2019 | 0 | 2 | 2020 | 4 | 2020 | 1460000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43395 | 0 | Fall 2016: new. Fall 17: NC; 2018 updated costs to include Allen Creek work plus new pipe to get City runoff out of UM pipe | NULL | 0 | 0 | UTST1803.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | SWMM Study | 0 | Stormwater Modeling Project | NULL | NULL | NULL | Programmed | Inactive | 42.86 | 17 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1914 | UT-ST-18-04 | Mulholland Ave. SWMM Area Stormwater Improvements | 1900000 | NULL | Murray-Washington branch of Allen Creek between S. Seventh Street and W. Washington. | NULL | NULL | 13 | Address flooding concerns; surcharge through manhole on Mulholland, overland flow between houses and into backyards. | Construct surface storage near Slauson per SWM. Easement/property (AAPS involvement) would be necessary. County drain; reduce flooding at structures; determine is any work is in the floodplain; in 1% floodplain; Possible property acquisition | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 130000 | 2 | 2023 | 4 | 2023 | 1770000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43395 | 0 | Fall 2016: new. Fall 17: NC; 2018 no change to cost | NULL | 0 | 0 | UTST1804.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | SWMM Study | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.24 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1915 | UT-ST-18-05 | Glendale/Charlton SWMM Area Stormwater Storage | 1200000 | NULL | Glendale Drive and Charlton Ave. | NULL | NULL | 13 | Address street flooding | Provide upstream detention as recommended in SWM project. Recommendation only reduces street flooding along Charlton. Street Ponding at low spots along Glendale. Could be addressed by redevelopment of upstream properties | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 85000 | 2 | 2024 | 4 | 2024 | 1115000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43395 | 0 | Fall 2016: new. Fall 17: NC; 2018 no change to cost | NULL | 0 | 0 | UTST1805.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | SWMM Study | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 39.29 | 23 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1918 | UT-ST-18-06 | Parkwood/Pittsfield Village SWMM Area Stormwater Improvements | 500000 | NULL | Open space between buildings between Parkwood Ave and Fernwood Ave. | NULL | NULL | 13 | Address flooding concerns. | Street flooding during large storms and overland flow into open space between buildings between Parkwood and Fernwood. Conveyance improvement and surface storage recommended. Pittsfield Retail upstream has reduced storage needs by recent detention | NULL | NULL | 1 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 35000 | 2 | 2024 | 4 | 2024 | 465000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43395 | 0 | Fall 2016: new. Fall 17: NC; 2018 no change to cost | NULL | 0 | 0 | UTST1806.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | SWMM Study | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.24 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1920 | UT-ST-18-08 | Traver Rd /Barton SWMM Area Stormwater Improvements | 200000 | NULL | Barton Drive south of Traver Road | NULL | NULL | 13 | Address street flooding. | Undersized pipe along Barton & Traver near intersection. Collection system overwhelmed by overland flow coming downhill along Traver. Coordinate with Traver WM project | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 15000 | 2 | 2024 | 4 | 2024 | 185000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43395 | 0 | Fall 2016: new, Fall 17: NC but does nto match Marti's cap. Bdgt. Spreadsheet which shows beyond 24.; 2018 no change to cost but moved to match water project | NULL | 0 | 0 | UTST1808.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | SWMM Study | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 35.79 | 27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1921 | UT-ST-18-09 | Lower Allen Creek SWMM Area Stormwater Improvements | 6000000 | NULL | Allen Creek Watershed | NULL | NULL | 13 | Address flooding concerns in lower Allen Creek watershed | Continue implementation of green street policy, WCWRC SW standards for all redevelopment, and residential rain garden program. Continue Encouragement of UM to comply with WCWRC SW standards. Incremental project. Voluntary prop. acquisition/mitigation | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2021 | 300000 | 2 | 2022 | 4 | 2025 | 3068000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43017 | 0 | Fall 2016: new. Edgewood in district. Fall 17: addded $600K pot to each year; will allocate to projects as identifed; allocated $700K to Hoover-Greene in FY18 and $116K to 5th in 18 and $276 to AC Railroad Berm and 240,600 to 5th in 19 | NULL | 0 | 0 | UTST1809.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | SWMM Study | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 58.96 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2002 | UT-WS-18-31 | WTP: Architectural and Structural Improvements Ph 3 | 1000000 | NULL | Water Treatment System Buildings and Structures | NULL | NULL | 14 | Rehabilitation and repair of Water Treatment System Buildings and Structures | Architectural and structural improvements including items such as concrete, masonry, roofing, painting, etc. This phase will include work at some of the outstations. | NULL | NULL | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | NULL | 1 | NULL | 0 | 3 | 2022 | 2 | 2024 | 1000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43438 | 0 | Fall 2016: New Project. Fall 18 updated | NULL | 0 | 0 | UTWS1831.jpg | Wiczorek, Glen | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 33.86 | 51 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2003 | UT-WS-18-32 | WTP: Metering of Pressure Districts | 1200000 | NULL | Systemwide | NULL | NULL | 14 | Improve data accuracy to monitor non-revenue water loss | Implement recommendations from the Water Audit; Install 6 additional meters in vaults to aid in monitoring water loss | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 3 | NULL | NULL | NULL | 0 | 3 | 2020 | 2 | 2020 | 200000 | 4 | 2021 | 4 | 2022 | 1000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Gosselin, Deb | 43438 | 0 | Fall 2016: New Project. Fall 17: shifted back a year Fall 18: moved back | NULL | 0 | 0 | UTWS1832.jpg | Wiczorek, Glen | Baughman, Troy | Steglitz, Brian | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | Data Accuracy | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 20.59 | 77 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2004 | UT-WS-18-33 | Main St (Huron to RR Bridge) Water Main Replacement | 1800000 | NULL | N Main (Huron to RR bridge) | NULL | NULL | 14 | Replace aging main | Replace water main; MDOT; DDA; Do as part of road project (cost is based on this). | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 0 | 2 | 2022 | 4 | 2022 | 2600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new. Fall 2017: added 5Kmin FY19 to coordinate with MDOT; 2018 cost updated | NULL | 0 | 0 | UTWS1833.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 33.46 | 52 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2030 | UT-ST-20-S1 | Glen Leven Area Stormwater Investigation | 100000 | NULL | Glen Leven Area | NULL | NULL | 13 | Further evaluate SWMM model initial findings | Identified as area of further investigation in SWM; model overpredicting field observations; further flow metering; re-calibrate model if necessary; smoke testing; investigate possible sanitary cross connections | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2021 | 2 | 2022 | 100000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43390 | 0 | Fall 18: new | NULL | 0 | 0 | UTST18S1.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | SWMM | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 12.62 | 41 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
2007 | TR-SC-18-03 | Barton Dr (M14 to Pontiac) Resurfacing | 589000 | NULL | Barton Dr. (M14 to Pontiac) | NULL | NULL | 11 | Pavement condition | Resurfacing; sidewalk gaps; crosswalk near Brede; Barton-Chandler intersection reconfiguration; Look at Pontiac intersection - possible bump outs/pedestrian improvements; sanitary extension at west end; water (Northside to Pontiac); Barton/Starwick inters | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 100000 | 2 | 2019 | 4 | 2020 | 600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Hutchinson, Nick | 43410 | 0 | Fall 2016: new. Fall 17: rounded to 600K; updated cost to $700K | NULL | 0 | 0 | TRSC1803.jpg | Hutchinson, Nick | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 63.74 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 14513.02 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 2 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2008 | TR-SC-18-04 | Greenview (Stadium to Scio Church) Resurfacing | 1290000 | NULL | Greenview - Stadium to Scio Church | NULL | NULL | 11 | Pavement condition | Consider pavement narrowing; coordinate with water project; Consider Avondale intersection reconfiguration; Review major mid block crossing elements at N and S limits | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 80000 | 2 | 2024 | 4 | 2024 | 1210000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2016: new, Fall 17: NC | NULL | 0 | 0 | TRSC1804.jpg | Hutchinson, Nick | Baughman, Troy | Cooper, Eli | Dykman, Dave | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.57 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2009 | TR-SC-18-05 | Jackson (Wagner to MDOT Jurisdiction) Resurfacing | 1235000 | NULL | Jackson (Wagner to MDOT Jurisdiction) | NULL | NULL | 11 | Pavement condition | Resurfacing and CPM; Coordinate with sidewalk gap project; bike lanes; guard rails; coordinate with mid-block crossing project; Evaluate culvert conditions; MDOT and WCRC | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 1 | 2018 | 65000 | 2 | 2018 | 4 | 2018 | 1170000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43433 | 1 | Added as a FY18 project; updated schedule/funding. Fall 17: NC Fall 18; | NULL | 0 | 0 | TRSC1805.jpg | Dykman, Dave | Redinger, Cynthia | Pennington, Kirk | Cooper, Eli | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2010 | TR-SC-18-06 | Scio Church (Maple to 7th) Road Resurfacing | 1870000 | NULL | Scio Church (Maple to 7th) | NULL | NULL | 11 | Pavement condition | Resurfacing; sidewalk gaps; mid block crossings; bike lanes; Stormwater; Potential coordination with Churchill Park basin; address water main with inadequate cover; Look at concrete pavement at Maple intersection | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2017 | 4 | 2017 | 0 | 3 | 2018 | 4 | 2018 | 2122000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Hutchinson, Nick | 43418 | 0 | Fall 2016: new. Fall 17: moved to FY22 | NULL | 0 | 0 | TRSC1806.jpg | Hutchinson, Nick | Cooper, Eli | Lawson, Jennifer | Sheehan, Harry | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 60.66 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 2 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2011 | TR-NS-18-07 | Chalmers Drive Paving | 785000 | NULL | Chalmers Dr. (Washtenaw to Woodcreek) | NULL | NULL | 8 | Paving gravel road | Paving with Complete Streets requirements; sidewalk, curb/gutter, green streets, stormwater improvements, trees; consider extending limits City jurisdictional limit; Developer contribution | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 2 | 2022 | 260000 | 2 | 2022 | 4 | 2023 | 785000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 43033 | 0 | Fall 2016: new. Fall 17: added 260K for design with GF in 19 per CH; did not edit balance of figures or tiiming other than raising total by amount of design. | NULL | 0 | 0 | TRSC1807.jpg | Hupy, Craig | Allen, Jane | Slotten, Cress | Hancock, Jerry | NULL | 1 | Citizen/Property Owner | NULL | NULL | Private Development | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 57.53 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 2 | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2013 | TR-SC-18-09 | North University (State to Fletcher) Resurfacing | 380000 | NULL | N University (State to Fletcher) | NULL | NULL | 11 | Pavement condition | Resurfacing; Mid block crossing; coordinate with UM; DDA; evaluate concrete crosswalks; Allen Creek watershed; consider water lead transfer; proposed Connector route; look at brick pavers in islands; install buffered bike lane. Sanitary Spot Repair; | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 1 | 2021 | 25000 | 2 | 2021 | 2 | 2021 | 355000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2106: new. Fall 17: NC | NULL | 0 | 0 | TRSC1809.jpg | Dykman, Dave | Cooper, Eli | Hancock, Jerry | Baughman, Troy | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 60.11 | 10 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2015 | TR-SC-18-10 | South Industrial (Stimson to Eisenhower) Concrete Pavement Repair | 1600000 | NULL | S Industrial (Stimson to Eisenhower) | NULL | NULL | 11 | Pavement condition | Concrete joint repairs; joint sealing; concrete repairs; diamond grinding; evaluate width for bike lanes; evaluate mid block crossings | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 1 | 2020 | 0 | 2 | 2020 | 4 | 2020 | 1700000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2016: new. Fall 17: cut $600K in FY18 and put in ACPM; REEVALUATE NEXT FALL | NULL | 0 | 0 | TRSC1810.jpg | Dykman, Dave | Cooper, Eli | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 54.07 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 2 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2016 | TR-SC-18-11 | State St (Stimson to Oakbrook) Concrete Repairs | 400000 | NULL | S State St - Stimson to Oakbrook | NULL | NULL | 11 | Concrete Repairs | Concrete pavement repairs; joint sealing; diamond grinding. | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2019 | 0 | 1 | 2019 | 2 | 2019 | 585000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | TRSC1811.jpg | Dykman, Dave | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 38.68 | 39 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2017 | TR-SC-18-12 | Earhart (Geddes to Greenhills) Resurfacing | 915000 | NULL | Earhart Rd (Geddes to Green Hills) | NULL | NULL | 11 | Pavement condition | Resurfacing; evaluate culvert at Earhart Park; evaluate water main; sidewalk gaps; bike lanes | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 0 | 2 | 2022 | 3 | 2022 | 1140000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | TRSC1812.jpg | Dykman, Dave | Cooper, Eli | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 44.61 | 33 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 2 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1924 | TR-AT-18-03 | Jackson | (Wagner to | Park Lake) Sidewalks | 400000 | NULL | Jackson | (Wagner to | Park Lake); south side | NULL | NULL | 6 | Complete sidewalk system | Install approximately 1600 LF of sidewalks to fill existing gaps; Parks frontage on Dolph Nature Area. Difficulty Rating: 3 (Topography, Utility Conflict, Natural Features, Drainage) | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 35000 | 2 | 2020 | 4 | 2020 | 465000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Hutchinson, Nick | 42656 | 0 | Fall 2016: new Project; show 50% Parks for now but need to evaluate policy on County millage for sidewalks | NULL | 0 | 0 | TRAT1803.jpg | Carson, Chris | Kuras, Amy | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 63.99 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1926 | TR-AT-18-05 | Traver Rd (John A Woods to Moore) Sidewalks | 888000 | NULL | Traver (Moore to Barton) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 3700 LF of sidewalks to fill existing gaps; both sides; coordinate with water project UT-WS-16-24 and any associated paving. Difficulty Rating: 2-3 (Topography, Utility Conflict, Natural Features, Possible Lack of ROW) | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 0 | 2 | 2024 | 4 | 2025 | 888000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Hutchinson, Nick | 42656 | 0 | Note: show General fund to fill in gap but need to figure out. ; show using STP and 0062 funds | NULL | 0 | 0 | TRAT1805.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 50.61 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1929 | TR-AT-18-08 | Jewett (S Industrial to Packard) Sidewalks | 552000 | NULL | Jewett (S Industrial to Packard) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 2300 LF of sidewalks to fill existing gaps. Difficulty Rating: mostly 2-3 (some utility Conflicts, Natural Features, Lack of ROW) possible 50' ROW, check pole offsets, landscaping | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 38000 | 2 | 2025 | 4 | 2025 | 514000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2016: new; general fund shown as placeholder. Fall 18 to FY25 | NULL | 0 | 0 | TRAT1808.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 46.01 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1935 | UT-WS-18-11 | Brooks & Mixtwood Water Main Replacement | 1000000 | NULL | Brooks (Mixtwood to Sunset); Mixtwood (Brooks to Red Oak) | NULL | NULL | 14 | Replace and upsize aging mains | Replace 6" main; coordinate with resurfacing project; cost estimate based on work being done with road project | NULL | Yes | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 100000 | 2 | 2023 | 4 | 2023 | 1400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; 2018 cost updated | NULL | 0 | 0 | UTWS1811.jpg | Elenbaas, Chris | Baughman, Troy | Sanford, Larry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 28.51 | 63 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1930 | TR-AT-18-09 | Ellsworth (Railroad to Stone School) Sidewalks | 697500 | NULL | Ellsworth (Railroad to Stone School) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 3100 LF of sidewalks to fill existing gaps. Difficulty Rating: 1&3 (Topography-all, Natural Features, Drainage E of Varsity) E of Varsity can be done w difficulty. Probably will need boardwalk. | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 50000 | 2 | 2025 | 4 | 2025 | 647500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2016: new; used general fund as placeholder; Fall 18; moved to FY25 | NULL | 0 | 0 | TRAT1809.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.04 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1936 | UT-SN-18-01 | Harding (Morton to Wallingford) Sanitary Sewer | 175000 | NULL | Harding (Morton to Wallingford) | NULL | NULL | 12 | Provide proper sanitary sewer service to these parcels; they are currently being serviced by a non-standard utility service configuration | Extend sanitary sewer to unserved parcels; Coordinate w/water project; coordinate w/ possible paving; existing 4" pipe from Wllingford into Harding to be replaced; Cost estimate assumes ext. from Morton & done with road project. | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 0 | 2 | 2024 | 4 | 2024 | 350000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43390 | 0 | Fall 2016: new. Fall 17: NC; 2018 - cost updated | NULL | 0 | 0 | UTSN1801.jpg | Heatley, Alison | Baughman, Troy | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 39.82 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
2181 | UT-ST-20-04 | Apple Way Stormwater Improvements | 800000 | NULL | Apple Way | NULL | NULL | 13 | Drainage Issues | Coordinate with water main project. Driveway culverts property owner responsibility; cost estimate based on installing 1000' of storm sewer; still need to evaulate and determine what the solution is tho. | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 50000 | 2 | 2025 | 4 | 2025 | 750000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43390 | 0 | 2018 no change to cost | NULL | 0 | 0 | UTST2004.jpg | Lawson, Jennifer | Baughman, Troy | Slizewski, Brian | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 32.06 | 32 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1931 | TR-AT-18-10 | Nixon (Westbury Ct to Traver Blvd) Sidewalks | 231250 | NULL | Nixon (Westbury Ct to Traver Blvd) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 925 LF of sidewalks to fill existing gaps; also on Traver Blvd to Logan. Difficulty Rating: 3 (Natural Features, Drainage, Investigate ROW) | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 17000 | 2 | 2020 | 4 | 2020 | 214250 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 43437 | 0 | Fall 2016: New; Deb spread costs determined by Nick; May 2018, marked as eliminated as these will be rolled into the Nixon corridor improvements. Fall 18: restored as citizens don't want to wait for big project | NULL | 0 | 0 | TRAT1810.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.65 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1932 | TR-AT-18-11 | Virginia and Fair Area Sidewalks | 192500 | NULL | Virginia (Fair to W Liberty) and Fair (Virginia to Glendale Cir.) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 1100 LF of sidewalks to fill existing gaps; Parks involvement at Virginia Park; also consider small gaps on Glendale Cir S of Fair (about 360') or do those from annual allotment. Difficulty Rating: 1 (Nat features on Fair) | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 0 | 2 | 2025 | 4 | 2025 | 192500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2106: new. Fall 18: to FY25 and showed street as match | NULL | 0 | 0 | TRAT1811.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization Project | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 37.89 | 32 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2229 | UT-ST-20-08 | Nixon (Bluett to Dhu Varren) Phase 2 Stormwater Improvements | 1830000 | NULL | Nixon (Bluett to Dhu Varren) | NULL | NULL | 13 | Provide Green Steets stormwater improvements | Provide Green Steets stormwater improvements | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2026 | 4 | 2026 | 1830000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | NULL | NULL | 0 | NULL | NULL | 0 | 0 | UTST2008.jpg | Wall, Chris | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1943 | UT-WS-18-13 | Harding (Morton to Wallingford) Water Main Construction | 150000 | NULL | Harding (Morton to Wallingford) | NULL | NULL | 14 | Provide water main | Construct 8" main and remove non-standard mains; coordinate with sanitary project UT-SN-18-01 and possible paving; loop main; cost est. based on being done with road project | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 20000 | 2 | 2024 | 2 | 2024 | 280000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; 2018 cost updated | NULL | 0 | 0 | UTWS1813.jpg | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.35 | 24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1944 | UT-WS-18-12 | Horman Ct Water Main Replacement | 165000 | NULL | Horman Ct | NULL | NULL | 14 | Replace undersized main | Coordinate with sanitary project UT-SN-18-02; upsize main; loop main | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 30000 | 2 | 2018 | 2 | 2018 | 135000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Elenbaas, Chris | 42676 | 1 | Fall 2106: new | NULL | 0 | 0 | UTWS1812.jpg | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 40.38 | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 7302.51 | 2017-09-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1945 | UT-WS-18-14 | Water Main Annexation Extensions | 0 | NULL | TBD | NULL | NULL | 14 | Provide Water Service as requested by annexed parcel owners | Provide Water Service as requested by annexed parcel owners; no funds allocated until needs are known more clearly | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43046 | 0 | Possible locations: Parkcrest; Hampstead Ct. Fall 17: NC | NULL | 0 | 0 | UTWS1814.jpg | Coleman, Kayla | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 37.42 | 40 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1946 | UT-SN-18-07 | Pittsfield Village Sanitary Sewers | 2850000 | NULL | Pittsfield Village Subdivision | NULL | NULL | 12 | Replace aging sanitary sewers | Replace sanitary sewers based on condition analysis; will probably need to phase the project; coordinate with water and paving projects; consider stormwater issues if reconstruction | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 250000 | 2 | 2024 | 4 | 2025 | 2600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Elenbaas, Chris | 42716 | 0 | Fall 2016: new; no companion water yet created so show beyond 23 | NULL | 0 | 0 | UTSN1807.jpg | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.88 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1947 | TR-AT-18-12 | Newport (Sunset to Downup Circle) Sidewalks | 950000 | NULL | Newport (Sunset to Downup Cir) East Side | NULL | NULL | 6 | Complete sidewalk system | Install approximately 1200 LF of sidewalks to fill existing gaps; MDOT involvement for highway crossing; Park involvement for Bird Hills frontage. Difficulty Rating: 3 (Topography, Utility Conflict, Natural Features, some lack of ROW) | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 0 | 2 | 2024 | 4 | 2024 | 428000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2016: new; used general fund as placeholder. Fall 18, shortened to start at Sunset and reduced costs; show County millage as tentative | NULL | 0 | 0 | TRAT1812.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.65 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1953 | TR-BR-18-01 | Fuller Rd/Maiden Lane Bridge Painting | 1847000 | NULL | Fuller and Maiden Lane Bridges | NULL | NULL | 7 | Re-paint bridges and perform related rehabilitation work. | Paint bridges; coordinate work with Island Drive bridge if possible; coordinate and perform with Fuller Road/Maiden Lane/E. Medical Center Drive intersection work; possible need to widen | NULL | Yes | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 4 | 2025 | 155000 | 2 | 2027 | 4 | 2027 | 1654000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Gosselin, Deb | 43432 | 0 | Fall 2016: added; completes work not finished with TR-BR-10-06; edited schedule and funds to match 0062 spreadsheet or now pending outside funding. Fall 18: shifted to beyond 25 | NULL | 0 | 0 | TRBR1801.jpg | Nearing, Mike | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | Bridge Inspection Report | 0 | NULL | NULL | NULL | NULL | Active | Planning | 73.09 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 37867.79 | 2019-03-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2218 | UT-WS-20-21 | William Street Water Main Consolidation | 600000 | NULL | William (between Ashley and Main; and 5th to State) | NULL | NULL | 14 | Water main consolidation | Coordinate with DDA project. Abandon small aging main and transfer leads to existing larger (12") main. 1967 main in William between Division and State, but exploratory excavation was performed and pipe is good | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2019 | 3 | 20 | 0 | 2 | 2019 | 2 | 2019 | 600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Baughman, Troy | 43388 | 1 | Fall 18 new but will be complete before FY20 in theory; Spring 2019:had to adjust scope based on bids | NULL | 0 | 0 | UTWS2021.jpg | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 213008.89 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1948 | TR-AT-18-13 | Sunset (Brooks to Newport) Sidewalks | 528000 | NULL | Sunset (Brooks to Newport) North side | NULL | NULL | 6 | Complete sidewalk system | Install approximately 2200 LF of sidewalks to fill existing gaps. Difficulty Rating: 2-3 (Topography, Natural Features) | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 35000 | 2 | 2024 | 4 | 2024 | 493000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Hutchinson, Nick | 42656 | 0 | Fall 18: NC but could become an FY21 or FY22 county millage project if approved | NULL | 0 | 0 | TRAT1813.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | Sidewalk Gap Prioritization | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 41.41 | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1949 | TR-AT-18-14 | Brooks (Mixtwood to Sunset) Sidewalks | 495000 | NULL | Brooks (Mixtwood to Sunset) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 2200 LF of sidewalks to fill existing gaps; Coordinate with water and paving. Difficulty Rating: 1 (E side) and 2 (W side) (Natural Features). Consider Bydding gaps as well | NULL | Yes | 1 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 0 | 2 | 2023 | 4 | 2023 | 495000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gray, Kerry | 43434 | 0 | Fall 2016: new; show general fund as placeholder. Fall 18: showed county millage as tentative funding source | NULL | 0 | 0 | TRAT1814.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 55.94 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 0 | NULL | NULL | 1
1950 | TR-AT-18-15 | Riverwood Nature Area Sidewalks | 270000 | NULL | Riverwood Nature Area | NULL | NULL | 6 | Complete sidewalk system | Install approximately 1200 LF of sidewalks to fill existing gaps; Parks. Difficulty Rating: 2 (Topography, Utility Conflict, Natural Features) | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2024 | 4 | 2024 | 0 | 2 | 2025 | 4 | 2025 | 270000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2016: show all as Parks. Fall 18 to FY25 | NULL | 0 | 0 | TRAT1815.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 41.41 | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1951 | TR-AT-18-16 | Dhu Varren (Omlesaad to west end Nixon Farms) Sidewalks | 630000 | NULL | Dhu Varren (Omlesaad to west end Nixon Farms) | NULL | NULL | 6 | Complete sidewalk system | Install approx. 2515 LF of sidewalks to fill existing gaps; Small park frontage. Difficulty Rating: 1-4 (Topography, some Utility Conflict, Natural Features, Drainage, investigate ROW; segment of 4 rating significant topography/nat. features challenge | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2017 | 4 | 2018 | 83000 | 2 | 2019 | 4 | 2019 | 625000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43434 | 0 | Fall 2016: new; SAD funds to be allocated when known. Fall 18: parks = abt 318 LF; show use of STP for construction + CE. | NULL | 0 | 0 | TRAT1816.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 48.65 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | 83000 | 2018-05-01 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 83848 | 2019-01-05 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1952 | TR-AT-18-17 | Green | (Gettsyburg to | Burbank) Sidewalks | 271250 | NULL | Green | (Gettsyburg to | Burbank) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 1550 LF of sidewalks to fill existing gaps; all on Chapel Hill condominiums. Late addition not rated but looks standard with a few trees. Special assessment | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 270500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Hutchinson, Nick | 42656 | 1 | Fall 2016: new project; SAD shown just a zero for now but will be most | NULL | 0 | 0 | TRAT1817.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 42.37 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1954 | TR-BR-18-02 | Huron Parkway Bridge Repairs | 200000 | NULL | Huron Parkway Bridge over Huron River and railroad | NULL | NULL | 7 | Repair bridge | Concrete patching on piers; work around cliff swallow nesting season; after August 1 construction for nesting season accommodation; convey staging plans to UM; | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 30000 | 2 | 2020 | 4 | 2020 | 170000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Nearing, Mike | Nearing, Mike | 43432 | 0 | Fall 2016: New. Fall 18: moved up to 20-21 | NULL | 0 | 0 | TRBR1802.jpg | Nearing, Mike | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | Bridge Inspection | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 67.52 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
1973 | TR-OT-18-04 | Traffic Observation Expansion | 200000 | NULL | Major traffic corridors | NULL | NULL | 9 | Identify real-time traffic needs and verify effectiveness of changes | Purchase 20 traffic observation cameras; key corridors include Plymouth (3), Main (2), Fuller/Glen (3), Stadium (3), Packard (1), Eisenhower (5), Ellsworth (1), Scio Church (1), Maple (1); EMC (3-UM to pay, but not in CMAQ app) | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 2 | 2019 | 230000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Liu, Luke | 42716 | 1 | Fall 2106: new. Fall 17: moved FY18 to FY19 | NULL | 0 | 0 | TROT1804.jpg | Liu, Luke | Matthews, Paul | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 45.79 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1955 | TR-AT-18-18 | Fuller Ct (Fuller to 2250 Fuller Ct) Sidewalks | 315000 | NULL | Fuller Ct (Fuller to 2250 Fuller Ct) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 1400 LF of sidewalks to fill existing gaps; some UM frontage. Difficulty Rating: 1&3 (UM frontage has Topography, Natural Features) | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 25000 | 2 | 2020 | 4 | 2020 | 325000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 43433 | 0 | Fall 2016: new; Fall 18: STP funds. Fall 18: updated $ and use STP and 0062 | NULL | 0 | 0 | TRAT1818.jpg | TR-AT-18-18 | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 50.29 | 17 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 3 | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1965 | UT-ST-18-15 | Arboretum Culverts and Headwalls (School Girls Glen) | 250000 | NULL | Downstream end of School Girls Glen in the Arb | NULL | NULL | 13 | Reconstruct existing structures | Reconstruct existing culverts and headwall at Nichols Dr.;; evaluate erosion at sanitary aerial crossing; UM coordination; MDEQ permit | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 30000 | 2 | 2020 | 2 | 2020 | 270000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43012 | 0 | Fall 2016: new. Fall17: increased budget to $300K per capital budget but left in 2020 versus FY18 as shown in cap. Bdgt. | NULL | 0 | 0 | UTST1815.jpg | Nearing, Mike | Elenbaas, Chris | Lawson, Jennifer | Robinson, Molly | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 37.62 | 25 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1933 | UT-WS-18-10 | Summit (Broadway to Main) Water Main Replacement | 1400000 | NULL | Summit (Broadway to Main) | NULL | NULL | 14 | Replace aging mains | Replace aging gravity main; some preliminary survey work already completed; consider also replacing pressure main and local main; consider alt const. methods/materials; cost est. assumes replacing all 3 mains (16,16, 6) | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 4 | 2025 | 100000 | 2 | 2026 | 4 | 2026 | 1300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43439 | 0 | Fall 2106: new. Fall 17: NC Fall 18: costs not updated, moved to FY26-27 | NULL | 0 | 0 | UTWS1810.jpg | Slizewski, Brian | Baughman, Troy | Wooden, Dan | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 25.15 | 71 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1937 | UT-SN-18-02 | Horman Ct Sanitary | 500000 | NULL | Horman Ct and S Forest (Horman to Minerva) | NULL | NULL | 12 | Replace aging undersized pipe | Increase slope; coordinate w/water project; currently maintenance issue; replace piep on Forest as needed and coordinate with DTE duct bank work there | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 35000 | 2 | 2018 | 4 | 2018 | 640000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43004 | 1 | Fall 17: Increased cost 35% to reflect work on Forest. | NULL | 0 | 0 | UTSN1802.jpg | Elenbaas, Chris | Matthews, Paul | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 39.01 | 17 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 300000 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1938 | UT-SN-18-03 | Sanitary Sewer Annexation Extensions | 0 | NULL | TBD | NULL | NULL | 12 | Extend sanitary sewer as requested to service annexed parcels | Extend sanitary sewer as requested to service annexed parcels; no costs included until parameters better known but recording need | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 42716 | 0 | Fall 2106: new Possible locations: Parkcrest; Bird; Hampstead Ct; Newport N of Warrington; no costs added until process moves along further | NULL | 0 | 0 | UTSN1803.jpg | Baughman, Troy | Coleman, Kayla | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 35.02 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
1940 | UT-SN-18-05 | Medical Center Drive Sanitary Manhole Access | 880000 | NULL | Medical Center Drive from Glen to S of Helipad | NULL | NULL | 12 | Gain access to buried manholes through vertical extension; between found MHs 71-68806 and 71-71813 | Gain access to buried manholes through vertical extension; determine condition of trunkline; Connector impacts; U of M involvement | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2021 | 4 | 2021 | 80000 | 0 | NULL | 0 | NULL | 800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 42716 | 0 | Fall 2016: new | NULL | 0 | 0 | UTSN1805.jpg | Elenbaas, Chris | Baughman, Troy | Nearing, Mike | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.01 | 14 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | NULL | NULL | 0
1941 | UT-SN-18-S1 | WWTP: Area Odor Study | 200000 | NULL | 1/2 mile radius of WWTP; Palmer Dr. | NULL | NULL | 12 | Address citizen odor complaints | WCC, St Joes Hospital, residential areas near WWTP; Arboretum by UM Hospitsal systematically investigate potential sources of odors | NULL | No | 0 | 0 | 4 | NULL | NULL | 1 | 0 | NULL | 4 | 2017 | 1 | 2018 | 200000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Englert, Chris | Englet, Chris | 42717 | 0 | Fall 2016: new STUDY | NULL | 0 | 0 | UTSN18S1.jpg | Englert, Chris | Baughman, Troy | NULL | NULL | NULL | 1 | Citizen/Property Owner | University of Michigan | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 26.98 | 33 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 1
1992 | UT-WS-18-21 | Ann (Observatory to Zina Pitcher) Water Main Relocation | 1000000 | NULL | Ann (Observatory to Zina Pitcher); connect to new pipe in Observatory | NULL | NULL | 14 | Relocate transmission main across Palmer Field | Evaluate removing Palmer Field main from city system; upsize existing main in Ann with 16"; connect to new pipe in Observatory; coordinate w U of M; approx. 900 LF | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 70000 | 2 | 2024 | 4 | 2024 | 930000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; 2018 cost verified and NC | NULL | 0 | 0 | UTWS1821.jpg | Baughman, Troy | Kotlyar, Igor | Sanford, Larry | Matthews, Paul | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 37.03 | 41 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1989 | UT-WS-18-18 | WTP: Barton Pump Station 20" Raw Water Suction Piping Replacement | 2400000 | NULL | Barton Pump Station Piping (Barton Pond to Pump Station) | NULL | NULL | 14 | Increase raw water flow to pump station and address aging pipe | Upsize 20" suction pipe to increase flow to Barton Pump Station; has been identified as a critical weak link in system as current size can restrict raw water flow to the WTP. Valve replacement is also part of this project. | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2018 | 440000 | 1 | 2023 | 4 | 2024 | 9000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Gosselin, Deb | 43028 | 0 | Fall 2016: New Project.Fall 17: rolled UT-WS-18-20 into this project,upped total $ to 9M and parked in FY23 until next fall. Fall 18 updated per WTP | NULL | 0 | 0 | UTWS1818.jpg | Wiczorek, Glen | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Condition Analysis | Customer Level of Service | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 54.85 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 401175 | 2018-05-22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1990 | UT-WS-18-19 | WTP: Barton Pump Station Raw Water Transmission Pipe Repairs | 1750000 | NULL | Barton Pump Station (From Pump Station to WTP) | NULL | NULL | 14 | Address aging infrastructure and leaks in piping | Both the original 24" cast iron piping sytem & the newer 42" conc. prestressed pipe require condition assessment . The 24" pipe has experienced leaks and full or partial replacement is anticipated. Valves are also needed for isolation.Size to be evaluated | NULL | Yes | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 2 | 2021 | 250000 | 4 | 2021 | 4 | 2023 | 1500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43437 | 0 | Fall 2016: New project. Fall 18 updated per WTP | NULL | 0 | 0 | UTWS1819.jpg | Wiczorek, Glen | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 54.85 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2006 | TR-SC-18-02 | Springwater Phase IV Road Reconstruction | 998000 | NULL | McComb (all), Sharon (Cardinal to Springbrook); Cardinal (resurface only) | NULL | NULL | 11 | Pavement condition | Reconstruct roads in coordination with water, sanitary (lining), and stormwater projects in the subdivision. Streets include all or portions of Cardinal and McComb, and Sharon (Cardinal to Springbrook). Consider sidewalk gaps. Public art enhanced. | NULL | Yes | 1 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 69000 | 2 | 2024 | 4 | 2024 | 929000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43038 | 0 | Fall 2016: new; used Anne's figures. Fall 17: NC | NULL | 0 | 0 | TRSC1802.jpg | Warrow, Anne | Allen, Jane | Sheehan, Harry | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 35.02 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | 2 | 32500 | 0
1994 | UT-WS-18-23 | Water Main Distribution System Valve Replacements | 1000000 | NULL | Systemwide | NULL | NULL | 14 | Evaluate and replace aging distribution system valves | Replace aging valves as identified; UM and private development coordination; create prioritization system | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2024 | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43046 | 0 | Fall 2016: new: estimate #.75M but only show what is programmed. Fall 17: moved all FY18 money to Plymouth-Gren for valve replacements there | NULL | 0 | 0 | UTWS1823.jpg | Matthews, Paul | Elenbaas, Chris | Sanford, Larry | Wooden, Dan | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.95 | 23 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1995 | UT-WS-18-24 | Creal Cres., Creal Ct., Helen St., & Argyle Cres. Water Main Replacement | 1600000 | NULL | Creal Cres. and Argyle Cres. Area | NULL | NULL | 14 | Replace aging watermain | Replace aging water main due to breaks. Creal Ct has water quality issues. Cost estimate is assuming this work will be done with road project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 175000 | 2 | 2024 | 4 | 2024 | 2325000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2106: new; 2018 cost updated | NULL | 0 | 0 | UTWS1824.jpg | Baughman, Troy | Sanford, Larry | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 28.12 | 65 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1996 | UT-WS-18-25 | Chaucer, Ascot, & Wembley Water Main Replacement | 1200000 | NULL | Chaucer Dr. (Scio Church to Ascot); Ascot; Wembley Ct | NULL | NULL | 14 | Replace aging water mains | Coordinate with any stormwater efforts; Chaucer Ct was not included since this is was built in the 1970s (may want to re-evaluate during design phase); Cost estimate based on work being done with road project | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 125000 | 2 | 2022 | 4 | 2022 | 1675000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; 2018 cost updated and oushed back as roads not proposed | NULL | 0 | 0 | UTWS1825.jpg | Baughman, Troy | Lawson, Jennifer | Matthews, Paul | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 30.49 | 59 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1997 | UT-WS-18-26 | Page Ave (King George south to end) Water Main Replacement | 300000 | NULL | Page Ave (King George south to end) | NULL | NULL | 14 | Upsize main and create loop for future school project | Upsize 8" main to 12" when road is resurfaced (cost is based on that assumption) ; will ultimately connect to a 12" water main on abutting school property; school project is currently on hold; confirm with AAPS prior to moving fwd. with this project; | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 30000 | 3 | 2020 | 4 | 2020 | 370000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new. Fall 17: shifted to FY20-21; 2018 cost updated | NULL | 0 | 0 | UTWS1826.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.96 | 27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1998 | UT-WS-18-27 | Northside STEAM to Barton Water Main Connection | 500000 | NULL | Northside STEAM to Barton | NULL | NULL | 14 | Create 12" water loop | Upsize existing mains for continuation of 12" loop recently installed by AAPS; Assumes being done as part of rd proj; cost based on upsizing Peach St & John Woods out to Traver. (the mains north of the school were recently replaced with 8"); not urgent | NULL | NULL | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 50000 | 2 | 2024 | 4 | 2024 | 650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; check cost next time as may or may not include Hiawatha and Barton to get loop to Pontiac. Fall 17: NC; 2018 cost updated | NULL | 0 | 0 | UTWS1827.jpg | Baughman, Troy | Sanford, Larry | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.96 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1999 | UT-WS-18-28 | Stadium Service Drive Water Main Replacement | 700000 | NULL | Stadium Service Drive | NULL | NULL | 14 | Replace and loop aging water main. | Replace main due to break history; need to loop out to W. Stadium | NULL | Yes | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 50000 | 2 | 2024 | 4 | 2024 | 650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; Fall 17: NC; 2018 cost confirmed and NC | NULL | 0 | 0 | UTWS1828.jpg | Baughman, Troy | Wooden, Dan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 52.87 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2000 | UT-WS-18-29 | Soule (Liberty to Eberwhite School) Water Main Replacement | 750000 | NULL | Soule (Liberty to Eberwhite School) | NULL | NULL | 14 | Upsize water main for increased fire flow capacity. | Upsize water main in Soule between Liberty and Eberwhite School to complete a 12" loop which was recently installed at the school. Perform as part of road project (cost estimate is based on this). | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 70000 | 2 | 2024 | 4 | 2024 | 930000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; 2018 cost updated | NULL | 0 | 0 | UTWS1829.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.96 | 27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2001 | UT-WS-18-30 | Dams: Superior Dam Gate Painting | 160000 | NULL | Superior Dam | NULL | NULL | 14 | Capital maintenance per regulatory requirements (FERC) | Complete painting of the Superior Dam Tainter Gate (both wet and dry sides); consider including painting of stop logs and seal repairs. | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2020 | 1 | 2020 | 50000 | 3 | 2021 | 4 | 2020 | 140000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Gosselin, Deb | 43438 | 0 | Fall 2016: New Project.100% general fund. Fall 17: slight fund shift | NULL | 0 | 0 | UTWS1830.jpg | Wiczorek, Glen | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | FERC | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.81 | 37 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2018 | TR-SC-18-13 | Earhart (Greenhills to US23) Resurfacing | 1735000 | NULL | Earhart Rd (Greenhills to US23) | NULL | NULL | 11 | Pavement condition | Resurfacing; evaluate culvert at Earhart Park; evaluate water main; sidewalk gaps; Road diet, buffered bike lanes | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 1 | 2022 | 105000 | 2 | 2023 | 3 | 2023 | 1625000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | TRSC1813.jpg | Dykman, Dave | Cooper, Eli | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 44.61 | 33 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2019 | TR-SC-18-14 | Platt (Washtenaw to Huron Pkwy) Resurfacing | 605000 | NULL | Platt Rd (Washtenaw to Huron Pkwy) | NULL | NULL | 11 | Pavement condition | Capital preventive maintenance initially; monitor development on County site; evaluate condition of box culvert; bike lanes; sidewalk gaps; evaluate water mains; coordinate with WCWRC | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 0 | 2 | 2019 | 4 | 2019 | 515000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2016: new. Fall 17: switched to an FY19 CPM project | NULL | 0 | 0 | TRSC1814.jpg | Dykman, Dave | Pennington, Kirk | Cooper, Eli | Baughman, Troy | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 53.52 | 21 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2020 | TR-SC-18-15 | Platt (Huron Pkwy to Packard) Resurfacing | 1220000 | NULL | Platt Rd (Huron Pkwy to Packard) | NULL | NULL | 11 | Pavement condition | Resurfacing; Evaluate pedestrian safety rail at drain crossing; Coordinate with WCWRC; coordinate with water project S of Oakwood; Evaluate sanitary lining | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 0 | 2 | 2022 | 4 | 2022 | 1300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | TRSC1815.jpg | Dykman, Dave | Elenbaas, Chris | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.57 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2021 | TR-SC-18-16 | South University (State to E University) Resurfacing | 430000 | NULL | S University (State to E University) | NULL | NULL | 11 | Pavement condition | Resurfacing; coordinate with UM tunnel projectt, Allen Creek Watershed storage improvements, and consolidation of two 12" water mains and elimination of 6"; Coordinate with DDA; also do to Church | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 1 | 2018 | 0 | 2 | 2018 | 3 | 2018 | 975000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43430 | 0 | Fall 2016: new.Fall 17: moved to FY20 BUT NEED TO COORDINATE WITH UM | NULL | 0 | 0 | TRSC1816.jpg | Dykman, Dave | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 52.97 | 23 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2018-036 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 53660.04 | 2019-06-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2022 | TR-SC-18-17 | Brooks (Miller to Sunset) Resurfacing | 1230000 | NULL | Brooks St - Miller to Sunset | NULL | NULL | 11 | Pavement condition | Resurfacing; coordinate with water and sidewalk gap projects (N of Mixtwood); Evaluate sanitary; consider extending limits on Mixtwood to Red Oak; Allen Creek watershed; Replace speed humps | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 1 | 2023 | 75000 | 1 | 2023 | 3 | 2023 | 1155000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 17: NC | NULL | 0 | 0 | TRSC1817.jpg | Dykman, Dave | Elenbaas, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.57 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2023 | TR-SC-18-18 | Huron Pkwy/Tuebingen (Nixon to Traver) Resurfacing | 1210000 | NULL | Huron Pkwy/Tuebingen - Nixon to Traver | NULL | NULL | 11 | Pavement condition | Resurfacing; coordinate with sidewalk gap project; Evaluate creek crossing on Tuebingen; Evaluate responsibility of pedestrian tunnel on Tuebingen | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 75000 | 2 | 2022 | 3 | 2022 | 1135000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43038 | 0 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | TRSC1818.jpg | Dykman, Dave | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 52.53 | 24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 2 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
2025 | UT-WS-18-34 | Hatcher Cres., Saunders Cres., & Cooley Ave Water Main Replacement | 2000000 | NULL | Hatcher Cres and Saunders Cres Area | NULL | NULL | 14 | Replacing aging water main. | Replace mains due to break history. This will be the 2nd phase of the neighborhood project. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 220000 | 2 | 2025 | 4 | 2025 | 2880000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2106: new project.; 2018 cost updated | NULL | 0 | 0 | UTWS1834.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 28.12 | 65 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2026 | UT-WS-18-35 | Summit (Daniel to Main) Water Main Replacement | 1500000 | NULL | Summit (Daniel to Main) | NULL | NULL | 14 | Replace aging water mains. | Replace aging water mains. Gravity appears to be worst, but other main is same vintage. Both high PAN scores. Consider alternative construction material/methods; Crossing of Main St/RR/Allens Ck. Some survey work/prelim design has been done. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 105000 | 2 | 2021 | 4 | 2021 | 1511000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new. Fall 17: NC; 2018 cost confirmed | NULL | 0 | 0 | UTWS1835.jpg | Baughman, Troy | Wooden, Dan | Slizewski, Brian | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 31.09 | 57 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2027 | UT-ST-18-19 | Tuebingen Culvert Rehabilitation | 250000 | NULL | Culvert under Tuebingen at Traver Blvd | NULL | NULL | 13 | Rehabilitate aging culvert | Evaluate culvert; Review Traver Lakes legal agreements; coordinate with road project; MDEQ permit; Evaluate sanitary main above culvert | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 1 | 2022 | 40000 | 2 | 2022 | 2 | 2022 | 210000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43045 | 0 | Fall 2016: new project. Fall 1&: NC Fall 18: | NULL | 0 | 0 | UTST1819.jpg | Goebel, Steve | Elenbaas, Chris | Lawson, Jennifer | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 23.09 | 38 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
2028 | UT-ST-18-17 | 1250 N Main Area Storm Main Relocation | 900000 | NULL | 1250 N Main Area | NULL | NULL | 13 | Relocate failing storm sewer from underneath buildings | Relocate from MH in Bluffs Park through 1250/1251 N Main to RR; Eliminate sanitary conflict; possible RR involvement; Coordinate with private property owners; Evaluate sizing | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | NULL | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 70000 | 2 | 2021 | 4 | 2021 | 830000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | TR-BR-10-06 | Gosselin, Deb | 43423 | 0 | Fall 2016: new; CE cost figure. Fall 17: NC | NULL | 0 | 0 | utst1817.jpg | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 51.73 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | ut-sn-16-08 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2029 | UT-ST-18-18 | Traver Creek Tributary Streambank Stabilization | 1000000 | NULL | Foxfire South Park from RR to Omlesaad ROW extension | NULL | NULL | 13 | Address streambank erosion | Streambank stabilization; parks involvement; MDEQ permit; County Drain; possible coordination with [Placid Way] culvert project | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 75000 | 2 | 2024 | 4 | 2024 | 925000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hancock, Jerry | Gosselin, Deb | 43424 | 0 | Fall 2106: new; number needs much more review Fall 17: NC Fall 18: funded in sigle year as SRF by County | NULL | 0 | 0 | UTST1818.jpg | Sheehan, Harry | Lawson, Jennifer | Borneman, Dave | Hancock, Jerry | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 33.73 | 31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1956 | TR-AT-18-19 | Oakwood Sidewalks | 507500 | NULL | Oakwood | NULL | NULL | 6 | Sidewalk Gap Prioritization | Sidewalks along Oakwood - Platt to existing; provide connectivity to Pittsfield Elementary; 2900 ft. This stretch not rated but looks standard with some trees. | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 35000 | 2 | 2025 | 4 | 2025 | 472500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2016: new; used general fund as placeholder Fall 18: to FY25 | NULL | 0 | 0 | TRAT1819.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.21 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1957 | TR-AT-18-20 | Allmendinger Park Area Sidewalks | 400000 | NULL | Allmendinger Park Area (Edgewood/Potter/Hutchins) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 2000 LF of sidewalks to fill existing gaps; consider coordination other infrastructure projects in the area (Stadium west of Main, stormwater projects). Difficulty Rating: 1-2 (Topography on S edge, Natural Features) | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2024 | 4 | 2024 | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Hutchinson, Nick | 42656 | 0 | Fall 2016: New; put in 2024 as placeholder year and set Park funds as placeholder. Fall 18: NC | NULL | 0 | 0 | TRAT1820.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 37.89 | 32 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1958 | TR-AT-18-21 | Snyder (7th to Edgewood) Sidewalks | 400000 | NULL | Snyder (7th to Edgewood) | NULL | NULL | 6 | Complete sidewalk system | Install approximately 2000 LF of sidewalks to fill existing gaps; may need to coordinate with stormwater projects in area. Difficulty Rating: 1-2 (some Topography, Util. Conflict, Nat Features), 3 E of Prescott (Util. Conflict, Nat Features, ROW) | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 0 | 2 | 2025 | 4 | 2025 | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 2106: new; used general fund as placeholder. Fall 18 to FY25 | NULL | 0 | 0 | TRAT1821.jpg | Carson, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 37.89 | 32 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1959 | TR-AT-18-25 | Annual Sidewalk Gap Projects | 650000 | NULL | TBD | NULL | NULL | 6 | Complete sidewalk system | Annual allocation to address filling of smaller sidewalk gaps under an annual contract or similar means: special assessment where applicable: large projects will be identified as standalone projects; also creates a placeholder to allow for flexibility: | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 2 | 2025 | 933000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 42697 | 0 | Fall 2016: added will take money from this pot as needed when projects identified. For FY18, using funds on Hiscock gap. FY19" possible Safe Routes to STEAM. Fall 17: directed to Northside STEAM. Fall 18: updated per Nick but edited by Deb | NULL | 0 | 0 | TRAT1825.jpg | Hutchinson, Nick | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | Sidewalk Gap Prioritization | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.34 | 23 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
2045 | TR-PF-18-01 | Parking Equipment | 1475000 | NULL | Systemwide | NULL | NULL | 10 | Capital Replacement on aging equipment | Replace equipment as-needed including items such as automated equipment, loops, gate arms, etc. | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2025 | 3526861 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43433 | 0 | Fall 2017: updated FY18 and FY19 and added all funds thru FY24. Fall 18: updated per DDA | NULL | 0 | 0 | TRPF1801.jpg | Pollay, Susan | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Construction | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1962 | UT-ST-20-03 | Greenview (Stadium to Scio Church) Stormwater Improvements | 245000 | NULL | Greenview (Stadium to Scio Church) | NULL | NULL | 13 | NULL | Evaluate stormwater improvements achievable with resurfacing and watermain project; not Green Street; may come from Allen Creek funding; coordinate with storm/san study (UT-ST-20-S1) | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 70000 | 2 | 2024 | 3 | 2024 | 175000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Carson, Chris | Gosselin, Deb | 43417 | 0 | DOLLARS SHOWN ARE COMPLETELY A PLACEHOLDER; NEED TO REFINE; Original # was 18-12 but was never added to plan Fall 18: do after pending Glen Leven Study | NULL | 0 | 0 | UTST1812.jpg | Baughman, Troy | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | SWMM | NULL | NULL | NULL | Programmed | Inactive | 31.03 | 33 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
1963 | UT-ST-18-13 | Springwater Phase IV Stormwater Improvements | 950000 | NULL | Cardinal (all), McComb (all), Sharon (Cardinal to Springbrook) | NULL | NULL | 13 | Replace existing storm sewer system in streets slated for reconstruction; implement Green Streets | Evaluate all storm sewer in neighborhood, replace & upsized existing storm sewer where necessary, deal with existing storm sewer taps, evaluate downstream impacts if upsized, follow with road construction. Coordinate with lining of sanitary sewer. | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 65000 | 2 | 2024 | 4 | 2024 | 885000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43045 | 0 | Fall 2016. Fall 17: NC | NULL | 0 | 0 | UTST1813.jpg | Warrow, Anne | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.52 | 13 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1964 | UT-ST-18-14 | Chalmers Drive Stormwater Improvements | 475000 | NULL | Chalmers- Washtenaw to Woodcreek | NULL | NULL | 13 | Add stormwater facilities with paving | Green Streets; SAD; consider expanding limits north to City jurisdictional limit | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 50000 | 2 | 2021 | 4 | 2021 | 425000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Allen, Jane | 43045 | 0 | Fall 2016: new. Fall 17: NC Fall 18: | NULL | 0 | 0 | UTST1814.jpg | Lawson, Jennifer | Allen, Jane | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 24.2 | 37 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
1966 | TR-AT-18-22 | Border to Border Trail: Fuller/Maiden Ln | 1750000 | NULL | North side of Fuller between Fuller Park and Riverside Park | NULL | NULL | 6 | Connect Fuller Park to Riverside Park | Bridge will be required; Coordinate if possible with intersection project & bridge rehabilitation; MDEQ permit (river crossing); UM involvement. Public art enhanced | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 4 | 2025 | 160000 | 2 | 2026 | 4 | 2026 | 1590000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43434 | 0 | Fall 2016; added to plan but funds unknown; shown as GF but will seek County reimbursement and possible TAP. Fall 18: moved to beyond 25 and now show County millage, Tap, and UM as contributors | NULL | 0 | 0 | TRAT1822.jpg | Kuras, Amy | Dykman, Dave | Cooper, Eli | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Non-Motorized Plan | NULL | Parks & Recreation Open Space (PROS) Plan | NULL | Programmed | Inactive | 64.08 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 50000 | 0
2037 | UT-WS-18-36 | Springwater Phase IV Water Main Replacement | 1272000 | NULL | Cardinal; McComb; Sharon (Cardinal to Springbrook) | NULL | NULL | 14 | Replace aging water mains | Replace water mains; coordinate with road and stormwater construction; may be broken into phases later | NULL | Yes | 1 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 3 | 2025 | 85000 | 2 | 2026 | 4 | 2026 | 1187000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43046 | 0 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | UTWS1836.jpg | Warrow, Anne | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 27.13 | 67 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1967 | TR-AT-18-23 | Jackson (West of Highlake) Pedestrian Crossing | 200000 | NULL | Jackson Ave between Highlake and split | NULL | NULL | 6 | Facilitate pedestrian crossing; AAATA contribution; coordinate with road project | Pedestrian Island, Lighting, Two independent PHBs; Coordinate with planned capital maintenance on Jackson Rd in 2018 construction year. MDOT involvement: AAATA; Need identified in development plan | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 1 | 2018 | 25000 | 2 | 2019 | 3 | 2019 | 235000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43434 | 0 | Fall 2106: new. Fall 18: moved to FY19 as MDOT has not yet authorized | NULL | 0 | 0 | TRAT1823.jpg | Redinger, Cynthia | Heatley, Alison | Thacher, Jill | NULL | NULL | 1 | NULL | NULL | NULL | AAATA | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 62.94 | 10 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 2 | 1 | NULL | 1 | 1 | 1 | 1 | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
1970 | TR-OT-18-02 | Huron West (Third to Division) Streetscape | 1430000 | NULL | Huron (Third to Division) | NULL | NULL | 9 | Encourage those west of downtown to make the trip by improving connectivity to the downtown core; help restore Huron as a gateway into downtown and improve the walking experience east to west and crossing north to south | DDA: new sidewalks, street trees, lighting, decorative paving, stormwater infiltration, and crossing treatments; at grade Treeline crossing; investigate vaults and water leads and sizes: DTE gas main replacement; conduit, non-rush hr pking, signal changes | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2017 | 4 | 2018 | 500000 | 3 | 2018 | 4 | 2019 | 5100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | 43425 | 0 | Fall 2016: new as approved by DDA;. Fall 2017: changed limits aand cost. Fall 18: no cost change per amber | NULL | 0 | 0 | TROT1802.jpg | Miller, Amber | Elenbaas, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | DDA | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 56000 | 0
2246 | UT-WS-18-59 | Dunmore, Waverly, Weldon, Hartoford Pl Water Main Replacement | 700000 | NULL | Dunmore (Sanford Pl to Waverly); Waverly (Dunmore to Weldon); Weldon (Waverly to Winsted) Hartford PL | NULL | NULL | 14 | Improve water quality issues and improve flows | Replace 1950 iron 6" mains with 8" mains to address water quality and flow issues; consider PVC water mains: coordinate with Weldon and Dunmore pavement treatment;; cost est. based on road being done; | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 150000 | 2 | 2021 | 4 | 2021 | 2110000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43524 | 0 | Fall 2016: new; March 2019 CPAN: added Hartford Pl Scope; eval 6" main size to reduce risk of stagnant water in neighborhood; Feb. 2019 changed from UT-WS-18-01 to 18-59 per Fiance; _01 is now only Maywood | NULL | 0 | 0 | NULL | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Condition Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 59 | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2019-07-30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1971 | TR-OT-18-03 | Guardrail Capital Maintenance | 154000 | NULL | TBD | NULL | NULL | 9 | Address guardrail functional deficiencies and regulatory upgrades | Address guardrail functional deficiencies and regulatory upgrades; projects to be identified from a guardrail inspection report; applied for funds for ones on Jackson and Fuller for FY18; more will be added over time | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2018 | 4 | 2018 | 0 | 2 | 2018 | 4 | 2018 | 67000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43039 | 1 | Fall 2016: new. Fall 17: did not get grant so reduced to just Act 51 funds; Fall 18; NH said completing present round and will budget as Act 51 O and M going forward so marked complete | NULL | 0 | 0 | TROT1803.jpg | Nelson, Jenn | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 33.4 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1975 | TR-OT-18-S2 | Signal Timing Optimization | 500000 | NULL | Systemwide | NULL | NULL | 9 | Signal Timing Optimization | Engineering services to optimize 1/3rd of existing signal system that is not part of SCOOT; UM involvement for the signals that interact; possible CMAQ eligible; identification of system deficiencies; evaluate crash patterns and signal interaction | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2018 | 2 | 2019 | 500000 | 3 | 2018 | 2 | 2019 | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Gosselin, Deb | 43437 | 0 | New Fall 2016 Fall 2017: increased to $500K as approved in Act 51 budget. Fall 18 NC | NULL | 0 | 0 | TROT18S2.jpg | Liu, Luke | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | Condition Analysis | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 53.19 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
1979 | MF-CB-18-05 | Fire Station 4 Replacement | 4715000 | NULL | Fire Station 4 | NULL | NULL | 1 | Replace existing station on-site to improve station efficiency | Replace existing station on site; Net Zero bldg.;improve station efficiency; may need additional land to achieve Net Zero | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 1 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2021 | 4 | 2022 | 350000 | 2 | 2023 | 2 | 2025 | 4365000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | 43431 | 0 | Fall 2016: new. Fall 2107: moved evrything back two years as not funded at capital budget; Fall 18: renamed from New Fire Station B and updated costs; costs include $43,000 for public art | NULL | 0 | 0 | MFCB1805.jpg | Taylor, Ellen | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | Fire Station Master Plan | Programmed | Inactive | 76.33 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 2 | 2 | 2 | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | 2 | 27000 | 0
1978 | MF-CB-18-03 | Fire Station 3 Replacement | 4350000 | NULL | Fire Station 3 | NULL | NULL | 1 | Replace existing station on-site to improve station efficiency | Build new fire station to replace bldgs. over 50 yrs. old; Net Zero energy building;; update fire service tech; may need additional land to achieve Net Zero; maintain rain gardens; | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 1 | NULL | 3 | NULL | 0 | NULL | 0 | 3 | 2019 | 1 | 2021 | 350000 | 2 | 2021 | 2 | 2023 | 4365000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kennedy, Michael | Gosselin, Deb | 43431 | 0 | Fall 2016: New. Fall 17: moved everything back two years as not funded at capital budget Fall 18; renamed from Fire Station A and updated costs; costs include $43,000 for public art | NULL | 0 | 0 | MFCB1803.jpg | Kennedy, Michael | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | Fire Station Master Plan | Programmed | Inactive | 76.33 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 2 | 2 | 2 | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | 2 | 43000 | 0
1993 | UT-WS-18-22 | Ann (Glen to Zina Pitcher) Water Main Replacement | 300000 | NULL | Ann (Glen to Zina Pitcher) | NULL | NULL | 14 | Replace aging water main | Connector route; upsize approx. 550 LF to 12" minimum; cost estimate assumes done with future road project; | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 28000 | 2 | 2025 | 4 | 2025 | 372000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; no road programmed but shown in fy22/23; 2018 cost updated | NULL | 0 | 0 | UTWS1822.jpg | Baughman, Troy | Wooden, Dan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 47.92 | 17 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2079 | TR-OT-18-12 | Liberty (Main to Division) Streetscape | 770000 | NULL | Liberty (Main to Division) | NULL | NULL | 9 | Improve the walking experience on downtown’s most pedestrian traveled east/west street and reduce maintenance | Potential elements: create space for healthy trees, improve lighting, and reduce maintenance needs; add a new brick subbase, new brick, new tree pits, stormwater infiltration, and trees | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 300000 | 2 | 2022 | 4 | 2022 | 2200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43437 | 0 | Fall 2016: new. Fall 18: upped $ per DDA and moved to FY23 as placeholder | NULL | 0 | 0 | TROT1812.jpg | Miller, Amber | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 25000 | 0
2080 | TR-OT-18-13 | Washington (Ashley to 3rd) Streetscape | 575000 | NULL | Washington (Ashley to 3rd) | NULL | NULL | 9 | Improve the safety and functionality of the pickup/drop-off area adjacent to the YMCA and strengthen the connection of the near-in west side neighborhood to downtown | DDA project. Possible elements: include improving the appearance of the sidewalks under the railroad overpass and across from the YMCA, creating a strategy for curbside drop-off, and installing an Allen Creek Greenway Crossing (costs not incl.) | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 240000 | 2 | 2023 | 4 | 2023 | 1760000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43437 | 0 | Fall 2016: new. Fall 18 updated $ per DDA | NULL | 0 | 0 | TROT1813.jpg | Miller, Amber | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 2 | 20000 | 0
2059 | UT-WS-18-48 | Madison (Soule to end) Water Main Replacement | 900000 | NULL | Madison (Soule to end) | NULL | NULL | 14 | Replace aging water main | Replace aging main; coordinate with road resurfacing | NULL | No | 1 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 100000 | 2 | 2024 | 4 | 2024 | 1300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2016: new; 2018 cost updated | NULL | 0 | 0 | UTWS1848.jpg | Baughman, Troy | Elenbaas, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 23.17 | 74 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2058 | TR-OT-18-S3 | Transportation Plan Update | 400000 | NULL | Citywide | NULL | NULL | 9 | Update Transportation and Non-Motorized Plans to reflect current City goals and needs | Update the 2009 City Transportation plan and 2013 Non-motorized Transportation Plan and merge into one document; community engagement; focus on strategies for multi-modal network, safety (Vision Zero), congestion mitigation | NULL | No | 0 | 0 | 4 | NULL | NULL | 1 | 0 | NULL | 4 | 2018 | 2 | 2020 | 440000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Cooper, Eli | 43404 | 0 | Fall 2016: new. Fall 17: only $100K funded in FY18 so asking for balance in FY19 and 20. Fall 18: | NULL | 0 | 0 | TROT18S3.jpg | Cooper, Eli | Redinger, Cynthia | Liu, Luke | Lenart, Brent | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 69.49 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2062 | UT-WS-18-52 | WTP: Ammonia Building Improvements | 440000 | NULL | WTP | NULL | NULL | 14 | Replace aging ammonia feed system | Replace aging ammonia feed system, replace leaking ammonia pipes, correct safety issues | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2018 | 40000 | 1 | 2020 | 2 | 2020 | 190000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43437 | 0 | Fall 2016: new. Fall 18 updated per WTP | NULL | 0 | 0 | UTWS1852.jpg | Wiczorek, Glen | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 56.03 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 2 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2064 | UT-WS-18-49 | Arbordale St, Sherwood St and Sherwood Ct Water Main Replacement | 1500000 | NULL | Arbordale between Stadium and Pauline; Sherwood St and Sherwood Court | NULL | NULL | 14 | Replace aging mains | Replace water main due to break history prior to road resurfacing. | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 160000 | 2 | 2024 | 4 | 2024 | 2140000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 2106: new; 2018 cost updated | NULL | 0 | 0 | UTWS1849.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 25.15 | 71 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2040 | UT-WS-18-40 | State St (Ellsworth to I-94) Raw Water Main 30" Upgrade | 2107000 | NULL | State St (Ellsworth to I-94) | NULL | NULL | 14 | Replace and upsize raw water main | Replace approximately 2450 LF of raw water main and upsize; align with road reconstruction; need came from WTP master plan study; | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2028 | 4 | 2028 | 150000 | 2 | 2029 | 4 | 2029 | 1957000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43046 | 0 | Fall 2016: split form bigger project. Assume $860 per LF based on info from MN for Stadium. Fall 17: NC Fall 18: moved to FY30 to match road | NULL | 0 | 0 | UTWS1840.jpg | Sanford, Larry | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.26 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2109 | UT-SN-20-S1 | Capital Recovery Charge Study - Sanitary | 125000 | NULL | Citywide | NULL | NULL | 12 | Update capital recovery charge study | Update capital recovery charge study; coordinate with water Recovery Charge Study | NULL | Yes | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2020 | 2 | 2021 | 125000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN20S1.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 41.93 | 36 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
2110 | UT-SN-20-03 | Ann Arbor Woods Wet Weather Sanitary Improvements (DOM) | 2800000 | NULL | Ann Arbor Woods Subdivision Area | NULL | NULL | 12 | Wet weather capacity issues | Increase sewer capacity; evaluate all other infrastructure; coordinate with UT-WS-18-51; Coordinate with county parks; consider phasing; DOM funding; see 2018 OHM SSIPE Report; explore alt const methods for cost savings; cost est assumes open cut method | NULL | Yes | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 200000 | 2 | 2025 | 4 | 2025 | 2600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2003.jpg | Baughman, Troy | Elenbaas, Chris | Slizewski, Brian | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Sanitary Sewer Wet Weather Evaluation Study | NULL | NULL | NULL | Programmed | Inactive | 52.56 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2104 | TR-AT-20-03 | Low Stress Bicycle Network Signage | 400000 | NULL | Citywide | NULL | NULL | 6 | Establish wayfinding for low stress bicycle network to encourage active transportation | Determine routes with community input; install customized wayfinding signage | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 2 | 2025 | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Cooper, Eli | 43437 | 0 | Fall 18: new | NULL | 0 | 0 | TRAT2003.jpg | Cooper, Eli | Redinger, Cynthia | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Transportation Plan Update (2009) | NULL | NULL | NULL | Programmed | Inactive | 43.12 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2107 | UT-SN-20-01 | Darlington Subdivision Wet Weather Sanitary Improvements (DOM) | 2400000 | NULL | Darlington Subdivision | NULL | NULL | 12 | Wet weather capacity issues | Norwood, Fernwood; evaluate all infrastructure; possible drain redistricting (storm is county drain district); DOM funding; Refer to 2018 OHM SSIPE Report. Coordinate with water project | NULL | Yes | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 160000 | 2 | 2025 | 4 | 2025 | 2240000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2001.jpg | Baughman, Troy | Slizewski, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Sanitary Sewer Wet Weather Evaluation Study | NULL | NULL | NULL | Programmed | Inactive | 52.56 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 2 | 2 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2106 | TR-AT-20-05 | Mulholland Sidewalks | 87000 | NULL | Mulholland Ave | NULL | NULL | 6 | Fill sidewalk gap | Fill sidewalk gaps - see FTCH report | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 0 | 2 | 2025 | 2 | 2025 | 87000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43437 | 0 | Fall 18: new; showed in outer years but could probably do with small gaps sooner | NULL | 0 | 0 | TRAT2005.jpg | Hutchinson, Nick | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 45.34 | 25 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2066 | UT-WS-18-55 | Scio Church (Winsted to Welch) and Waltham to Covington Consolidation | 150000 | NULL | Scio Church between Winsted & Welch AND Scio Church between Waltham & Covington | NULL | NULL | 14 | Abandon one of the dual water mains due to break history in advance of upcoming road project | Abandon existing 6" water main; relocate house leads (13) and transfer 2 hydrants to 12" main | NULL | Yes | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2021 | 25000 | 4 | 2020 | 4 | 2021 | 125000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Gosselin, Deb | 43438 | 0 | Fall 2016: new. Fall 17: moved to FY22 to match street Fall 18: back to 21 to match street | NULL | 0 | 0 | UTWS1855.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 20 | 80 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2067 | UT-WS-18-56 | State St (S University to Hill) Water Main Consolidation | 250000 | NULL | State Street between South University and Hill Street | NULL | NULL | 14 | Abandon one of the dual water mains in advance of upcoming road project | Abandonment of 6"/4" water main; Transfer 9 leads and 2 hydrants to existing 12" main; coordinate with resurfacing | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 20000 | 2 | 2023 | 2 | 2023 | 230000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43046 | 0 | Fall 2016: new. Fall 17: NC Fall 18 moved to go with resurfacing; costs not updated | NULL | 0 | 0 | UTWS1856.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2068 | UT-WS-18-57 | South University (State to E University) Water Main Abandonment | 200000 | NULL | South University between State Street and East University | NULL | NULL | 14 | Consolidatemultiple water mains for efficiency | Abandon 6" water main; consolidate City 12" main and UM 12" main to a single new main with cost sharing; transfer leads from the 6" main to new 12"; cooridnate with resurfacing; UM to lead project and also address steam tunnels | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 0 | 2 | 2020 | 4 | 2020 | 2140000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43389 | 0 | Fall 2016: new; match to road work. Fall 17: moved out of FY18 to FY20 and costs will increase but then be split with UM to replace 12' and transfer leads; COST FIGURES Shown are rough and need to be checked next fall; cost updated | NULL | 0 | 0 | UTWS1857.jpg | Dykman, Dave | Baughman, Troy | NULL | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 19.4 | 81 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | 2018-036 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2070 | TR-SC-18-19 | Springwater Phase V Road Reconstruction | 1320000 | NULL | Rosedale (all); Redwood and Sharon (Springbrook to Platt) | NULL | NULL | 11 | Reconstruct roads | Reconstruct roads in coordination with water, sanitary (lining), and stormwater projects in the subdivision. Streets include all or portions of Rosedale and Redwood and Sharon (Springbrook to Plat). Consider sidewalk gaps. Public art enhanced | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 95000 | 2 | 2025 | 4 | 2025 | 1225000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43038 | 0 | Fall 2016: new. Fall 17: NC | NULL | 0 | 0 | TRSC1819.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 53.85 | 20 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | 2 | 32500 | 0
2072 | UT-WS-18-58 | Springwater Phase V Water Main Replacement | 683000 | NULL | Rosedale (all) and Sharon (Springbrook to Platt) | NULL | NULL | 14 | Replace aging water mains | Replace aging water mains; coordinate with road reconstruction and stormwater improvements | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 50000 | 2 | 2025 | 4 | 2026 | 633000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Warrow, Anne | Gosselin, Deb | 43439 | 0 | Fall 2106: new. Fall 17: NC Fall 18 $ not updated moved out | NULL | 0 | 0 | UTWS1858.jpg | Warrow, Anne | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 27.13 | 67 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2073 | UT-WS-16-42 | Washtenaw Ave (County Farm Park to Platt) Water Main Replacement | 1600000 | NULL | Washtenaw Ave between County Farm Park and Platt | NULL | NULL | 14 | Replace aging water mains | High PAN. Examine both mains and consider upsizing. Enviro sensitivity. Coord. w/WCWRC/Cnty. Park/MDOT. Close proximity to franchise utilities. Cost assumed replacing both mains & won't be done w/rd. proj.; limits are from mid-pt. of County Prk. to Platt | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 140000 | 2 | 2024 | 4 | 2024 | 1860000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | 2016 - Split previous project (stadium to H. Pkwy) into 3 different projects due to cost and updated cost figures. Fall 17:NC; 2018 cost updated | NULL | 0 | 0 | UTWS1642.jpg | Baughman, Troy | Wooden, Dan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 16.24 | 83 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2074 | UT-WS-16-43 | Washtenaw Ave (Platt to Huron Parkway) Water Main Replacement | 750000 | NULL | Washtenaw Ave between Platt and Huron Parkway | NULL | NULL | 14 | Replacing aging water main | High PAN. Enviro sensitivity. Coord w/ WCWRC/Cnty Park/MDOT. Close proximity to franchise utilities. Cost assume it won't be done with road project | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 3 | 2024 | 50000 | 3 | 2025 | 4 | 2025 | 700000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | 2016 - Split previous project (stadium to H. Pkwy) into 3 different projects due to cost and updated cost figures; 2018 cost verified as NC | NULL | 0 | 0 | UTWS1643.jpg | Baughman, Troy | Wooden, Dan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 16.24 | 83 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2099 | TR-AT-19-06 | School Safety: Fuller Road Sidewalk Gap | 185000 | NULL | Fuller Road (south side from Gallup Park etrance west to new Huron High pedestrian crossing) | NULL | NULL | 6 | Improve safety of crossing to Huron High School | Install sidewalk on south side of Fuller from Gallup Park easterly ped. entrance to new pedestrian crossing location across from Huron High School; relocate RRFB from present to new crossing location and install ped. island; applied for HSIP funds | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 4 | 2017 | 0 | 3 | 2018 | 4 | 2018 | 185000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43041 | 0 | Fall 17: added. Fall 18: NC; grant obtained but project may not proceed | NULL | 0 | 0 | TRAT1906.jpg | Redinger, Cynthia | Slizewski, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 66.55 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2084 | TT-XX-01-01 | Test project | 15 | NULL | NULL | NULL | NULL | 0 | fdsm,faksdf'al | asdfsdfas | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | 0 | NULL | 0 | NULL | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gosselin, Deb | Gosselin, Deb | NULL | 0 | NULL | NULL | 0 | 0 | TTXX0101.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | 2 | 2017-03-06 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | Yes | NULL | 0
2095 | TR-SC-19-02 | Nixon (M-14 to Huron Pkwy) Street Improvements Design | 1200000 | NULL | Nixon (M-14 to Huron Pkwy) | NULL | NULL | 11 | Design street improvements on Nixon | Review Nixon Corridor Traffic Study recommendations; design elements which further design and community engagement efforts prove to be feasible and desirable; cooridnate with water and storm projects; Green Streets; non-motorized elements; $ are design | NULL | NULL | 1 | 0 | 8 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2017 | 2 | 2019 | 8287000 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43038 | 1 | Fall 17: added per Council from fund balance | NULL | 0 | 0 | TRSC1902.jpg | Kotlyar, Igor | Hutchinson, Nick | Elenbaas, Chris | Lawson, Jennifer | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | Active | Design | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 50467.19 | 2018-03-31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2108 | UT-SN-20-02 | Sanitary Sewer Repair Under US-23 at Washtenaw | 500000 | NULL | US 23 and Washtenaw | NULL | NULL | 12 | Repair grouted in 15" sanitary sewer | Likely new sanitary sewer bore under US 23; county permits for Swift Run crossing - possible MDEQ permit | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 35000 | 2 | 2022 | 2 | 2022 | 465000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2002.jpg | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 34.04 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2096 | UT-ST-19-01 | Nixon (M-14 to Huron Pkwy) Stormwater Improvements | 300000 | NULL | Nixon (M-14 to Huron Pkwy) | NULL | NULL | 13 | Design stormwater improvements in conjunction with proposed street improvements | Design stormwater improvemetns in conjunction with prop street improvements; some may be first time improvements subject to assessment; possible SRF project; may not be improvmetns in all segments if not all are reconstructed; costs shown are design only | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | 2018 | 4 | 2018 | 300000 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43045 | 1 | Fall 17: new (design) Fall 18: closed design phase and created 3 | NULL | 0 | 0 | UTST1901.jpg | Lawson, Jennifer | Sheehan, Harry | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | Active | Design | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 2017-12-23 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2111 | UT-SN-20-04 | Trader Joe's Sanitary Sewer Repair | 290000 | NULL | Trader Joe's | NULL | NULL | 12 | Repair sanitary sewer | Retaining wall; access easements needed; coordinate with property owner | NULL | No | 0 | 0 | 3 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 40000 | 2 | 2022 | 2 | 2022 | 250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43440 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2004.jpg | Elenbaas, Chris | Ferrell, Ryan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 36.29 | 26 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2143 | UT-WS-20-19 | Barton to WTP Raw Water Main Condition Analysis | 450000 | NULL | Barton to WTP | NULL | NULL | 14 | Analyze 42" PCCP condition | Potential to evaluate other PCCP mains across city; major construction required to access pipe | NULL | NULL | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 50000 | 2 | 2021 | 2 | 2021 | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43439 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2019.jpg | Elenbaas, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 35.84 | 44 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2127 | UT-WS-20-06 | Ashley Water Main Consolidation | 1200000 | NULL | Ashley (between Washington and Liberty;and Liberty to William) | NULL | NULL | 14 | Consolidate parallel mains | Abandon 6" main and move leads and hydrants to 12" main. Also included in cost figures is upsizing of mains funded by DDA | NULL | NULL | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2020 | 3 | 2020 | 1200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18: new | NULL | 0 | 0 | UTWS2006.jpg | Baughman, Troy | Rolla, Liz | Elenbaas, Chris | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 42.37 | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2133 | UT-WS-20-10 | Rock Creek and Huntington Dr. Water Mains | 4200000 | NULL | Rock Creek Dr, Rock Creek Ct, and Huntington Dr. to Huntington Pl | NULL | NULL | 14 | New water mains | Cooridnate with sanitary sewer project; signifcant right of way needs; See 2018 TetraTech Report | NULL | Yes | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2024 | 350000 | 2 | 2025 | 4 | 2025 | 3850000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Baughman, Troy | 43391 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2010.jpg | Slizewski, Brian | Baughman, Troy | Elenbaas, Chris | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.46 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2148 | TR-OT-20-01 | Jackson Guardrail and Friction Pavement Project | 158000 | NULL | Jackson Rd (WB from hotel drive to overpass bridge) | NULL | NULL | 9 | Increase safety | Safety Grant funded improvements to guadrail and test friction pavement project | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2019 | 3 | 2019 | 158000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Hutchinson, Nick | NULL | 0 | Fall 18 new | NULL | 0 | 0 | TROT2001.jpg | Hutchinson, Nick | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 26.4 | 17 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 0
2149 | TR-OT-20-02 | Streetlights: Ann Arbor-Saline Rd Corridor | 162000 | NULL | Ann Arbor-Saline: S Main St to I-94 ramp | NULL | NULL | 9 | Install streetlights on unlit corridor | Minimum 18 lights; replace existing solar ped crossing lights | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2022 | 4 | 2022 | 50000 | 2 | 2023 | 2 | 2023 | 162000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | MacDonald, Josh | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2002.jpg | MacDonald, Josh | Fojtik, Chuck | Miller, Ethan | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 40.77 | 11 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2167 | TR-SC-20-06 | Ann (State to Glen) Resurfacing | 560000 | NULL | Ann Street (State to Glen) | NULL | NULL | 11 | Resurface street | Resurface street. Evaluate 2-way conversion. Private development at Glen. Coordinate with water main project (Ann/Ingalls fire flow improvements) | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 560000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2006.jpg | Dykman, Dave | Liu, Luke | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 50.55 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2236 | TR-SC-20-20 | Geddes Road (Church to Observatory) Resurfacing | 235000 | NULL | Geddes Rd (Church to Observatory) | NULL | NULL | 11 | Address pavement condition | Resurface street | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2019 | 4 | 2020 | 235000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2020.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 40.66 | 37 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2237 | UT-WS-20-25 | Geddes Road (Windy Crest to 500' West of Earhart) Water Main Replacement | 2300000 | NULL | Geddes Road (Windy Crest to 500' West of Earhart) | NULL | NULL | 14 | Replace Aging water main (abt 2300 LF) | Replace Aging water main | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 165000 | 2 | 2021 | 4 | 2021 | 2135000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43438 | 0 | Fall 18: added, Assumed not done with road when estimating | NULL | 0 | 0 | UTWS2025.jpg | Elenbaas, Chris | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 34.06 | 48 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2238 | UT-ST-20-10 | Huron Pkwy at Hubbard Area Millers Creek Outfall | 170000 | NULL | Huron Pkwy at Hubbard | NULL | NULL | 13 | Address Millers Creek outfall capital maintenance | To be completed in conjunction with UM project | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2020 | 2 | 2020 | 170000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43424 | 0 | Fall 18: new | NULL | 0 | 0 | UTST2010.jpg | Elenbaas, Chris | NULL | NULL | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2239 | UT-ST-20-11 | State St (1-94 WB Ramps to Oakbrook) Stormwater | 4400000 | NULL | State St (1-94 WB Ramps to Oakbrook) | NULL | NULL | 13 | Green Streets Improvements | Green Streets Improvements in conjunction with street project TR-SC-20-48 | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2027 | 4 | 2027 | 4400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43425 | 0 | Fall 18: added; years are really juts "Beyond 2025" | NULL | 0 | 0 | UTST2011.jpg | Cooper, Eli | Carson, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | State Street Corridor Transportation Study | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2241 | UT-ST-20-13 | State St (Ellsworth to I-94 EB Ramp) Stormwater | 1500000 | NULL | State St (Ellsworth to I-94 EB Ramp) | NULL | NULL | 13 | Green Street Improvements | Green Street Improvements in conjunction with street project TR-SC-20-50 | NULL | NULL | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2029 | 4 | 2029 | 1500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43425 | 0 | Fall 18: added; year is placeholder | NULL | 0 | 0 | UTST2013.jpg | Cooper, Eli | Carson, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | State Street Corridor Transporation Study | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2243 | UT-ST-20-S4 | Urban & Community Forestry Management Plan Update | 65000 | NULL | Citywide | NULL | NULL | 13 | Update existing Urban $ Community Forestry Management Plan | Update existing Urban $ Community Forestry Management Plan | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 2 | 2020 | 65000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gray, Kerry | Gosselin, Deb | 43430 | 0 | Fall 18 New | NULL | 0 | 0 | UTST20S4.jpg | Gray, Kerry | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2247 | UT-SN-20-14 | John Street Sanitary Sewer | 40000 | NULL | John Street | NULL | NULL | 12 | Address failing sewer | Construct new sanitary sewer from rear yard location at east end south to tie to sewer in John Street; re-plumb house that taps to the rear yard sewer; obtain easement for new sewer; | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2018 | 2 | 2019 | 15000 | 2 | 2019 | 2 | 2019 | 25000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43579 | 0 | Added due to emergency nature; will be les than 100K but added for tracking | NULL | 0 | 0 | NULL | Elenbaas, Chris | Slizewski, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Low Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2112 | UT-SN-20-05 | WWTP: Tertiary Clear Well Wall Replacement | 1200000 | NULL | WWTP | NULL | NULL | 12 | Existing baffle walls need replacement | Replace baffle walls and diffusers in two locations | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 3 | 2020 | 100000 | 1 | 2021 | 2 | 2021 | 1100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Englert, Chris | Gosselin, Deb | 43440 | 0 | NULL | NULL | 0 | 0 | UTSN2005.jpg | Englert, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 46.77 | 9 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | 2 | 2 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2113 | UT-SN-20-06 | WWTP: Screening and Grit System Replacement | 2575000 | NULL | WWTP | NULL | NULL | 12 | Replace screening and grit system | Replace screening and grit system | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 2 | 2020 | 275000 | 3 | 2020 | 4 | 2020 | 2300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Englert, Chris | Gosselin, Deb | 43440 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2006.jpg | Englert, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 50.4 | 7 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
2114 | UT-SN-20-07 | WWTP: Access Bridge Replacement | 6000000 | NULL | WWTP Access Bridge | NULL | NULL | 12 | Bridge needs to be replaced | Construct bridge in new location, abandon existing; address pipes on existing bridge | NULL | No | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2025 | 2 | 2026 | 6000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Englert, Chris | Gosselin, Deb | 43440 | 0 | Fall 18 new. $6M total swag | NULL | 0 | 0 | UTSN2007.jpg | Englert, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 36.89 | 24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2115 | UT-SN-20-08 | Swift Run Interceptor Lining | 700000 | NULL | Swift Run Interceptor from Clark to South Side Interceptor | NULL | NULL | 12 | Address condition - extensive roots an H2S corrosion on 18"/24" sewer | Evaluate wet weather capactity; easement; may require bypass pumping | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 80000 | 2 | 2020 | 2 | 2020 | 620000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | NULL | NULL | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2008.jpg | Elenbaas, Chris | Matthews, Paul | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 50.87 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | 2 | 2 | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2116 | UT-SN-20-09 | Spring, Miller, & Chapin Intersection Area Sanitary Sewer Improvements | 760000 | NULL | Spring Miller Chapin intersection | NULL | NULL | 12 | Address flat sewers, specifically the 12" that from Spring that turns west to the Chapin/Miller intersection; consolidate existing sewers | Investigate consolidation and inadequate slope conditions; Will require flow metering and preliminary engineering; evaluate water main in area; in floodway. Cooridnate with road project. | NULL | Yes | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 30000 | 3 | 2023 | 4 | 2023 | 80000 | 2 | 2024 | 4 | 2024 | 650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43440 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2009.jpg | Elenbaas, Chris | Ferrell, Ryan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.77 | 21 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 0 | 0 | 1 | NULL | NULL | 1
2117 | UT-SN-20-S2 | Original High Level Sanitary Sewer Evaluation | 40000 | NULL | Original high level 15" sewer from Hill/Division to Washington | NULL | NULL | 12 | Evaluate high risk aging infrastructure | Evaluate condition and potential for abandonment; review SSIPE smoke testing results in Division/Hill area; UM coordination; in flood plain/floodway; look for coordination opportunities with other projects; possible DOM funding | NULL | NULL | 0 | 0 | 5 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 40000 | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 2 | 2021 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43440 | 0 | Fall 18 new; 1/9/19 - Due to budget constraints this project will not happen in FY20. | NULL | 0 | 0 | UTSN20S2.jpg | Elenbaas, Chris | Ferrell, Ryan | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 17.02 | 35 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2118 | UT-SN-20-11 | Sanitary Sewer Infiltration Mitigation | 400000 | NULL | Citywide as need identified | NULL | NULL | 12 | Address sewer deposits from infiltration | Cut deposits and grout joints to eliminate infiltration | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 2 | 2023 | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Elenbaas, Chris | 43418 | 0 | Fall 18 | NULL | 0 | 0 | UTSN2011.jpg | Elenbaas, Chris | Matthews, Paul | Ferrell, Ryan | Baughman, Troy | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 27.42 | 32 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2134 | UT-ST-20-01 | Maywood Storm Sewer | 650000 | NULL | Maywood | NULL | NULL | 13 | Replace and lower storm main | Coordinate with Dunmore/Waverly/Weldon/Maywood WM project | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 1 | 2018 | 45000 | 2 | 2019 | 4 | 2019 | 605000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Humphriss, Tesha | Gosselin, Deb | 43402 | 0 | Fall 18: new | NULL | 0 | 0 | UTST2001.jpg | Elenbaas, Chris | Baughman, Troy | Slizewski, Brian | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 56.5 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | 2 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2119 | UT-SN-20-10 | Sanitary Sewer Siphons Improvements | 75000 | NULL | Citywide | NULL | NULL | 12 | Assess condition of siphons | Assess condition of siphons; railroad, DDA coordination; floodway; Main St at Allen Creek first look | NULL | No | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2019 | 2 | 2020 | 75000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43440 | 0 | Fall 18 | NULL | 0 | 0 | UTSN2010.jpg | Elenbaas, Chris | Ferrell, Ryan | Baughman, Troy | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 29.29 | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2126 | UT-WS-20-05 | Ann and Ingalls Area Fire Flow Improvement | 800000 | NULL | Ann (Thayer to Glen) or Ingalls (Catherine to Huron) | NULL | NULL | 14 | Improve fire flow | Evaluate which main to upsize (Ann (Thayer to Glen) or Ingalls (Kingsley to Huron)). Construct chosen main. Upsize to 12". Evaluate Ingalls all the way to Kingsley; Dave brought up both Ann & Ingalls need repaving; | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 56000 | 2 | 2024 | 4 | 2024 | 744000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Cost estimate assumes project will be done with road project | NULL | 0 | 0 | UTWS2005.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | ISO Report | NULL | NULL | NULL | Programmed | NULL | 52.67 | 10 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2120 | UT-SN-20-12 | Huntington Place to North Sanitary Extension | 800000 | NULL | West end Huntington Place to north to 350 Huntington Dr | NULL | NULL | 12 | Provide sanitary sewer service | Extend sanitary sewer; significant easement needs; coordinate with water project; evaluate solid waste access; evaluate drainage | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 56000 | 2 | 2025 | 4 | 2025 | 744000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2012.jpg | Baughman, Troy | Elenbaas, Chris | Slizewski, Brian | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Township Utility Island Investigation Report | NULL | NULL | NULL | Programmed | Inactive | 36 | 27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2121 | UT-SN-20-13 | Orchard Hills Drive Sanitary Extension | 500000 | NULL | Orchard Hills Drive | NULL | NULL | 12 | Provide sanitary service | Potential UM involvement; easements needed | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 50000 | 2 | 2025 | 4 | 2025 | 450000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTSN2013.jpg | Baughman, Troy | Elenbaas, Chris | Slizewski, Brian | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Township Utility Island Investigation Report | NULL | NULL | NULL | Programmed | NULL | 26.84 | 34 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2122 | UT-WS-20-01 | Dams: Barton Air Shaft Reconstruction | 675000 | NULL | Barton Dam | NULL | NULL | 14 | Severe concrete deterioration as identified in FERC inspection | Reconstruct air sfhaft; FERC approval needed; begin with detailed design phase and then program construction after; safety issues | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 4 | NULL | 0 | NULL | 0 | 4 | 2018 | 1 | 2019 | 75000 | 3 | 2019 | 2 | 2020 | 790000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2001.jpg | Wiczorek, Glen | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 71.08 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 2 | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | NULL | 1 | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 1
2123 | UT-WS-20-02 | Dams: Barton Pond USGS Gauging Station | 100000 | NULL | Barton Pond | NULL | NULL | 14 | FERC requirement to operate river in run of river mode | Work with USGS to design and install a new guaging station; MDEQ permit probably needed | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Gosselin, Deb | 43438 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2002.jpg | Wiczorek, Glen | Steglitz, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 29.9 | 61 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
2124 | UT-WS-20-03 | WTP: Interim UV Disinfection Project | 2460000 | NULL | WTP | NULL | NULL | 14 | MDEQ compliance for Long Term Treatment 2 requirement for cryptosporidium removal | Design and construct an interim UV system at the WTP to facilitate cryptosporidium removal; MDEQ involvement | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 3 | 2018 | 4 | 2018 | 25000 | 4 | 2018 | 1 | 2019 | 185000 | 2 | 2019 | 3 | 2020 | 2250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43437 | 0 | Fall 18 new per WTP | NULL | 0 | 0 | UTWS2003.jpg | Wiczorek, Glen | Steglitz, Brian | NULL | NULL | NULL | 1 | MDEQ | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 57.02 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | 2 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2125 | UT-WS-20-04 | WTP: Barton Pump Station Valve Replacement | 2200000 | NULL | Barton Pump Stattion | NULL | NULL | 14 | Replace aging valves | Replace valves in advance of 20" raw water suction piping project | NULL | No | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 1 | NULL | 4 | NULL | 0 | 4 | 2021 | 4 | 2023 | 2200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wiczorek, Glen | Wiczorek, Glen | 43437 | 0 | Fall 18 new per WTP | NULL | 0 | 0 | UTWS2004.jpg | Wiczorek, Glen | Steglitz, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 47.52 | 18 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2150 | TR-OT-20-03 | Streetlights: Liberty Corridor (Scio Ridge to Maple) | 126000 | NULL | Liberty (Scio Ridge to Maple) | NULL | NULL | 9 | Install streetlights on unlit corridor | Approximately 14 lights, span I-94 | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 40000 | 3 | 2023 | 2 | 2024 | 126000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | MacDonald, Josh | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2003.jpg | MacDonald, Josh | Fojtik, Chuck | Miller, Ethan | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 30.67 | 14 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2151 | TR-OT-20-04 | Streetlights: Packard (State to Stadium) | 728400 | NULL | Packard (State to Stadium) | NULL | NULL | 9 | Light corridor with many crosswalks, bike lanes, pedestrian activity | Safety grant application pending. Remove existing DTE lights and replace with approximately 40 lights to fully light corridor/crosswalks; HSIP grant applied for | NULL | No | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2019 | 1 | 2020 | 56000 | 2 | 2020 | 3 | 2020 | 672400 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Redinger, Cynthia | Redinger, Cynthia | 43390 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2004.jpg | Redinger, Cynthia | MacDonald, Josh | Fojtik, Chuck | Miller, Ethan | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 56.78 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2152 | TR-OT-20-05 | Streetlight Capital Maintenance | 595000 | NULL | Citywide where needs identified | NULL | NULL | 9 | Capital maintenance of city owned streetlights | Capital maintenance of city owned streetlights including pole replacement, luminaire replacement, painting, electrical upgrades, etc. | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 4 | 2018 | 55500 | 1 | 2019 | 2 | 2025 | 3159500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2005.jpg | Elenbaas, Chris | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Design | 50.88 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 0
2153 | TR-OT-20-06 | Central Signal System Software Upgrades | 150000 | NULL | Citywide | NULL | NULL | 9 | Upgrade Central Signal System Software | Upgrade SCOOT, Tactics, and Video Wall software; New central camera management software | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 3 | 2019 | 150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2006.jpg | Liu, Luke | Fojtik, Chuck | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 35.63 | 13 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2154 | TR-TR-20-01 | Transit Signal Priority Pilot | 100000 | NULL | Selected intersection on Fuller Rd and Plymouth Rd | NULL | NULL | 16 | Improve bus travel time reliability and emissions reductions | Selected intersection on Fuller Rd and Plymouth Rd. Technology enhancements to allow buses to have priority at certain intersections. UM and/or AAATA coordination and funding needed | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 4 | 2021 | 100000 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Gosselin, Deb | 43433 | 0 | Fall 18: new | NULL | 0 | 0 | TRTR2001.jpg | Liu, Luke | Fojtik, Chuck | NULL | NULL | NULL | 1 | AAATA | University of Michigan | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 38.11 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 0 | 1 | NULL | NULL | 0
2163 | TR-SC-20-04 | Miller Avenue (Linda Vista to Chapin) Rehabilitation | 1600000 | NULL | Miller Avenue (Linda Vista to Chapin) | NULL | NULL | 11 | Rehabilitate street | Consider removing old brick base where encountered. Evaluate water mains. Coordinate with Chapin/Miller Sanitary improvements. Examine pedestrian crossings. Treeline crossing at Chapin | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 0 | 2 | 2024 | 4 | 2024 | 1600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43418 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2004.jpg | Dykman, Dave | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 52.53 | 24 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2155 | TR-SC-20-01 | Downtown Alley Improvements | 700000 | NULL | DDA | NULL | NULL | 11 | Implement pilot project to Improve service access, acitivation, and overall function of downtown alleys | Utilize recommendations per Solid Waste Plan. Investigate stormwater infiltration | NULL | No | 0 | 0 | 5 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 1 | 2020 | 4 | 2020 | 700000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43425 | 0 | Fall 18: new | NULL | 0 | 0 | TRSC2001.jpg | Miller, Amber | Slotten, Cress | Seyfarth, Heather | Hancock, Jerry | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Solid Waste Plan | NULL | NULL | NULL | Programmed | Inactive | 60.55 | 8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | 1 | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2156 | TR-NS-20-01 | Hollywood (Maple to Allison) Paving | 250000 | NULL | Hollywood (Maple to Alliison) | NULL | NULL | 8 | Improve street from gravel to paved | Street paving petitioned by residents; Green Streets improvements | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 2 | 2020 | 250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Gosselin, Deb | 43425 | 0 | Fall18: new | NULL | 0 | 0 | TRNS2001.jpg | Hutchinson, Nick | NULL | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 58.77 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2157 | UT-ST-20-02 | Hollywood (Maple to Allison) Stormwater Improvements | 230000 | NULL | Hollywood (Maple to Allison) | NULL | NULL | 13 | Green Street improvements | Green Street Improvements in conjunction with first time paving of street; cooridinate with TR-SC-20-02; | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 0 | 2 | 2020 | 4 | 2020 | 230000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 43423 | 0 | Fall 18: new | NULL | 0 | 0 | UTST2002.jpg | Hutchinson, Nick | Allen, Jane | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.28 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
2242 | UT-ST-20-S3 | Tree Inventory Update | 115000 | NULL | Citywide | NULL | NULL | 13 | Update existing tree inventory | Update existing tree inventory | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 2 | 2019 | 115000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gray, Kerry | Gosselin, Deb | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | UTST20S3.jpg | Gray, Kerry | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2160 | TR-SC-20-02 | Washington (First to Third) Reconstruction | 1300000 | NULL | Washington (First to Third) | NULL | NULL | 11 | Replace underlying deteriorated concrete pavement | Reconstruct Stree. Coordinate with: Washington Bike Boulevard, DDA streetscape project, Treeline, YMCA, County Drain, Washington water main project, Stormwater, AAATA. In the floodplain. Investigate RR clearance. | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 90000 | 2 | 2025 | 4 | 2025 | 1210000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Hutchinson, Nick | Dykman, Dave | 43418 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2002.jpg | Hutchinson, Nick | Miller, Amber | Baughman, Troy | Cooper, Eli | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 62.75 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2161 | TR-SC-20-03 | State St (Hoover to Granger) Resurfacing | 770000 | NULL | State St - Hoover to Granger | NULL | NULL | 11 | Resurface | Resurface. Evaluate pedestrian crossing improvements. Treeline. Evaulate utilities. Lower Allen Creek watershed. 500 year floodplain. UM coordination; 1.5" water (need policy decision on what to do) | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 0 | 2 | 2024 | 4 | 2024 | 770000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2003.jpg | Dykman, Dave | Baughman, Troy | Hancock, Jerry | Seyfarth, Heather | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | Customer Level of Service | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 63.6 | 4 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | 1 | 2 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2162 | TR-SC-20-21 | Plymouth Rd (Nixon to US-23) CPM | 618000 | NULL | Plymouth Rd (Nixon
to US-23) | NULL | NULL | 11 | Capital maintenance | CPM treatment. Phased project. Potential Lower Town Traffic Study impacts Barton to Broadway. Examine pedestrian. Coordinate with UM | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 55000 | 3 | 2020 | 4 | 2020 | 763000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | Gosselin, Deb | 43430 | 0 | New Fall 18 | NULL | 0 | 0 | TRSC2021.jpg | Dykman, Dave | Liu, Luke | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Active | Inactive | 54.72 | 17 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 2 | NULL | NULL | NULL | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2164 | TR-SC-20-05 | Liberty (Stadium to Crest) Resurfacing | 460000 | NULL | Liberty (Stadium to Crest) | NULL | NULL | 11 | Resurfacing or CPM treatments | Stadium to Virginia likely CPM; Virginia to Seventh likely resurfacing. Coordinate with water main project 7th to Zion Church. Examine sewer needs for 1432 W Liberty (vacant); dual WMs west of Crest (need condition check on 1960s main) | NULL | Yes | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2019 | 4 | 2019 | 460000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Dykman, Dave | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2005.jpg | Dykman, Dave | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 48.57 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2128 | UT-WS-20-07 | Darlington Subdivision Area Water Mains | 450000 | NULL | Darlington Subdivision | NULL | NULL | 14 | Replace aging water mains | Coordinate with sanitary project. Replace water main along the proposed sanitary limits. Evaluate storm water (county drain) | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 30000 | 2 | 2025 | 4 | 2025 | 420000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | NULL | NULL | 0 | 0 | UTWS2007.jpg | Baughman, Troy | Slizewski, Brian | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 30.1 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2129 | UT-WS-20-S1 | Water Model Update | 200000 | NULL | Citywide | NULL | NULL | 14 | Update hydrauilic model | Update pipe network, demands, system operations etc. Perform flow testing necessary for re-calibration. Update water distribution system master plan. | NULL | No | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2019 | 2 | 2020 | 200000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43368 | 0 | Fall 18 new; 1/9/19 - Due to budget constraints, this project cannot be done in FY20/FY21. | NULL | 0 | 0 | UTWS20S1.jpg | Baughman, Troy | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 30.59 | 58 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2130 | UT-WS-20-S2 | Capital Recovery Charge Update - Water | 125000 | NULL | Citywide | NULL | NULL | 14 | Update capital recovery charge fees | Update charges; coordinate with sanitary charge update | NULL | Yes | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2020 | 2 | 2021 | 125000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS20S2.jpg | Baughman, Troy | Hupy, Craig | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 5.35 | 88 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0
2131 | UT-WS-20-08 | Broadway Water Main Consolidation (Maiden Lane to Jones) | 150000 | NULL | Broadway from Maiden Lane to Jones | NULL | NULL | 14 | Consolidate water mains | Abandon small main, move leads and hydrants to existing 12" main. Coordinate with development repaving and larger Broadway water main project to the east. Consider agreement to have Lower Town developer do work | NULL | NULL | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | 0 | 2 | 2020 | 2 | 2020 | 150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new; 2019 developer not cooperating and due to lack of funding this project may be pushed out or eliminated | NULL | 0 | 0 | UTWS2008.jpg | Baughman, Troy | Heatley, Alison | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 40 | 32 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2132 | UT-WS-20-09 | Pittsfield Village Water Main Improvements | 4700000 | NULL | Pittsfield Village | NULL | NULL | 14 | Replace 9,350 lf of aging water mains | Replace existing water mains; coordinate with sanitary improvement project; replacing AC pipes; very engaged neighborhood; evaluate elimination of master meters; replace galv service leads where lead goosenecks existed | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2023 | 4 | 2023 | 500000 | 2 | 2024 | 4 | 2025 | 4200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43439 | 0 | Fall 18 | NULL | 0 | 0 | UTWS2009.jpg | Baughman, Troy | Elenbaas, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 39.01 | 35 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2135 | UT-WS-20-11 | Huntington Pl, Huntington Dr, & Onaway Pl Water Main | 700000 | NULL | Huntington Place, Huntington Drive, Onaway Place | NULL | NULL | 14 | New water main | Cooridnate with sanitary sewer project; signifcant right of way needs | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 50000 | 2 | 2025 | 4 | 2025 | 650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2011.jpg | Baughman, Troy | Slizewski, Brian | Elenbaas, Chris | Nearing, Mike | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Township Utility Island Investigation | NULL | NULL | NULL | Programmed | Inactive | 43.46 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2136 | UT-WS-20-12 | Riverview Drive Water Main | 3250000 | NULL | Riverview Drive (N of Huntington Pll), Ausable Pl, Indian River Dr, Pineview Ct | NULL | NULL | 14 | New water main | Coordinate with sanitary sewer | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2024 | 3 | 2024 | 230000 | 2 | 2025 | 3 | 2025 | 3020000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2012.jpg | Baughman, Troy | Slizewski, Brian | Elenbaas, Chris | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Ann Arbor Township Utility Island Investigation | NULL | NULL | NULL | Programmed | Inactive | 37.52 | 39 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2137 | UT-WS-20-13 | Apple Way Water Main | 800000 | NULL | Apple Way | NULL | NULL | 14 | New water main | New water main | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 55000 | 2 | 2025 | 4 | 2025 | 745000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18 New | NULL | 0 | 0 | UTWS2013.jpg | Baughman, Troy | Slizewski, Brian | Elenbaas, Chris | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Ann Arbor Township Utility Island Investigation | NULL | NULL | NULL | Programmed | Inactive | 43.46 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2138 | UT-WS-20-14 | Galvanized Water Services Replacements | 14000000 | NULL | Citywide | NULL | NULL | 14 | Compliance with MDEQ lead and copper rules | Conduct desktop inventory of private galvanized leads by 2020, start replacing 2021, field verified inventory by 2025; replace 5% per year max | NULL | No | 0 | 0 | 2 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 1 | 2020 | 2 | 2040 | 14000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Matthews, Paul | Gosselin, Deb | 43439 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2014.jpg | Maciejewski, Molly | Matthews, Paul | Wooden, Dan | NULL | NULL | 1 | MDEQ | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 46.53 | 19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 2 | NULL | 1 | 2 | NULL | NULL | NULL | 2 | NULL | 2 | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2139 | UT-WS-20-15 | Arlington Place Condos Water Main Replacement | 770000 | NULL | Arlington Place Condos (Huron Pkwy, S of Washtenaw) | NULL | NULL | 14 | Replace 1,110 feet of deteriorating 10" water main. 200 feet is in casing | Further evaluate main condition | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 54000 | 2 | 2025 | 4 | 2025 | 716000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Elenbaas, Chris | Gosselin, Deb | 43439 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2015.jpg | Wooden, Dan | Elenbaas, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 20.2 | 79 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2140 | UT-WS-20-16 | State St (S Univ to Washington) Water Main Improvements | 1500000 | NULL | State St - S University to Washington | NULL | NULL | 14 | Replace aging main | Replace/upsize existing main, consolidate UM mains; coordinate with street project and DDA streetscape project; consider Allen Creek stormwater funded improvements | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 105000 | 2 | 2021 | 4 | 2021 | 1395000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Cost estimate assumes done with road | NULL | 0 | 0 | UTWS2016.jpg | Baughman, Troy | Elenbaas, Chris | NULL | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 43.56 | 28 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2141 | UT-WS-20-17 | North University Water Main Improvements | 800000 | NULL | North University - State to Fletcher | NULL | NULL | 14 | Replace aging water main | Replace/upsize aging water main, consolidate UM mains; coordinate with street project; cost assumes streets pays for road restoration | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 4 | 2020 | 60000 | 2 | 2021 | 4 | 2021 | 740000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Kotlyar, Igor | Baughman, Troy | 43413 | 0 | 2018: $800k is total project cost, do we assume UM pays for 50%? | NULL | 0 | 0 | UTWS2017.jpg | Baughman, Troy | Elenbaas, Chris | NULL | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 45.54 | 21 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 1 | NULL | NULL | NULL | 1 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2142 | UT-WS-20-18 | WTP: LIMS Software | 450000 | NULL | Water Treatment Plant - Environmental Lab | NULL | NULL | 14 | New software needed to manage lab and online data | Replacement of old Laboratory Information Management System with new software licenses to improve data entry, record keeping, data usage. 50/50 water/wastewater funded | NULL | NULL | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 2 | 2021 | 50000 | 3 | 2021 | 3 | 2021 | 350000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Page, Sarah | Gosselin, Deb | 43438 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2018.jpg | Steglitz, Brian | Page, Sarah | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 43.96 | 27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2145 | MF-PR-20-S1 | Parks ADA Study | 150000 | NULL | Citywide | NULL | NULL | 3 | Review facilities for ADA compliance | Review facilities for ADA compliance | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 150000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Smith, Colin | Smith, Colin | 43431 | 0 | Fall 18; new | NULL | 0 | 0 | MFPR20S1.jpg | Smith, Colin | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 58.57 | 6 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | 1 | 2 | 2 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2144 | UT-WS-20-20 | Federal Blvd (Stadium to Commerce) Water Main Upsize | 600000 | NULL | Federal Blvd - Stadium to Commerce | NULL | NULL | 14 | Upsize WM to 12" to complete loop | When ex wm warrants replacement, it needs to go back in as a 12". Nearby DVLP constructed part of 12" loop. This project will finish the loop. Cost assumes it will be done in coordination with road project. | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 42000 | 2 | 2025 | 4 | 2025 | 558000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43388 | 0 | Fall 18: new; at end awating road | NULL | 0 | 0 | UTWS2020.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 23.17 | 74 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2147 | TR-PF-20-01 | Maynard Parking Structure Office Build Out | 400000 | NULL | Maynard Parking Structure | NULL | NULL | 10 | Republic Parking (structure operator) needs more office space | Add a bathroom, expand office space and customer service areas; add a meeting space; facilities are for Republic Parking | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 4 | 2018 | 2 | 2019 | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43433 | 0 | Fall 18: new | NULL | 0 | 0 | TRPF2001.jpg | Pollay, Susan | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2168 | TR-SC-20-07 | Ingalls and Kingsley (Huron to State) Resurfacing | 750000 | NULL | Ingalls (Huron to Kingsley) and Kingsley (Ingalls to State) | NULL | NULL | 11 | Resurface street | Resurface street. Coordinate with water main project. UM coordination | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 750000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | NULL | NULL | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2007.jpg | Dykman, Dave | Baughman, Troy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 48.57 | 29 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2185 | TR-PF-20-02 | Parking Structure Fencing | 2113000 | NULL | City Parking Structures | NULL | NULL | 10 | Add safety fencing to City owned parking structures | Add safety fencing to City owned parking structures | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2017 | 2 | 2022 | 2112568 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43433 | 0 | Fall 18: new | NULL | 0 | 0 | TRPF2002.jpg | Miller, Amber | Pollay, Susan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2177 | TR-OT-20-S1 | Lower Town Area Mobility Study | 800000 | NULL | Broadway , Plymouth, Pontiac Tr, Barton, Swift, Moore, Division, Maiden Lane, Wall St. and Beakes | NULL | NULL | 9 | Investigate impacts of increased traffic due to existing, proposed, and future projects | Investigate impacts of increased traffic due to existing, proposed, and future projects | NULL | No | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2018 | 2 | 2020 | 800000 | 0 | NULL | 0 | NULL | 0 | 3 | 2018 | 2 | 2020 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | TROT20S1.jpg | Liu, Luke | Hess, Raymond | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 23.23 | 18 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Citywide | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | 1 | NULL | NULL | 1 | NULL | 1 | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2172 | TR-OT-20-10 | Fire Station Traffic Operations and Emergency Route Mgt. | 100000 | NULL | City Fire Stations | NULL | NULL | 9 | Facilitate ingress and egress from fire statiosn to improve response time and safety | Add signal premption for fire vehicles; add pavement markings and signige to facilitate fire vehicles entrance and exit from fire stations; improve traffic control on primary evacuation routes | NULL | No | 0 | 0 | 5 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2021 | 2 | 2022 | 100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2010.jpg | Liu, Luke | Box, Andy | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 29.23 | 16 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2173 | TR-OT-20-15 | Maiden Lane at Nielsen Ct Traffic Signal | 250000 | NULL | Maiden Lane at Nielsen Ct | NULL | NULL | 9 | Install new signal based on increasing traffic; community meeting prior to construction; in conjunction with new UM parking structure; UM funded | Install new signal; UM funded; need driven by Wall Street West parking structure; community meeting prior to construction | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 3 | 2020 | 250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Liu, Luke | 43390 | 0 | New Fall 2018 | NULL | 0 | 0 | TROT2015.jpg | Liu, Luke | NULL | NULL | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 62.77 | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2174 | TR-OT-20-11 | N University at CCTC Pedestrian Crossing Traffic Signal | 300000 | NULL | N University at Central Campus Transit Center Pedestrian Crossing | NULL | NULL | 9 | Install new signal based on increasing traffic and improve pedestrian safety | Improve transit operations (travel time reliability) and pedestrian safety; install new traffic signal and pedestrian signal; UM funded | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 4 | 2018 | 1 | 2020 | 15000 | 2 | 2020 | 3 | 2020 | 285000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Liu, Luke | 43390 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2011.jpg | Liu, Luke | NULL | NULL | NULL | NULL | 1 | University of Michigan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 55.52 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | High Local | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | NULL | 1 | 1 | 1 | NULL | NULL | 0
2175 | TR-OT-20-12 | Ellsworth at Research Park Traffic Signal and Pedestrrian Improvements | 300000 | NULL | Ellsworth at Research Park | NULL | NULL | 9 | Install new signal based on increasing traffic and improve pedestrian safety and improve pedestrian safety | Install new traffic signal at Ellsworth and Research Park; add pedestrain crosswalk and signal; provide connectivity from AAATA bus stop | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2019 | 2 | 2020 | 0 | 3 | 2020 | 4 | 2020 | 300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Allen, Jane | NULL | NULL | 0 | Rolled in old project TR-AT-12-04 | NULL | 0 | 0 | TROT2012.jpg | Liu, Luke | Allen, Jane | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | Capacity Analysis | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 58.51 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | 1 | 2 | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2176 | TR-OT-20-13 | Main at Madison Railroad Traffic Signal Upgrades | 650000 | NULL | Main/Madison intersection and Railroad Tracks to North and East | NULL | NULL | 9 | Federal Railroad Administration required safety improvement | Install new signals for at-grade railroad crossings; modify existing Main/Madison traffic signal; AAATA and MDOT coordination; MDOT funded | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2019 | 2 | 2019 | 650000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Liu, Luke | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2013.jpg | Liu, Luke | Fojtik, Chuck | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 44.89 | 10 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 2 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 0
2178 | UT-ST-20-S2 | Newport Creek Drainage Area Study | 75000 | NULL | Newport Creek Drainage Area | NULL | NULL | 13 | Evaluate bank erosion and flooding complaints | Hydrology study of creekshed | NULL | NULL | 0 | 0 | 4 | NULL | NULL | 0 | 0 | NULL | 3 | 2020 | 2 | 2021 | 75000 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Lawson, Jennifer | 43400 | 0 | Fall 18: new | NULL | 0 | 0 | UTST20S2.jpg | Lawson, Jennifer | Sheehan, Harry | NULL | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 13.81 | 40 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | 1 | NULL | 0
2180 | TR-OT-20-16 | Ann Arbor Railroad Quiet Zone | 9235000 | NULL | 21 Ann Arbor Railroad at grade crossings citywide (State to Dhu Varren) | NULL | NULL | 9 | Community request to silence train horns | Install raiilroad gates, medians near crossings, and other safety improvements necessitated by FRA regulations if Quiet Zones are pursued; traffic signal modifications; feasibility study underatken in FY19 | NULL | No | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 3 | 2018 | 3 | 2018 | 35000 | 3 | 2019 | 2 | 2021 | 200000 | 0 | NULL | 0 | NULL | 9000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Cooper, Eli | 43386 | 0 | Fall 18: new | NULL | 0 | 0 | TROT2016.jpg | Seyfarth, Heather | Cooper, Eli | Liu, Luke | Fojtik, Chuck | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Planning | 29.28 | 15 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 0 | NULL | NULL | 0
2196 | TR-SC-20-10 | Fletcher (N University to Huron) Resurfacing | 360000 | NULL | Fletcher (N University to Huron) | NULL | NULL | 11 | Resurface street; | Resurface street;; UM coordination; consider bumpouts; bike lanes | NULL | No | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 360000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2010.jpg | Dykman, Dave | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 50.99 | 27 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2244 | TR-PF-20-03 | Ann Ashley Parking Structure Solar Project | 1000000 | NULL | Ann Ashley Parking Structure | NULL | NULL | 10 | Alternative energy | : Install solar panels on the roof of the Ann/Ashley Parking Structure | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 1000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43438 | 0 | Fall 18 new per DDA | NULL | 0 | 0 | TRPF2003.jpg | Miller, Amber | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2221 | UT-WS-20-22 | Washington (First to Third) Water Main | 600000 | NULL | Washington (First to Third) | NULL | NULL | 14 | Aging water main | Replace water main only if full road reconstruction is being done. Cost assumes this. | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 42000 | 2 | 2025 | 4 | 2025 | 558000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Baughman, Troy | Baughman, Troy | 43413 | 0 | 2018: only do this is a full road recon is being done | NULL | 0 | 0 | UTWS2022.jpg | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2186 | TR-OT-20-17 | Annual DDA General Capital Improvements and Maintenance | 2400000 | NULL | DDA | NULL | NULL | 9 | Maintain infrastructure within DDA in good repair | Repair sidewalks (concrete and brick); replace trees and grates; Repair and replace streetlights | NULL | NULL | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 2 | 2025 | 3300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Miller, Amber | Gosselin, Deb | 43437 | 0 | Fall 18 new | NULL | 0 | 0 | TROT2017.jpg | Miller, Amber | Pollay, Susan | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2182 | UT-ST-20-05 | Detention Basin Restoration/Reconstruction | 1000000 | NULL | Citywide | NULL | NULL | 13 | Restoration or reconstruction of city owned detention basins | Waymarket Park, Furstenberg/Fuller Ct, Evergreen Sub (behind Maple Village). Smaller scale basin restoration through O&M | NULL | No | 0 | 0 | 3 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2019 | 4 | 2019 | 50000 | 1 | 2020 | 4 | 2020 | 950000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Lawson, Jennifer | 43417 | 0 | Fall 18: new | NULL | 0 | 0 | UTST2005.jpg | Lawson, Jennifer | Matthews, Paul | Nearing, Mike | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | Capacity Analysis | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Inactive | 41.75 | 21 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 2 | NULL | 1 | 1 | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 1
2198 | MF-SW-20-01 | Compost Pad Replacement | 200000 | NULL | Wheeler Center | NULL | NULL | 15 | Replace aging pad | Replace aggregate pad; | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2020 | 2 | 2021 | 200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Gomes, Christina | NULL | NULL | 0 | Fall 18: new | NULL | 0 | 0 | MFSW2001.jpg | Gomes, Christina | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 32.59 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 2 | NULL | 1 | NULL | 2 | NULL | 0 | 1 | 1 | NULL | NULL | 1
2230 | UT-ST-20-09 | Nixon (Dhu Varren to S of M-14) Phase 3 Stormwater Improvements | 1090000 | NULL | Nixon (Dhu Varren to S of M-14 | NULL | NULL | 13 | Provide Green Steets stormwater improvements | Provide Green Steets stormwater improvements; cooridnate with street construction | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2027 | 4 | 2027 | 1090000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | NULL | NULL | 0 | NULL | NULL | 0 | 0 | UTST2009.jpg | Wall, Chris | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2216 | TR-SC-20-12 | First and Ashley (Kingsley to Madison) and Kingsley (Main to First) Street | 1337000 | NULL | First and Ashley (Kingsley to Madison) and Kingsley (Main to First) | NULL | NULL | 11 | Address street condition in conjunction with DDA project | Utilize a range of pavement treatments appropriate to street condition in coordination with DDA project to restore First and Ashley Streets to two way; also cooridinate with associated water replacements and consolidations | NULL | Yes | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 1337000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Hutchinson, Nick | 43412 | 0 | Fall 18: added | NULL | 0 | 0 | TRSC2012.jpg | Dykman, Dave | Rolla, Liz | Miller, Amber | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 69.45 | 1 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | 1 | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2217 | TR-SC-20-13 | William (Ashley St to State) Pavement Treatments | 368000 | NULL | William (Ashley St to State) | NULL | NULL | 11 | Address street condition | Pavment treatments in conjunction with DDA William Protected Bikeway | NULL | Yes | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 2 | 2018 | 1 | 2019 | 10000 | 2 | 2019 | 4 | 2019 | 358000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Dykman, Dave | Gosselin, Deb | 43430 | 0 | Fall 18: new | NULL | 0 | 0 | TRSC2013.jpg | Dykman, Dave | Rolla, Liz | Miller, Amber | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 62.86 | 5 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | NULL | 1 | NULL | NULL | NULL | NULL | NULL | 0 | 1 | 1 | NULL | NULL | 0
2220 | UT-ST-20-06 | Washington (First to Third) Stormwater | 550000 | NULL | Washington (First to Third) | NULL | NULL | 13 | Green Streets stormwater improvements | Green Streets stormwater improvements in conjunction with street reconstruction project; also coordinate with water project; in DDA; coordinate with bicycle boulevard project | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 3 | 2024 | 4 | 2024 | 50000 | 2 | 2025 | 4 | 2025 | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Lawson, Jennifer | Lawson, Jennifer | 43400 | 0 | NULL | NULL | 0 | 0 | UTST2006.jpg | Lawson, Jennifer | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Condition Analysis | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | NULL | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2233 | TR-SC-20-17 | State St (I-94 WB Ramps to Oakbrook) Road Improvements | 16350000 | NULL | State Street (I-94 WB Ramps to Oakbrook) | NULL | NULL | 11 | Address motorized and non-motorized imrpovements per State Street Corridor Transporation Study | Address motorized and non-motorized imrpovements per State Street Corridor Transportation Study | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2027 | 4 | 2028 | 16350000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43417 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2017.jpg | Cooper, Eli | Liu, Luke | Carson, Chris | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 1 | State Street Corridor Transporation Study | NULL | NULL | NULL | Programmed | Inactive | 63.74 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2224 | MF-SW-20-02 | Termination of Public Street Dead Ends (Solid Waste) | 50000 | NULL | Locations as determined | NULL | NULL | 15 | Emergency access and user level of service. | Provide better maneuverability for refuse vehicles; improve emergency and plow access; type of turn-around requires determining design vehicle; natural features; stormwater management; Parks. Madison Pl., Dicken, Cedar Bend, and 8th are current prospects | NULL | No | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 4 | 2018 | 2 | 2019 | 50000 | 0 | NULL | 0 | NULL | 0 | 4 | 2018 | 2 | 2019 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Slizewski, Brian | Gosselin, Deb | 43410 | 0 | Fall 18: killed it as TR-NS-10-06 going forward and renamed to this to show in Solid Waste. | NULL | 0 | 0 | MFSW2002.jpg | Carson, Chris | Slizewski, Brian | Gomes, Christina | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 38.11 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | 1 | NULL | NULL | 1 | NULL | NULL | 1 | 3 | NULL | NULL | 0 | 0 | 1 | NULL | NULL | 1
2225 | TR-SC-20-14 | Nixon (Huron Pkwy to S of Bluett) Phase 1 Road Improvements | 2020000 | NULL | Nixon (Huron Pkwy to Bluett) | NULL | NULL | 11 | Address changing transporation needs | NULL | NULL | Yes | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2025 | 4 | 2025 | 2020000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43417 | 0 | NULL | NULL | 0 | 0 | TRSC2014.jpg | Wall, Chris | Hutchinson, Nick | Kotlyar, Igor | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 59.34 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2240 | UT-ST-20-12 | State St (Interchange at I-94 Bridge and Ramp) Stormwater | 2300000 | NULL | State St (Interchange at I-94 Bridge and Ramp) | NULL | NULL | 13 | Green Street Improvements | Green Street Improvements in conjunction with street project TR-SC-20-49 | NULL | NULL | 0 | 0 | 9 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2028 | 4 | 2028 | 2300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43425 | 0 | Fall 18: added; time frame is placeholder | NULL | 0 | 0 | UTST2012.jpg | Cooper, Eli | Carson, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | State Street Corridor Transportation Study | NULL | NULL | NULL | Programmed | Inactive | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2226 | TR-SC-20-15 | Nixon (Bluett to Dhu Varren) Phase 2 Road Improvements
Phase 2 Road Improvements | 3494000 | NULL | Nixon (Bluett to Dhu Varren) | NULL | NULL | 11 | Address changing transporation needs | Improvements per corridor study design phase | NULL | NULL | 0 | 0 | 6 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2026 | 4 | 2026 | 3494000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2015.jpg | Wall, Chris | Hutchinson, Nick | Kotlyar, Igor | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | Nixon Road Corridor Study | NULL | NULL | NULL | Programmed | Inactive | 59.34 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2227 | TR-SC-20-16 | Nixon (Dhu Varren to S of M-14) Phase 3 Road Improvements | 2000000 | NULL | Nixon (Dhu Varren to S of M-14) | NULL | NULL | 11 | Address changing traffic needs | Improvements per corridor study design phase | NULL | Yes | 0 | 0 | 6 | NULL | NULL | 1 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2027 | 4 | 2027 | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43430 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2016.jpg | Wall, Chris | Kotlyar, Igor | Hutchinson, Nick | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Nixon Road Corridor Study | NULL | NULL | NULL | Programmed | Inactive | 59.34 | 12 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2228 | UT-ST-20-07 | Nixon (Huron Pkwy to S of Bluett) Phase 1 Stormwater Improvements | 980000 | NULL | Nixon (Huron Pkwy to S of Bluett) | NULL | NULL | 13 | Provide Green Steets stormwater improvements | Provide Green Steets stormwater improvements; coordinate with street construction | NULL | Yes | 0 | 0 | 1 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2025 | 4 | 2025 | 980000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43417 | 0 | Fall18: added | NULL | 0 | 0 | UTST2007.jpg | Wall, Chris | Lawson, Jennifer | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 1 | Customer Level of Service | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 0 | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2232 | UT-WS-20-24 | Nixon (S of Bluett to S of Traver) Phase 2 Water Improvements | 216000 | NULL | Nixon (S of Bluett to S of Traver) | NULL | NULL | 14 | Upside water main | Upsize 12" water maim to 16"; coordinate with raod and stormwater improvements | NULL | NULL | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 2 | 2026 | 4 | 2027 | 216000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Wall, Chris | Gosselin, Deb | 43439 | 0 | Fall 18 new | NULL | 0 | 0 | UTWS2024.jpg | Baughman, Troy | Wall, Chris | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | Programmed | Design | 45.34 | 22 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2234 | TR-SC-20-18 | State St (Interchange at I-94 Bridge and Ramp) Reconstruction | 9450000 | NULL | State Street Interchange at I-94 | NULL | NULL | 11 | Address motorized and non-motorized imrpovements per State Street Corridor Transportation Study | Address motorized and non-motorized imrpovements per State Street Corridor Transportation Study | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 9450000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43417 | 0 | Fall 18: new | NULL | 0 | 0 | TRSC2018.jpg | Cooper, Eli | Liu, Luke | Carson, Chris | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 1 | State Street Coridor Transporation Plan | NULL | NULL | NULL | Programmed | Inactive | 63.74 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0
2235 | TR-SC-20-19 | State St (Ellsworth to I-94 EB Ramp) Road Improvements | 6200000 | NULL | State St (Ellsworth to I-94 EB Ramp | NULL | NULL | 11 | Address motorized and non-motorized imrpovements per State Street Corridor Transportation Study | Address motorized and non-motorized imrpovements per State Street Corridor Transportation Study | NULL | Yes | 0 | 0 | 2 | NULL | NULL | 0 | 0 | NULL | 0 | NULL | 0 | NULL | 0 | 0 | NULL | 0 | NULL | 0 | 3 | 2029 | 4 | 2030 | 6200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Cooper, Eli | Gosselin, Deb | 43417 | 0 | Fall 18 new | NULL | 0 | 0 | TRSC2019.jpg | Cooper, Eli | Liu, Luke | Carson, Chris | NULL | NULL | 1 | Citizen/Property Owner | NULL | NULL | NULL | 1 | Capacity Analysis | Customer Level of Service | NULL | NULL | 1 | State Street Corridor Transporation Study | NULL | NULL | NULL | Programmed | Inactive | 63.74 | 3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | 0 | NULL | 0 | 0 | NULL | NULL | 0 | NULL | No | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 0 | 0 | 0 | NULL | NULL | 0

## Funding Info
ProjectExpenseDetails |  |  |  |  | ProjectFundingLines | [7 empty] | Revenue Source |  | ProjectRevenueDetails
ProjectExpenseDetailId | ProjectId | FiscalYear | Object | Amount | ProjectId | Fund | Agency | XOrg | Activity | Functions | ID | CIP_Team_Member | REVENUE_SOURCE | REV_SOURCE_NAME | ProjectRevenueDetailId | ProjectId | FiscalYear | RevSource | Amount
448 | 87 | 2008 | 4520 | 300000 | 87 | 42 | 73 | NULL | NULL | 0 | 1 | Amicangelo, Mike | 2324 | AATA Grant | 181 | 87 | 2019 | 2742 | 725000
449 | 87 | 2009 | 4520 | 100000 | 92 | 98 | 73 | 9505 | 9000 | 0 | 2 | Bahl, Sumedh | 2722 | Act 51 Local Streets | 1884 | 92 | 2013 | 2245 | 850000
577 | 92 | 2005 | 4520 | 30000 | 93 | $NO$ | NULL | NULL | NULL | NULL | 3 | Baughman, Troy | 2721 | Act 51 Major Streets | 209 | 92 | 2013 | 2742 | 800000
471 | 92 | 2006 | 2100 | 150000 | 97 | 76 | 73 | 9510 | 9000 | 0 | 4 | Bemish, KC | 2770 | Affordable Housing | 212 | 92 | 2013 | 6647 | 950000
472 | 92 | 2007 | 4520 | 1095250 | 392 | 18 | 60 | 9254 | 6925 | 9018 | 5 | Bogan, Ken | 2748 | Airport | 1885 | 92 | 2014 | 2245 | 850000
662 | 97 | 2002 | 2100 | 400000 | 393 | 18 | 60 | 9258 | 6925 | 9018 | 73 | Miller, Amber | 2761 | Alternative Transportation | 1886 | 92 | 2014 | 2742 | 4000000
141 | 97 | 2006 | 2100 | 2100000 | 394 | 18 | 60 | 9680 | 6920 | 9018 | 76 | Borneman, Dave | 2778 | Comm. Dev. Block Grants | 1887 | 92 | 2014 | 6647 | 4000000
309 | 97 | 2006 | 5190 | 2500000 | 399 | 18 | 60 | 9200 | 6920 | 9018 | 77 | Coleman, Kayla | 2162 | Community Foundation Grant | 667 | 97 | 2004 | 6907 | 0
142 | 97 | 2007 | 2100 | 400000 | 401 | 18 | 60 | 9603 | 6960 | 9018 | 78 | Farrackand, Warreka | 6987 | Contributions and Memorials | 619 | 97 | 2005 | 6907 | 400000
310 | 97 | 2007 | 5190 | 14100000 | 406 | 18 | 60 | 9302 | 6920 | 9018 | 10 | Cooper, Eli | 0100 | County Mental Health Millage | 231 | 97 | 2006 | 6907 | 1000000
327 | 97 | 2008 | 2100 | 400000 | 407 | 18 | 60 | 9517 | 6930 | 9018 | 11 | Cozart, Mark | 6814 | County Millage Reimbursement | 232 | 97 | 2007 | 6907 | 1200000
328 | 97 | 2008 | 5190 | 13100000 | 408 | $NO$ | NULL | NULL | NULL | NULL | 12 | Crum, Lynn | 2703 | DDA | 233 | 97 | 2008 | 6907 | 1500000
405 | 97 | 2009 | 2100 | 400000 | 409 | 18 | 60 | 9516 | 6940 | 9018 | 13 | Dykman, Dave | 2763 | DDA Parking Fund | 234 | 97 | 2009 | 6907 | 3000000
406 | 97 | 2009 | 5190 | 14000000 | 410 | 18 | 60 | 9602 | 6960 | 9018 | 14 | Ernst, Kevin | 2730 | DDA Sidewalk and Streetscape Main | 235 | 97 | 2010 | 6907 | 2800000
407 | 97 | 2010 | 2100 | 200000 | 411 | 18 | 60 | 9504 | 6930 | 9018 | 79 | Gomes, Christina | 6988 | Developer Contributions | 236 | 97 | 2011 | 6907 | 2900000
408 | 97 | 2010 | 5190 | 4000000 | 412 | 71 | NULL | NULL | NULL | NULL | 16 | Gray, Kerry | 7119 | Developer Offset Mitigation | 237 | 97 | 2012 | 6907 | 4000000
409 | 97 | 2011 | 2100 | 100000 | 414 | 18 | 60 | 9508 | 6930 | 9018 | 17 | Hancock, Jerry | 2702 | Energy Fund | 655 | 97 | 2013 | 6907 | 94200000
410 | 97 | 2011 | 5190 | 1000000 | 415 | 18 | 60 | 9546 | 6940 | 9018 | 18 | Heatley, Alison | 2161 | Federal Railroad Admin. Grant | 1114 | 97 | 2014 | 6907 | 3760000
632 | 392 | 2005 | 4520 | 200000 | 416 | 18 | 60 | 9500 | 6914 | 9018 | 19 | Hupy, Craig | 2160 | FEMA Grant | 1787 | 97 | 2015 | 6907 | 3760000
571 | 392 | 2006 | 4520 | 95900 | 417 | 18 | 60 | 9605 | 6960 | 9018 | 20 | Hutchinson, Nick | 2710 | General Fund | 1788 | 97 | 2016 | 6907 | 3760000
572 | 392 | 2007 | 4520 | 95750 | 418 | 18 | 60 | 9503 | 6940 | 9018 | 21 | Kenzie, Earl | 2299 | MDOT Grant: No Local Match | 573 | 392 | 2006 | 6998 | 135000
633 | 393 | 2005 | 4520 | 170000 | 420 | 18 | 60 | 9301 | 6930 | 9018 | 80 | Kidwell-Bix, Jamie | 2296 | MDOT/Fed (STP,CMAQ.TAP, etc) | 574 | 393 | 2005 | 2718 | 50000
634 | 394 | 2005 | 4520 | 200000 | 421 | 18 | 60 | 9351 | 6940 | 9018 | 23 | Kotlyar, Igor | 2290 | MI: Econ. Dev. Corp. Grant | 3943 | 393 | 2023 | 2296 | 1000000
480 | 394 | 2006 | 4520 | 87700 | 422 | 18 | 60 | 9702 | 6930 | 9018 | 24 | Kulhanek, Matt | 2250 | MI: Energy Office Grant | 3189 | 393 | 2023 | 2336 | 1050000
624 | 399 | 2005 | 4520 | 593000 | 423 | 24 | 60 | 6000 | 9024 | 9000 | 25 | Kuras, Amy | 2245 | MI: MDEQ Grant (SAW, etc.) | 1791 | 393 | 2023 | 2710 | 50000
320 | 399 | 2006 | 4520 | 278923 | 535 | 99 | 73 | NULL | NULL | NULL | 26 | McKinnon, Kelli | 2260 | MI: Other State Grants (Airport, MDNR) | 1790 | 393 | 2023 | 2771 | 200000
321 | 399 | 2007 | 4520 | 328750 | 545 | 74 | 40 | 9430 | 9000 | 0 | 81 | Roselle, Tina | 2724 | Open Space & Park. Acq. | 3942 | 393 | 2024 | 2336 | 1050000
625 | 401 | 2005 | 4520 | 778000 | 568 | 42 | 73 | 9504 | 9000 | 0 | 28 | Naud, Matt | 2771 | Parks Maint. And Capital Impr.Millage | 3941 | 393 | 2024 | 2710 | 1050000
322 | 401 | 2006 | 4520 | 94260 | 575 | 89 | 40 | 9840 | NULL | 0 | 29 | Nearing, Mike | 2734 | Parks Memorials and Contributions | 575 | 394 | 2007 | 6998 | 300000
323 | 401 | 2007 | 4520 | 284700 | 595 | 43 | NULL | NULL | NULL | NULL | 30 | Oetzel, Ken | 2756 | Public Art (From Exst. Pots) | 565 | 399 | 2005 | 6998 | 593000
631 | 406 | 2005 | 4520 | 550000 | 597 | 43 | NULL | 9269 | NULL | NULL | 31 | Pennington, Kirk | 2743 | Sanitary System | 434 | 399 | 2006 | 6998 | 299000
617 | 407 | 2005 | 4520 | 300000 | 599 | 76 | 40 | 9777 | 4573 | 0 | 82 | Waldsmith, Matt | 2772 | Solid Waste | 435 | 399 | 2007 | 6998 | 350000
175 | 407 | 2006 | 4520 | 137700 | 600 | 43 | NULL | NULL | NULL | NULL | 33 | Pollay, Susan | 1620 | Spec. Assess. Curb & Gutter | 566 | 401 | 2005 | 6998 | 778000
614 | 409 | 2005 | 5420 | 135000 | 603 | 99 | 73 | NULL | NULL | 0 | 34 | Praschan, Marti | 1626 | Spec. Assess. Road | 436 | 401 | 2006 | 6998 | 100000
304 | 409 | 2006 | 4520 | 429500 | 621 | 76 | 73 | 9508 | 9000 | 0 | 35 | Pulcipher, Connie | 1627 | Spec. Assess. Sanitary | 437 | 401 | 2007 | 6998 | 300000
615 | 410 | 2005 | 4520 | 70000 | 626 | 48 | 40 | NULL | NULL | 0 | 36 | Rampson, Wendy | 1625 | Spec. Assess. Sidewalk | 572 | 406 | 2005 | 6998 | 550000
664 | 410 | 2006 | 4520 | 40000 | 627 | 48 | 40 | NULL | NULL | 0 | 37 | Rolla, Liz | 1624 | Spec. Assess. Sreet Lights | 559 | 407 | 2005 | 2703 | 296300
616 | 412 | 2005 | 4520 | 95000 | 628 | 48 | 40 | NULL | NULL | 0 | 38 | Sanford, Larry | 1623 | Spec. Assess. Storm Sewer | 22 | 407 | 2006 | 2746 | 305900
308 | 412 | 2006 | 4520 | 96720 | 630 | 00CP | 40 | 9761 | 4542 | 0 | 39 | Sheehan, Harry | 1629 | Spec. Assess. Water | 558 | 407 | 2008 | 2771 | 130000
620 | 414 | 2005 | 4520 | 100000 | 633 | 62 | 40 | 9679 | 4542 | 0 | 83 | Stephens, Peter | 2769 | Stormwater System | 946 | 407 | 2008 | 6998 | 550000
621 | 415 | 2005 | 4250 | 145000 | 635 | 21 | 40 | NULL | NULL | 0 | 41 | Sipowski, Les | 2762 | Street Millage | 555 | 409 | 2005 | 6998 | 135000
319 | 415 | 2006 | 4520 | 29180 | 637 | 21 | 40 | 4210 | 4124 | 0 | 42 | Slotten, Cress | 2336 | UM Reimbursement | 421 | 409 | 2006 | 6998 | 450000
629 | 416 | 2005 | 4520 | 50000 | 643 | 31 | 40 | 4500 | 9000 | 0 | 43 | Smith, Colin | 2175 | US Dept. of Energy Grant | 622 | 410 | 2006 | 6998 | 20000
479 | 416 | 2007 | 4520 | 189800 | 644 | $NO$ | NULL | NULL | NULL | NULL | 44 | Steglitz, Brian | 2180 | US Dept. of Trans. Grant (TIGER) | 944 | 411 | 2005 | 6998 | 153000
622 | 417 | 2005 | 4520 | 189000 | 645 | 21 | 40 | NULL | NULL | 0 | 84 | Nelson, Jenn | 2144 | US EPA Grant | 557 | 412 | 2011 | 6998 | 100000
566 | 417 | 2006 | 4520 | 187700 | 649 | $NO$ | 40 | 9027 | NULL | 0 | 85 | Liu, Luke | 2170 | US HUD Grant | 430 | 412 | 2012 | 6998 | 175000
626 | 418 | 2005 | 4520 | 150000 | 651 | 62 | 40 | 9787 | 4542 | 0 | 86 | Elenbaas, Chris | 2159 | Washtenaw County Grant | 561 | 414 | 2005 | 6998 | 100000
324 | 418 | 2007 | 4520 | 137250 | 652 | 21 | 40 | 9850 | 1000 | 0 | 48 | Robinson, Molly | 2338 | Washtenaw County Parks Grant | 562 | 415 | 2005 | 6998 | 145000
619 | 420 | 2005 | 4520 | 500000 | 655 | 21 | 40 | NULL | NULL | 0 | 49 | Warba, Matt | 2742 | Water System | 431 | 415 | 2006 | 6998 | 30000
628 | 421 | 2005 | 4520 | 150000 | 659 | 62 | 40 | NULL | NULL | 0 | 50 | Warrow, Anne | 9999 | z800 MHZ SYST NOTE PROCEEDS | 1483 | 415 | 2014 | 2771 | 60000
325 | 421 | 2006 | 4520 | 101800 | 660 | 62 | 40 | 9698 | 4573 | 0 | 51 | Wooden, Dan | 2151 | zArgo Dam Greenways Grant | 570 | 416 | 2005 | 6998 | 37000
326 | 421 | 2007 | 4520 | 280923 | 663 | 21 | 40 | NULL | NULL | 0 | 52 | Woodward, Nichole | 1512 | zAs-Builts | 441 | 416 | 2007 | 6998 | 200000
630 | 422 | 2005 | 4520 | 70000 | 664 | 21 | 40 | NULL | NULL | 0 | 87 | Landefeld, Josh | 6907 | zBond/Note Proceeds | 933 | 416 | 2009 | 6998 | 263000
578 | 423 | 2006 | 4520 | 1995080 | 665 | $NO$ | 40 | 9035 | 4542 | 0 | 54 | Fojtik, Chuck | 6647 | zContributed Capital-Customers | 563 | 417 | 2005 | 6998 | 189000
579 | 423 | 2007 | 4520 | 2054900 | 672 | 62 | 40 | NULL | NULL | 0 | 55 | Kahan, Jeff | 6640 | zCONTRIBUTED CAPITAL-OTHER FUND | 442 | 417 | 2006 | 6998 | 200000
580 | 423 | 2008 | 4520 | 2138000 | 676 | 62 | 40 | NULL | NULL | 0 | 88 | Wiczorek, Glen | 1119 | zDDA Taxes | 567 | 418 | 2005 | 6998 | 150000
581 | 423 | 2009 | 4520 | 2202140 | 679 | 62 | 40 | NULL | NULL | 0 | 57 | Stone, Nancy | 1113 | zDebt Service Levy | 438 | 418 | 2007 | 6998 | 150000
582 | 423 | 2010 | 4520 | 2208204.2 | 687 | 62 | 40 | NULL | NULL | 0 | 58 | Saam, Cheryl | 5407 | zDonations | 560 | 420 | 2005 | 6998 | 500000
583 | 423 | 2011 | 4520 | 2274450.3 | 690 | 21 | 40 | 9036 | 4542 | 0 | 60 | Crawford, Tom | 1112 | zEmployee Benefits Levy | 439 | 421 | 2006 | 6998 | 110000
584 | 423 | 2012 | 4520 | 2342683.8 | 695 | 48 | 40 | 9607 | NULL | 0 | 89 | Matthews, Paul | 7918 | zFleet Operation - Fund 0018 | 440 | 421 | 2007 | 6998 | 289000
637 | 545 | 2007 | 4520 | 60000 | 698 | $NO$ | NULL | NULL | NULL | NULL | 62 | Lawson, Jennifer | 1116 | zINDUSTRIAL FACILITIES TAX | 571 | 422 | 2005 | 2718 | 48000
651 | 545 | 2008 | 4520 | 200000 | 700 | 8 | 40 | 9505 | 9005 | 0 | 63 | Carson, Chris | 1518 | zInspection | 1473 | 422 | 2013 | 2159 | 400000
570 | 568 | 2005 | 4520 | 25000 | 709 | $NO$ | NULL | NULL | NULL | NULL | 90 | Redinger, Cynthia | 7111 | zMetered Service | 1849 | 422 | 2013 | 2245 | 300000
435 | 568 | 2006 | 2100 | 79500 | 725 | 95 | 73 | 9502 | 9000 | 0 | 65 | Elias, Abby | 6999 | zMiscellaneous | 1850 | 422 | 2013 | 5407 | 100000
436 | 568 | 2007 | 2100 | 178750 | 726 | 95 | 73 | 9506 | 9000 | 0 | 66 | TBD | 1111 | zOperating Levy | 1793 | 423 | 2005 | 2724 | 2000000
438 | 568 | 2008 | 4450 | 105000 | 734 | 76 | 40 | 9010 | 4573 | 0 | 91 | Allen, Jane | 27X2 | zOPERATING TRANSFER FROM 0002 | 423 | 423 | 2006 | 2724 | 2000000
439 | 568 | 2008 | 4520 | 113000 | 736 | 21 | 40 | 9046 | NULL | 0 | 68 | Thacher, Jill | 2705 | zOPERATING TRANSFER FROM 0005 | 424 | 423 | 2007 | 2724 | 4000000
635 | 568 | 2008 | 5190 | 1582000 | 836 | 95 | 73 | 9501 | 9000 | 0 | 69 | Gosselin, Deb | 2712 | zOPERATING TRANSFER FROM 0012 | 425 | 423 | 2008 | 2724 | 4000000
469 | 575 | 2008 | 4520 | 700000 | 837 | 95 | 73 | 9503 | 9000 | 0 | 70 | Norman, Rick | 2718 | zOPERATING TRANSFER FROM 0018 | 426 | 423 | 2009 | 2724 | 3000000
638 | 595 | 2008 | 4520 | 160000 | 838 | 42 | 73 | NULL | NULL | 0 | 71 | Geisler, Nate | 2727 | zOPERATING TRANSFER FROM 0027 | 427 | 423 | 2010 | 2724 | 3000000
639 | 595 | 2009 | 4520 | 375000 | 843 | 76 | 73 | 9511 | 9000 | 0 | 72 | Taylor, Ellen | 2745 | zOPERATING TRANSFER FROM 0045 | 428 | 423 | 2011 | 2724 | 2000000
331 | 597 | 2010 | 2100 | 100000 | 844 | 69 | 73 | NULL | NULL | 0 | 74 | Hall, Jennifer | 2746 | zOPERATING TRANSFER FROM 0046 | 582 | 423 | 2012 | 2724 | 2000000
332 | 597 | 2010 | 5190 | 400000 | 845 | 69 | 73 | NULL | NULL | 0 | 75 | Slizewski, Brian | 2768 | zOPERATING TRANSFER FROM 0068 | 1794 | 423 | 2013 | 2724 | 2000000
64 | 600 | 2009 | 4520 | 200000 | 847 | 69 | NULL | NULL | NULL | NULL | 92 | Lenart, Brent | 2774 | zOPERATING TRANSFER FROM 0074 | 1795 | 423 | 2014 | 2724 | 2000000
77 | 600 | 2010 | 4520 | 160000 | 849 | 69 | NULL | NULL | NULL | NULL | 93 | Englet, Chris | 2776 | zOPERATING TRANSFER FROM 0076 | 1796 | 423 | 2015 | 2724 | 2000000
653 | 603 | 1999 | 4520 | 61000 | 852 | 42 | NULL | NULL | NULL | NULL | 94 | Hanzel, Hillary | 2782 | zOPERATING TRANSFER FROM 0082 | 1797 | 423 | 2016 | 2724 | 2000000
65 | 603 | 2008 | 4520 | 2398000 | 854 | 42 | 40 | 9032 | 4573 | 0 | 95 | Summersgill, Kathleen | 2793 | zOPERATING TRANSFER FROM 0093 | 1798 | 423 | 2017 | 2724 | 2000000
66 | 603 | 2009 | 4520 | 767000 | 857 | 92 | 40 | 9033 | 9000 | 0 | 96 | Stetson, Jese | 2795 | zOPERATING TRANSFER FROM 0095 | 2254 | 423 | 2018 | 2724 | 2000000
67 | 603 | 2010 | 4520 | 2056000 | 858 | 92 | 40 | 9033 | 9000 | 0 | 97 | Ferrell, Ryan | 2797 | zOPERATING TRANSFER FROM 0097 | 2255 | 423 | 2019 | 2724 | 2000000
68 | 603 | 2011 | 4520 | 1619000 | 859 | 92 | 40 | 9435 | 9000 | 0 | 98 | Tefft, Emily | 27CP | zOPERATING TRANSFER FROM 00CP | 2272 | 423 | 2020 | 2724 | 2000000
69 | 603 | 2012 | 4520 | 5553000 | 863 | 42 | NULL | NULL | NULL | NULL | 99 | Wall, Chris | 1125 | zParks Maintenance & Repair | 2517 | 423 | 2021 | 2724 | 2000000
494 | 621 | 2005 | 2100 | 222000 | 864 | 42 | NULL | NULL | NULL | NULL | 100 | Seyfarth, Heather | 1118 | zParks Rehab Levy | 2518 | 423 | 2022 | 2724 | 2000000
495 | 621 | 2005 | 5190 | 150000 | 866 | 69 | 40 | 9698 | NULL | 0 | 101 | Stults, Missy | 6998 | zPrior Year Fund Balance | 3029 | 423 | 2023 | 2724 | 2000000
330 | 621 | 2006 | 2100 | 137700 | 871 | 69 | NULL | NULL | NULL | 0 | 102 | MacDonald, Josh | 1114 | zRefuse Collection Levy | 3101 | 423 | 2024 | 2724 | 2000000
311 | 621 | 2006 | 5190 | 1228000 | 872 | 42 | NULL | NULL | NULL | NULL | 103 | Hess, Raymond | 1628 | zSPECIAL ASSESS-OTHER | 3929 | 423 | 2025 | 2724 | 2000000
387 | 626 | 2005 | 4520 | 880000 | 873 | 99 | 73 | NULL | NULL | 0 | 104 | Humphriss, Tesha | 7113 | zStormwater Service | 3930 | 423 | 2026 | 2724 | 12000000
393 | 627 | 2010 | 4520 | 291000 | 874 | 42 | 73 | NULL | NULL | 0 |  |  | 1120 | zStreet Resurfacing Levy | 939 | 545 | 2006 | 6907 | 60000
399 | 628 | 2011 | 4520 | 31000 | 876 | 42 | NULL | NULL | NULL | NULL |  |  | 27XX | zTRANS FROM OTHER FUNDS | 579 | 545 | 2007 | 6907 | 390000
400 | 628 | 2012 | 4520 | 269000 | 879 | 42 | NULL | NULL | NULL | NULL |  |  | 2741 | zTRANS FROM PARKS MILLAGE FUND | 128 | 568 | 2015 | 2742 | 17000
333 | 635 | 2009 | 4520 | 90000 | 880 | 99 | 73 | NULL | NULL | 0 |  |  | 2298 | zU OF M PROJECT REIMBURSEMENT | 577 | 568 | 2016 | 2742 | 105000
189 | 637 | 2007 | 4520 | 86600 | 883 | 42 | 40 | NULL | NULL | 0 |  |  | 2221 | zWT/Gas Major Streets | 2756 | 568 | 2017 | 2742 | 20000
193 | 643 | 2006 | 5190 | 121300 | 885 | 99 | 73 | NULL | NULL | 0 |  |  |  |  | 2757 | 568 | 2022 | 2742
194 | 643 | 2007 | 5190 | 120250 | 887 | 99 | 73 | NULL | NULL | 0 |  |  |  |  | 2852 | 568 | 2023 | 2742
195 | 643 | 2008 | 5190 | 150000 | 889 | 95 | 40 | 9504 | 4573 | 0 |  |  |  |  | 2944 | 568 | 2024 | 2742
196 | 643 | 2009 | 5190 | 150000 | 891 | 99 | 73 | NULL | NULL | 0 |  |  |  |  | 2945 | 568 | 2025 | 2742
197 | 643 | 2010 | 5190 | 150000 | 892 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 207 | 575 | 2009 | 6907 | 500000
198 | 643 | 2011 | 5190 | 150000 | 893 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 631 | 575 | 2010 | 6907 | 1000000
649 | 643 | 2012 | 5190 | 150000 | 900 | 76 | 40 | 9708 | NULL | 0 |  |  |  |  | 580 | 595 | 2022 | 2743 | 290000
650 | 643 | 2013 | 5190 | 150000 | 901 | 88 | 73 | NULL | NULL | 0 |  |  |  |  | 581 | 595 | 2023 | 2743 | 435000
534 | 651 | 2005 | 4520 | 3200000 | 902 | 43 | 73 | NULL | NULL | 0 |  |  |  |  | 288 | 597 | 2019 | 2743 | 390000
185 | 651 | 2006 | 4520 | 2536000 | 903 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 3667 | 597 | 2020 | 2743 | 920000
186 | 651 | 2007 | 4520 | 730000 | 905 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 229 | 600 | 2025 | 2743 | 616000
78 | 652 | 2006 | 2100 | 250000 | 906 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 230 | 600 | 2026 | 2743 | 784000
79 | 652 | 2007 | 2100 | 200000 | 907 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 603 | 603 | 1999 | 2776 | 61000
80 | 652 | 2008 | 2100 | 50000 | 908 | 74 | 40 | 9776 | 9000 | 0 |  |  |  |  | 220 | 603 | 2010 | 6907 | 2398000
191 | 652 | 2008 | 4520 | 10000 | 910 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 221 | 603 | 2011 | 6907 | 767000
184 | 660 | 2005 | 4520 | 3400000 | 911 | 88 | 73 | NULL | NULL | 0 |  |  |  |  | 222 | 603 | 2012 | 6907 | 2056000
597 | 660 | 2006 | 4520 | 2599000 | 913 | 69 | 73 | NULL | NULL | 0 |  |  |  |  | 223 | 603 | 2013 | 6907 | 1619000
385 | 663 | 2008 | 4520 | 20000 | 915 | 82 | 40 | 9438 | 9000 | 0 |  |  |  |  | 224 | 603 | 2014 | 6907 | 5553000
386 | 663 | 2009 | 4520 | 180000 | 924 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 265 | 621 | 2006 | 2776 | 256000
334 | 665 | 2007 | 4520 | 433000 | 925 | 92 | 73 | 9774 | 9000 | 0 |  |  |  |  | 266 | 621 | 2007 | 2776 | 1708500
187 | 672 | 2008 | 4520 | 30000 | 930 | 76 | 40 | 9711 | NULL | 0 |  |  |  |  | 474 | 626 | 2005 | 2260 | 792000
419 | 672 | 2009 | 4520 | 170000 | 931 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 576 | 626 | 2005 | 2748 | 88000
645 | 672 | 2009 | 5196 | 200000 | 932 | 95 | 40 | 9011 | 4573 | 0 |  |  |  |  | 833 | 627 | 2019 | 2260 | 1479150
188 | 687 | 2008 | 4520 | 22500 | 934 | 43 | 73 | 9174 | NULL | 0 |  |  |  |  | 514 | 627 | 2019 | 2748 | 77850
418 | 687 | 2009 | 4520 | 127500 | 935 | 31 | 40 | 9734 | 4542 | 0 |  |  |  |  | 515 | 628 | 2024 | 2260 | 737200
646 | 687 | 2009 | 5196 | 150000 | 937 | 31 | 40 | NULL | NULL | 0 |  |  |  |  | 517 | 628 | 2024 | 2748 | 38800
91 | 690 | 2006 | 4520 | 125400 | 938 | 31 | 40 | NULL | NULL | 0 |  |  |  |  | 505 | 635 | 1986 | 6988 | 10000
416 | 690 | 2007 | 4520 | 547000 | 939 | 31 | 40 | NULL | NULL | 0 |  |  |  |  | 67 | 635 | 2025 | 2721 | 80000
644 | 690 | 2007 | 5196 | 1500000 | 941 | 31 | 40 | NULL | NULL | 0 |  |  |  |  | 45 | 637 | 2007 | 2721 | 50000
417 | 690 | 2008 | 4520 | 535000 | 942 | 31 | 40 | NULL | NULL | 0 |  |  |  |  | 46 | 637 | 2007 | 6988 | 40000
388 | 695 | 2007 | 4520 | 70000 | 943 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 24 | 643 | 2006 | 1625 | 150000
395 | 695 | 2008 | 4520 | 470000 | 944 | 61 | 40 | NULL | NULL | 0 |  |  |  |  | 26 | 643 | 2007 | 1625 | 150000
587 | 700 | 2006 | 4520 | 821300 | 945 | 31 | 40 | NULL | NULL | 0 |  |  |  |  | 27 | 643 | 2008 | 1625 | 150000
590 | 700 | 2006 | 5190 | 15000000 | 949 | 10 | 40 | 9702 | NULL | 0 |  |  |  |  | 29 | 643 | 2009 | 1625 | 150000
591 | 700 | 2007 | 4520 | 1253250 | 952 | 62 | 40 | 9705 | NULL | 0 |  |  |  |  | 31 | 643 | 2010 | 1625 | 150000
592 | 700 | 2007 | 5190 | 29150000 | 953 | 62 | 40 | 9704 | NULL | 0 |  |  |  |  | 33 | 643 | 2011 | 1625 | 150000
593 | 700 | 2008 | 4520 | 850000 | 954 | 62 | 40 | 9703 | NULL | 0 |  |  |  |  | 35 | 643 | 2012 | 1625 | 150000
594 | 700 | 2008 | 5190 | 22850000 | 956 | 97 | 71 | 9507 | 9000 | 0 |  |  |  |  | 37 | 643 | 2013 | 1625 | 150000
573 | 725 | 2005 | 4520 | 111350 | 958 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2379 | 644 | 2016 | 1111 | 10000
440 | 725 | 2006 | 2100 | 50000 | 959 | 10 | 60 | NULL | NULL | 0 |  |  |  |  | 2383 | 644 | 2016 | 1113 | 200000
441 | 725 | 2006 | 4450 | 23150 | 960 | 14 | NULL | NULL | NULL | NULL |  |  |  |  | 2380 | 644 | 2017 | 1112 | 20000
443 | 725 | 2006 | 4520 | 30000 | 963 | 62 | 40 | 9795 | 4542 | 0 |  |  |  |  | 2384 | 644 | 2017 | 1114 | 100000
442 | 725 | 2006 | 5190 | 450000 | 966 | 48 | 40 | NULL | NULL | 0 |  |  |  |  | 2385 | 644 | 2017 | 1116 | 10001
568 | 726 | 2005 | 4520 | 384000 | 967 | 48 | 40 | NULL | NULL | 0 |  |  |  |  | 778 | 649 | 2014 | 2299 | 300000
462 | 726 | 2006 | 2100 | 100000 | 968 | 48 | 40 | NULL | NULL | 0 |  |  |  |  | 1417 | 649 | 2014 | 2721 | 60000
192 | 736 | 2008 | 4520 | 105000 | 969 | 48 | 40 | NULL | NULL | 0 |  |  |  |  | 598 | 651 | 2005 | 2296 | 1200000
574 | 836 | 2005 | 4520 | 250000 | 970 | 48 | 40 | NULL | NULL | 0 |  |  |  |  | 597 | 651 | 2005 | 2762 | 2000000
444 | 836 | 2008 | 2100 | 200000 | 971 | 48 | 40 | NULL | NULL | 0 |  |  |  |  | 599 | 651 | 2006 | 2296 | 1800000
445 | 836 | 2008 | 4520 | 2000000 | 972 | 48 | 40 | NULL | NULL | 0 |  |  |  |  | 40 | 651 | 2006 | 2762 | 900000
575 | 837 | 2005 | 4520 | 447000 | 973 | 76 | 73 | 9509 | 9000 | 0 |  |  |  |  | 600 | 651 | 2007 | 2296 | 500000
458 | 837 | 2006 | 2100 | 200000 | 974 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 41 | 651 | 2007 | 2762 | 400000
459 | 837 | 2006 | 4450 | 80000 | 975 | 62 | 40 | 9698 | 4542 | 0 |  |  |  |  | 851 | 652 | 2007 | 2721 | 14375
460 | 837 | 2006 | 5190 | 4000000 | 978 | 74 | 40 | 9439 | 9000 | 0 |  |  |  |  | 852 | 652 | 2007 | 6988 | 20000
467 | 838 | 2008 | 2100 | 400000 | 980 | 61 | 40 | 9061 | 4542 | 0 |  |  |  |  | 54 | 652 | 2007 | 6998 | 360000
468 | 838 | 2009 | 4520 | 2400000 | 981 | 76 | 73 | 9512 | 9000 | 0 |  |  |  |  | 39 | 660 | 2005 | 6998 | 3400000
663 | 843 | 1999 | 2100 | 443000 | 984 | 4 | 40 | 9495 | 4501 | 0 |  |  |  |  | 461 | 660 | 2006 | 2296 | 1234000
314 | 843 | 2005 | 2100 | NULL | 985 | 95 | 73 | 9507 | 9000 | 0 |  |  |  |  | 460 | 660 | 2006 | 6998 | 1225000
313 | 843 | 2006 | 2100 | 520000 | 986 | 95 | 40 | 9012 | 4573 | 0 |  |  |  |  | 462 | 660 | 2007 | 2296 | 304000
315 | 843 | 2007 | 2100 | 350000 | 988 | 42 | 40 | 9030 | 4573 | 0 |  |  |  |  | 419 | 663 | 2010 | 2721 | 20000
316 | 843 | 2007 | 5190 | 16000000 | 989 | 42 | 40 | 9030 | 4573 | 0 |  |  |  |  | 444 | 663 | 2010 | 6988 | 100000
317 | 843 | 2008 | 2100 | 150000 | 990 | 99 | 40 | 9442 | 9000 | 0 |  |  |  |  | 420 | 663 | 2010 | 6998 | 80000
318 | 843 | 2008 | 5190 | 7000000 | 991 | 82 | 40 | 9443 | 9000 | 0 |  |  |  |  | 70 | 665 | 2017 | 2296 | 823640
106 | 844 | 2006 | 4520 | 100000 | 992 | 69 | 40 | 9444 | 9000 | 0 |  |  |  |  | 1418 | 665 | 2017 | 6999 | 6000
107 | 844 | 2007 | 4520 | 100000 | 995 | 69 | 40 | 9028 | NULL | 0 |  |  |  |  | 42 | 672 | 2008 | 2762 | 30000
108 | 844 | 2008 | 4520 | 100000 | 996 | 76 | 40 | 9503 | 4573 | 0 |  |  |  |  | 591 | 672 | 2009 | 2296 | 200000
109 | 844 | 2009 | 4520 | 100000 | 997 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 590 | 672 | 2009 | 2762 | 170000
110 | 844 | 2010 | 4520 | 100000 | 998 | 95 | 40 | 9506 | 4573 | 0 |  |  |  |  | 43 | 687 | 2008 | 2762 | 22500
111 | 844 | 2011 | 4520 | 100000 | 999 | 99 | 73 | NULL | NULL | 0 |  |  |  |  | 593 | 687 | 2009 | 2296 | 150000
112 | 844 | 2012 | 4520 | 100000 | 1000 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 592 | 687 | 2009 | 2762 | 127500
113 | 844 | 2013 | 4520 | 100000 | 1001 | 69 | 40 | 9445 | 9000 | 0 |  |  |  |  | 44 | 690 | 2006 | 6998 | 150000
114 | 844 | 2014 | 4520 | 100000 | 1002 | 69 | 73 | 9446 | 9000 | 0 |  |  |  |  | 589 | 690 | 2007 | 2296 | 309311
126 | 845 | 2006 | 4520 | 300000 | 1003 | 61 | 40 | NULL | NULL | 0 |  |  |  |  | 404 | 690 | 2007 | 6998 | 615000
127 | 845 | 2007 | 4520 | 300000 | 1004 | 62 | 40 | NULL | NULL | 0 |  |  |  |  | 596 | 690 | 2008 | 2296 | 1190689
128 | 845 | 2008 | 4520 | 300000 | 1006 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 488 | 690 | 2008 | 6998 | 535000
129 | 845 | 2009 | 4520 | 300000 | 1007 | 3 | 3 | NULL | NULL | 0 |  |  |  |  | 509 | 695 | 2007 | 2260 | 81900
130 | 845 | 2010 | 4520 | 300000 | 1008 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 469 | 695 | 2007 | 6998 | 2100
131 | 845 | 2011 | 4520 | 300000 | 1011 | 21 | 40 | 9029 | 4542 | 0 |  |  |  |  | 472 | 695 | 2008 | 2260 | 766000
132 | 845 | 2012 | 4520 | 300000 | 1012 | $NO$ | 40 | 8500 | NULL | 0 |  |  |  |  | 953 | 700 | 2007 | 6998 | 13950000
133 | 845 | 2013 | 4520 | 300000 | 1013 | $NO$ | 40 | 8500 | NULL | 0 |  |  |  |  | 586 | 700 | 2008 | 6998
134 | 845 | 2014 | 4520 | 300000 | 1016 | 18 | 60 | 9501 | 6914 | 9018 |  |  |  |  | 612 | 700 | 2009 | 6907
421 | 847 | 2008 | 2100 | 120000 | 1017 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1080 | 700 | 2010 | 6907 | 16390000
115 | 847 | 2008 | 4520 | 80000 | 1021 | 92 | 40 | 9816 | NULL | 0 |  |  |  |  | 1081 | 700 | 2010 | 6998 | 5790000
135 | 849 | 2006 | 4520 | 167200 | 1033 | 62 | 40 | NULL | NULL | 0 |  |  |  |  | 1079 | 700 | 2011 | 6907 | 11270000
137 | 849 | 2007 | 2100 | 734000 | 1034 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 309 | 725 | 2005 | 6907 | 111000
136 | 849 | 2007 | 4520 | 15000 | 1035 | 3 | 3 | NULL | NULL | 0 |  |  |  |  | 171 | 725 | 2007 | 6907 | 766000
138 | 849 | 2008 | 4520 | 200000 | 1036 | 21 | 40 | NULL | NULL | 0 |  |  |  |  | 200 | 726 | 2005 | 2795 | 350000
262 | 852 | 2009 | 4520 | 100000 | 1037 | 21 | 40 | 9039 | 4542 | 0 |  |  |  |  | 201 | 726 | 2005 | 6998 | 34000
263 | 852 | 2010 | 4520 | 170000 | 1038 | 97 | 71 | 9503 | 9000 | 0 |  |  |  |  | 202 | 726 | 2006 | 6998 | 141000
261 | 854 | 2006 | 4520 | 39000 | 1039 | 97 | 71 | 9506 | 9000 | 0 |  |  |  |  | 1462 | 736 | 2010 | 2721 | 150000
482 | 854 | 2007 | 4520 | 356250 | 1040 | 97 | 71 | 9505 | 9000 | 0 |  |  |  |  | 57 | 736 | 2013 | 2299 | 711000
485 | 857 | 2005 | 4520 | 90000 | 1041 | 72 | 71 | 9508 | 9000 | 0 |  |  |  |  | 178 | 836 | 2009 | 2742 | 300000
303 | 857 | 2006 | 4520 | 139000 | 1042 | 72 | 71 | 9509 | 9000 | 0 |  |  |  |  | 180 | 836 | 2010 | 2742 | 1700000
483 | 858 | 2005 | 4520 | 75000 | 1044 | $NO$ | 40 | 9065 | 4542 | 0 |  |  |  |  | 185 | 837 | 2005 | 6907 | 447000
288 | 858 | 2006 | 4520 | 109000 | 1045 | 62 | 40 | NULL | NULL | 0 |  |  |  |  | 186 | 837 | 2007 | 6907 | 6663000
484 | 859 | 2005 | 4520 | 75000 | 1046 | 99 | 73 | NULL | NULL | 0 |  |  |  |  | 206 | 838 | 2023 | 2742 | 500000
302 | 859 | 2006 | 4520 | 109000 | 1048 | 82 | 40 | 9448 | 9000 | 0 |  |  |  |  | 634 | 838 | 2024 | 2742 | 1250000
640 | 863 | 2008 | 4520 | 130000 | 1049 | 92 | 73 | 9449 | 9000 | 0 |  |  |  |  | 2943 | 838 | 2025 | 2742 | 1250000
491 | 864 | 2010 | 4520 | 40000 | 1051 | 92 | 73 | 9450 | 9000 | 0 |  |  |  |  | 621 | 843 | 1999 | 6907 | 443000
492 | 864 | 2011 | 4520 | 140000 | 1052 | 43 | 40 | 9803 | NULL | 0 |  |  |  |  | 283 | 843 | 2006 | 6907 | 700000
139 | 866 | 2006 | 4520 | 333600 | 1053 | 92 | 73 | 9451 | 9000 | 0 |  |  |  |  | 286 | 843 | 2007 | 6907 | 1060000
116 | 871 | 2007 | 4520 | 24500 | 1054 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 285 | 843 | 2008 | 6907 | 900000
430 | 871 | 2008 | 4520 | 50000 | 1055 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 287 | 843 | 2009 | 6907 | 5700000
298 | 872 | 2009 | 2100 | 350000 | 1056 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 683 | 843 | 2010 | 6907 | 26200000
488 | 872 | 2009 | 4520 | 670000 | 1058 | 42 | 40 | 9455 | 9000 | 0 |  |  |  |  | 1115 | 843 | 2011 | 6907 | 19800000
641 | 872 | 2010 | 4520 | 1000000 | 1059 | 92 | 73 | 9456 | 9000 | 0 |  |  |  |  | 314 | 844 | 2006 | 7113 | 100000
643 | 872 | 2011 | 4520 | 380000 | 1060 | 62 | 40 | 9712 | 9000 | 0 |  |  |  |  | 315 | 844 | 2007 | 7113 | 100000
270 | 873 | 2006 | 4520 | 100000 | 1061 | 21 | 40 | NULL | NULL | 0 |  |  |  |  | 316 | 844 | 2008 | 7113 | 100000
271 | 873 | 2007 | 4520 | 100000 | 1062 | 92 | 40 | 9814 | NULL | 0 |  |  |  |  | 317 | 844 | 2009 | 7113 | 100000
272 | 873 | 2008 | 4520 | 100000 | 1063 | 99 | 73 | NULL | NULL | 0 |  |  |  |  | 318 | 844 | 2010 | 7113 | 100000
273 | 873 | 2009 | 4520 | 100000 | 1064 | 42 | 73 | NULL | NULL | 0 |  |  |  |  | 319 | 844 | 2011 | 7113 | 100000
274 | 873 | 2010 | 4520 | 100000 | 1065 | 92 | 40 | 9823 | NULL | 0 |  |  |  |  | 320 | 844 | 2012 | 7113 | 300000
275 | 873 | 2011 | 4520 | 100000 | 1066 | 92 | 40 | 9817 | NULL | 0 |  |  |  |  | 331 | 845 | 2006 | 7113 | 300000
276 | 873 | 2012 | 4520 | 100000 | 1067 | 82 | 40 | 9452 | 9000 | 0 |  |  |  |  | 332 | 845 | 2007 | 7113 | 300000
277 | 873 | 2013 | 4520 | 100000 | 1068 | 92 | 40 | 9453 | 9000 | 0 |  |  |  |  | 333 | 845 | 2008 | 7113 | 300000
278 | 873 | 2014 | 4520 | 100000 | 1069 | 92 | 40 | 9454 | 9000 | 0 |  |  |  |  | 334 | 845 | 2009 | 7113 | 300000
279 | 874 | 2006 | 4520 | 200000 | 1070 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 335 | 845 | 2010 | 7113 | 300000
280 | 874 | 2007 | 4520 | 200000 | 1071 | 92 | 40 | 9813 | NULL | 0 |  |  |  |  | 336 | 845 | 2011 | 7113 | 300000
281 | 874 | 2008 | 4520 | 200000 | 1072 | 89 | 40 | 9842 | NULL | 0 |  |  |  |  | 337 | 845 | 2012 | 7113 | 900000
282 | 874 | 2009 | 4520 | 200000 | 1074 | 18 | 60 | 9519 | 6930 | 9018 |  |  |  |  | 321 | 847 | 2017 | 2769 | 200000
283 | 874 | 2010 | 4520 | 200000 | 1075 | 4 | 40 | 9040 | 4542 | 0 |  |  |  |  | 338 | 849 | 2007 | 2742 | 47612
284 | 874 | 2011 | 4520 | 200000 | 1078 | 62 | 40 | NULL | NULL | 0 |  |  |  |  | 339 | 849 | 2007 | 2743 | 220203
285 | 874 | 2012 | 4520 | 200000 | 1080 | 92 | 40 | 9811 | NULL | NULL |  |  |  |  | 487 | 849 | 2007 | 2769 | 1499990
286 | 874 | 2013 | 4520 | 200000 | 1082 | 69 | 40 | 9611 | NULL | NULL |  |  |  |  | 1707 | 849 | 2012 | 2769 | 0
287 | 874 | 2014 | 4520 | 200000 | 1083 | $NO$ | 40 | NULL | NULL | NULL |  |  |  |  | 1708 | 849 | 2013 | 2769 | 850000
253 | 876 | 2009 | 4520 | 75000 | 1085 | 62 | 40 | 9706 | NULL | NULL |  |  |  |  | 1892 | 849 | 2014 | 2769 | 0
254 | 876 | 2010 | 4520 | 150000 | 1086 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 118 | 852 | 2015 | 2742 | 0
299 | 879 | 2010 | 4520 | 160000 | 1087 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 119 | 852 | 2025 | 2742 | 275000
661 | 880 | 1999 | 4520 | 61000 | 1088 | 92 | 73 | 9449 | NULL | NULL |  |  |  |  | 4002 | 852 | 2026 | 2742 | 350000
255 | 880 | 2008 | 4520 | 1200000 | 1089 | 42 | 73 | 9703 | NULL | NULL |  |  |  |  | 116 | 854 | 2006 | 6998 | 80000
256 | 880 | 2009 | 4520 | 2479000 | 1090 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 117 | 854 | 2007 | 6998 | 420000
257 | 880 | 2010 | 4520 | 1928000 | 1091 | 42 | NULL | 9149 | NULL | NULL |  |  |  |  | 217 | 857 | 2005 | 6907 | 90000
258 | 880 | 2011 | 4520 | 2350000 | 1092 | 48 | 40 | 9848 | NULL | NULL |  |  |  |  | 218 | 857 | 2006 | 6907 | 180000
259 | 880 | 2012 | 4520 | 3614000 | 1093 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 149 | 858 | 2005 | 6907 | 75000
266 | 883 | 2009 | 4520 | 75000 | 1094 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 150 | 858 | 2006 | 6907 | 150000
267 | 883 | 2010 | 4520 | 200000 | 1095 | 98 | 73 | NULL | NULL | NULL |  |  |  |  | 583 | 863 | 2018 | 2742 | 130000
291 | 885 | 2008 | 4520 | 70000 | 1096 | 89 | 73 | 9736 | NULL | NULL |  |  |  |  | 192 | 864 | 2017 | 2742 | 0
292 | 885 | 2009 | 4520 | 140000 | 1097 | 98 | 73 | 9461 | NULL | NULL |  |  |  |  | 1695 | 864 | 2023 | 2742 | 225000
295 | 887 | 2008 | 4520 | 130000 | 1098 | 89 | 73 | NULL | NULL | NULL |  |  |  |  | 340 | 866 | 2006 | 6998 | 350000
493 | 887 | 2009 | 4520 | 270000 | 1099 | 42 | 73 | NULL | NULL | NULL |  |  |  |  | 322 | 871 | 2018 | 2769 | 0
213 | 891 | 2006 | 4520 | 100000 | 1100 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 323 | 871 | 2025 | 2769 | 100000
214 | 891 | 2007 | 4520 | 100000 | 1101 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 175 | 872 | 2018 | 2742 | 0
215 | 891 | 2008 | 4520 | 100000 | 1102 | 71 | 60 | 9101 | NULL | NULL |  |  |  |  | 177 | 872 | 2019 | 2742 | 2400000
216 | 891 | 2009 | 4520 | 100000 | 1103 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 135 | 873 | 2006 | 6907 | 100000
217 | 891 | 2010 | 4520 | 100000 | 1104 | 42 | 73 | NULL | NULL | NULL |  |  |  |  | 136 | 873 | 2007 | 6907 | 100000
218 | 891 | 2011 | 4520 | 100000 | 1105 | 98 | 73 | NULL | NULL | NULL |  |  |  |  | 137 | 873 | 2008 | 6907 | 100000
219 | 891 | 2012 | 4520 | 100000 | 1107 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 138 | 873 | 2009 | 6907 | 100000
220 | 891 | 2013 | 4520 | 100000 | 1108 | 43 | NULL | 9242 | NULL | NULL |  |  |  |  | 139 | 873 | 2010 | 6907 | 100000
221 | 891 | 2014 | 4520 | 100000 | 1109 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 140 | 873 | 2011 | 6907 | 100000
233 | 892 | 2010 | 4520 | 350000 | 1110 | 88 | 40 | 9437 | NULL | NULL |  |  |  |  | 141 | 873 | 2012 | 6907 | 300000
234 | 892 | 2011 | 4520 | 750000 | 1111 | 31 | 40 | 9604 | NULL | NULL |  |  |  |  | 142 | 874 | 2006 | 7111 | 200000
231 | 893 | 2009 | 4520 | 500000 | 1112 | 74 | 40 | 9805 | NULL | NULL |  |  |  |  | 143 | 874 | 2007 | 7111 | 200000
232 | 893 | 2010 | 4520 | 1100000 | 1113 | 43 | 73 | NULL | NULL | NULL |  |  |  |  | 144 | 874 | 2008 | 7111 | 200000
240 | 900 | 2009 | 4520 | 400000 | 1114 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 145 | 874 | 2009 | 7111 | 200000
466 | 900 | 2010 | 4520 | 900000 | 1115 | 88 | 73 | NULL | NULL | NULL |  |  |  |  | 146 | 874 | 2010 | 7111 | 200000
241 | 901 | 2010 | 4520 | 475000 | 1116 | 74 | 40 | 9801 | NULL | NULL |  |  |  |  | 147 | 874 | 2011 | 7111 | 200000
242 | 901 | 2011 | 4520 | 975000 | 1117 | $NO$ | 40 | 9731 | NULL | NULL |  |  |  |  | 148 | 874 | 2012 | 7111 | 600000
222 | 902 | 2006 | 4520 | 200000 | 1118 | 43 | 73 | 9731 | NULL | NULL |  |  |  |  | 106 | 876 | 2025 | 2742 | 160000
223 | 902 | 2007 | 4520 | 200000 | 1119 | 71 | 60 | 9204 | NULL | NULL |  |  |  |  | 188 | 879 | 2019 | 2742 | 350000
224 | 902 | 2008 | 4520 | 200000 | 1121 | 71 | 60 | 9200 | NULL | NULL |  |  |  |  | 618 | 880 | 1999 | 2776 | 61000
225 | 902 | 2009 | 4520 | 200000 | 1122 | 71 | 60 | 9105 | NULL | NULL |  |  |  |  | 101 | 880 | 2010 | 6907 | 1200000
226 | 902 | 2010 | 4520 | 200000 | 1123 | 71 | 60 | 9106 | NULL | NULL |  |  |  |  | 100 | 880 | 2011 | 6907 | 2479000
227 | 902 | 2011 | 4520 | 200000 | 1124 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 108 | 880 | 2012 | 6907 | 1928000
228 | 902 | 2012 | 4520 | 200000 | 1125 | 71 | 60 | 9109 | NULL | NULL |  |  |  |  | 109 | 880 | 2013 | 6907 | 2350000
229 | 902 | 2013 | 4520 | 200000 | 1126 | 18 | 60 | 9809 | NULL | NULL |  |  |  |  | 110 | 880 | 2014 | 6907 | 3614000
230 | 902 | 2014 | 4520 | 200000 | 1127 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 127 | 883 | 2015 | 2742 | 0
243 | 903 | 2008 | 4520 | 150000 | 1128 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1759 | 883 | 2026 | 2742 | 275000
244 | 903 | 2009 | 4520 | 295000 | 1129 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 165 | 885 | 2010 | 6907 | 210000
237 | 905 | 2009 | 4520 | 100000 | 1130 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 172 | 887 | 2011 | 6907 | 130000
238 | 905 | 2010 | 4520 | 200000 | 1131 | $NO$ | 73 | NULL | NULL | NULL |  |  |  |  | 173 | 887 | 2012 | 6907 | 270000
235 | 906 | 2008 | 4520 | 115000 | 1132 | 76 | 40 | 9707 | NULL | NULL |  |  |  |  | 247 | 891 | 2006 | 6907 | 100000
463 | 906 | 2009 | 4520 | 350000 | 1133 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 248 | 891 | 2007 | 6907 | 100000
236 | 907 | 2009 | 4520 | 115000 | 1134 | 99 | 40 | NULL | NULL | NULL |  |  |  |  | 249 | 891 | 2008 | 6907 | 100000
465 | 907 | 2010 | 4520 | 245000 | 1135 | 89 | 73 | NULL | NULL | NULL |  |  |  |  | 250 | 891 | 2009 | 6907 | 100000
453 | 908 | 2005 | 4520 | 230000 | 1136 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 251 | 891 | 2010 | 6907 | 100000
251 | 908 | 2006 | 4520 | 886000 | 1137 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 252 | 891 | 2011 | 6907 | 100000
252 | 908 | 2007 | 4520 | 680000 | 1138 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 253 | 891 | 2012 | 6907 | 300000
245 | 910 | 2010 | 4520 | 650000 | 1139 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 263 | 892 | 2015 | 2743 | 0
246 | 910 | 2011 | 4520 | 1550000 | 1140 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 264 | 892 | 2019 | 2743 | 745000
239 | 911 | 2008 | 4520 | 436000 | 1141 | 89 | 73 | NULL | NULL | NULL |  |  |  |  | 262 | 893 | 2016 | 2743 | 0
117 | 913 | 2006 | 4520 | 100000 | 1142 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 261 | 893 | 2019 | 2743 | 1225000
118 | 913 | 2007 | 4520 | 100000 | 1143 | 89 | 73 | NULL | NULL | NULL |  |  |  |  | 274 | 900 | 2008 | 6907 | 550000
119 | 913 | 2008 | 4520 | 100000 | 1144 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 276 | 901 | 2010 | 6907 | 475000
120 | 913 | 2009 | 4520 | 100000 | 1145 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 277 | 901 | 2011 | 6907 | 975000
121 | 913 | 2010 | 4520 | 100000 | 1146 | 89 | 73 | NULL | NULL | NULL |  |  |  |  | 254 | 902 | 2006 | 7111 | 200000
122 | 913 | 2011 | 4520 | 100000 | 1147 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 255 | 902 | 2007 | 7111 | 200000
123 | 913 | 2012 | 4520 | 100000 | 1148 | 89 | 73 | NULL | NULL | NULL |  |  |  |  | 256 | 902 | 2008 | 7111 | 200000
124 | 913 | 2013 | 4520 | 100000 | 1149 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 257 | 902 | 2009 | 7111 | 200000
125 | 913 | 2014 | 4520 | 100000 | 1150 | 62 | 40 | 9614 | 4500 | NULL |  |  |  |  | 258 | 902 | 2010 | 7111 | 200000
145 | 915 | 2007 | 4520 | 230000 | 1151 | 62 | 40 | 9610 | NULL | NULL |  |  |  |  | 259 | 902 | 2011 | 7111 | 200000
148 | 915 | 2008 | 4520 | 250000 | 1152 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 260 | 902 | 2012 | 7111 | 600000
149 | 915 | 2009 | 4520 | 250000 | 1153 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 278 | 903 | 2015 | 2743 | 0
150 | 915 | 2010 | 4520 | 250000 | 1154 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 279 | 903 | 2019 | 2743 | 410000
151 | 915 | 2011 | 4520 | 250000 | 1155 | 82 | 73 | NULL | NULL | NULL |  |  |  |  | 271 | 905 | 2015 | 2743 | 0
437 | 915 | 2012 | 4520 | 250000 | 1156 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 272 | 905 | 2019 | 2743 | 225000
250 | 924 | 2008 | 4520 | 35000 | 1157 | 76 | 40 | 9711 | NULL | NULL |  |  |  |  | 267 | 906 | 2019 | 2743 | 475000
470 | 924 | 2009 | 4520 | 85000 | 1158 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 269 | 907 | 2014 | 2743 | 0
652 | 925 | 2002 | 4520 | 625000 | 1159 | 21 | 40 | 9043 | NULL | NULL |  |  |  |  | 270 | 907 | 2019 | 2743 | 460000
202 | 925 | 2004 | 4520 | 4448000 | 1160 | 21 | 40 | 9041 | NULL | NULL |  |  |  |  | 298 | 908 | 2005 | 6907 | 6500
203 | 925 | 2005 | 4520 | 1517000 | 1161 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 299 | 908 | 2006 | 6907 | 63000
447 | 925 | 2006 | 4520 | 1496400 | 1162 | $NO$ | 73 | NULL | NULL | NULL |  |  |  |  | 300 | 908 | 2007 | 6907 | 560500
450 | 925 | 2007 | 4520 | 1541000 | 1163 | 69 | 40 | 9888 | NULL | NULL |  |  |  |  | 768 | 908 | 2008 | 6907 | 1500000
451 | 925 | 2008 | 4520 | 1658000 | 1164 | 69 | 40 | 9886 | NULL | NULL |  |  |  |  | 281 | 910 | 2014 | 2743 | 0
207 | 930 | 2009 | 4520 | 1500000 | 1165 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 282 | 910 | 2019 | 2743 | 2000000
208 | 930 | 2010 | 4520 | 1500000 | 1166 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 273 | 911 | 2014 | 6907 | 650000
209 | 930 | 2011 | 4520 | 1500000 | 1168 | 71 | 61 | 9002 | NULL | NULL |  |  |  |  | 324 | 913 | 2006 | 7113 | 100000
210 | 930 | 2012 | 4520 | 1500000 | 1169 | 71 | 61 | 9003 | NULL | NULL |  |  |  |  | 325 | 913 | 2007 | 7113 | 100000
211 | 930 | 2013 | 4520 | 1500000 | 1170 | 71 | NULL | 9004 | NULL | NULL |  |  |  |  | 326 | 913 | 2008 | 7113 | 100000
212 | 930 | 2014 | 4520 | 1500000 | 1171 | 71 | NULL | 9005 | NULL | NULL |  |  |  |  | 327 | 913 | 2009 | 7113 | 100000
452 | 930 | 2015 | 4520 | 13659000 | 1172 | 71 | 60 | 9108 | NULL | NULL |  |  |  |  | 328 | 913 | 2010 | 7113 | 100000
204 | 934 | 2015 | 4520 | 50000000 | 1173 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 329 | 913 | 2011 | 7113 | 100000
199 | 935 | 2009 | 4520 | 200000 | 1174 | $NO$ | 60 | 9251 | NULL | NULL |  |  |  |  | 330 | 913 | 2012 | 7113 | 300000
200 | 937 | 2010 | 4520 | 28000 | 1175 | 21 | 40 | 9044 | NULL | NULL |  |  |  |  | 295 | 924 | 2018 | 2743 | 0
201 | 937 | 2011 | 4520 | 140000 | 1176 | 49 | NULL | NULL | NULL | NULL |  |  |  |  | 1692 | 924 | 2024 | 2743 | 260000
358 | 938 | 2009 | 4520 | 100000 | 1177 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 3666 | 924 | 2025 | 2743 | 440000
354 | 939 | 2008 | 4520 | 64000 | 1178 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 601 | 925 | 2002 | 2776 | 625000
355 | 939 | 2009 | 4520 | 320000 | 1179 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 238 | 925 | 2005 | 2776 | 5965000
356 | 941 | 2009 | 4520 | 80000 | 1180 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 239 | 925 | 2006 | 2776 | 1562000
357 | 941 | 2010 | 4520 | 350000 | 1181 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 240 | 925 | 2007 | 2776 | 1609000
360 | 942 | 2008 | 4520 | 205000 | 1182 | 69 | 73 | NULL | NULL | NULL |  |  |  |  | 819 | 934 | 2009 | 6907 | 1400000
411 | 943 | 2008 | 4520 | 175000 | 1183 | 82 | 73 | NULL | NULL | NULL |  |  |  |  | 820 | 934 | 2010 | 6907 | 250000
413 | 943 | 2009 | 4520 | 1825000 | 1184 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 1321 | 934 | 2010 | 6988 | 750000
363 | 944 | 2012 | 4520 | 55000 | 1185 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 821 | 934 | 2011 | 6907 | 1000000
364 | 944 | 2013 | 4520 | 260000 | 1186 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1322 | 934 | 2011 | 6988 | 750000
365 | 945 | 2008 | 4520 | 120000 | 1187 | $NO$ | 40 | NULL | NULL | NULL |  |  |  |  | 822 | 934 | 2012 | 6907 | 6520000
361 | 949 | 2012 | 4520 | 150000 | 1188 | 43 | 73 | NULL | NULL | NULL |  |  |  |  | 823 | 934 | 2013 | 6907 | 2775000
362 | 949 | 2013 | 4520 | 520000 | 1189 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 1310 | 934 | 2014 | 6907 | 0
382 | 952 | 2008 | 4520 | 170000 | 1190 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 1805 | 934 | 2015 | 6907 | 2500000
383 | 952 | 2009 | 4520 | 210000 | 1191 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 1806 | 934 | 2016 | 2743 | 1300000
647 | 952 | 2009 | 5196 | 840000 | 1192 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 1807 | 934 | 2017 | 2743 | 3500000
384 | 952 | 2010 | 4520 | 270000 | 1193 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 242 | 934 | 2018 | 2743 | 3187000
648 | 952 | 2010 | 5196 | 840000 | 1194 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 2269 | 934 | 2019 | 2743 | 0
93 | 953 | 2008 | 4520 | 330000 | 1195 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 2300 | 934 | 2020 | 2743 | 1500000
94 | 953 | 2009 | 4520 | 245000 | 1196 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 2626 | 934 | 2021 | 2743 | 2500000
95 | 953 | 2010 | 4520 | 562500 | 1197 | 99 | 73 | NULL | NULL | NULL |  |  |  |  | 638 | 935 | 2000 | 1625 | 10000
96 | 953 | 2011 | 4520 | 547500 | 1198 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1288 | 943 | 2023 | 1626 | 50000
97 | 954 | 2008 | 4520 | 560000 | 1199 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 405 | 943 | 2023 | 6907 | 50000
98 | 954 | 2009 | 4520 | 410000 | 1200 | 18 | 60 | 9819 | NULL | NULL |  |  |  |  | 1287 | 943 | 2023 | 6988 | 100000
99 | 954 | 2010 | 4520 | 795000 | 1201 | 18 | 60 | 9810 | NULL | NULL |  |  |  |  | 1289 | 943 | 2024 | 1626 | 112500
100 | 954 | 2011 | 4520 | 765000 | 1202 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1286 | 943 | 2024 | 6907 | 112500
527 | 956 | 2006 | 4520 | 1275000 | 1203 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1285 | 943 | 2024 | 6988 | 225000
528 | 956 | 2007 | 4520 | 475000 | 1204 | 71 | 60 | 9352 | NULL | NULL |  |  |  |  | 458 | 943 | 2025 | 1626 | 608333
473 | 958 | 2008 | 2100 | 50000 | 1205 | 71 | 60 | 9501 | NULL | NULL |  |  |  |  | 459 | 943 | 2025 | 6907 | 608333
474 | 958 | 2008 | 4520 | 350000 | 1206 | 71 | 60 | 9119 | NULL | NULL |  |  |  |  | 527 | 943 | 2025 | 6988 | 608334
398 | 966 | 2008 | 4520 | 37000 | 1208 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 3950 | 949 | 2021 | 2296 | 1000000
397 | 967 | 2008 | 4520 | 258000 | 1209 | 61 | 40 | 9065 | NULL | NULL |  |  |  |  | 991 | 949 | 2021 | 2762 | 600000
392 | 968 | 2008 | 4520 | 206000 | 1210 | 92 | 40 | 9822 | NULL | NULL |  |  |  |  | 990 | 949 | 2022 | 1625 | 0
396 | 969 | 2010 | 4520 | 86000 | 1211 | 18 | NULL | NULL | NULL | NULL |  |  |  |  | 3198 | 949 | 2022 | 2336 | 0
389 | 970 | 2009 | 4520 | 250000 | 1212 | 89 | 73 | NULL | NULL | NULL |  |  |  |  | 3949 | 949 | 2022 | 2762 | 630000
390 | 971 | 2009 | 4520 | 20000 | 1217 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 970 | 952 | 2007 | 2742 | 57000
391 | 971 | 2010 | 4520 | 200000 | 1218 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 92 | 952 | 2009 | 1625 | 700000
394 | 972 | 2011 | 4520 | 344000 | 1219 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 594 | 952 | 2009 | 2299 | 1100000
289 | 975 | 2006 | 4520 | 70000 | 1220 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 964 | 952 | 2009 | 2742 | 1293000
457 | 978 | 2006 | 4520 | 79500 | 1221 | 69 | 40 | 9889 | NULL | NULL |  |  |  |  | 962 | 952 | 2009 | 2762 | 2000000
247 | 978 | 2007 | 4520 | 1072500 | 1222 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 95 | 952 | 2009 | 6987 | 315000
248 | 978 | 2008 | 4520 | 1200000 | 1223 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 93 | 952 | 2010 | 2299 | 1050000
249 | 978 | 2009 | 4520 | 1200000 | 1224 | 69 | NULL | 9137 | NULL | NULL |  |  |  |  | 961 | 952 | 2010 | 2762 | 635000
454 | 978 | 2010 | 4520 | 1200000 | 1225 | 89 | NULL | NULL | NULL | NULL |  |  |  |  | 595 | 952 | 2010 | 6987 | 300000
455 | 978 | 2011 | 4520 | 1200000 | 1226 | 89 | 42 | NULL | NULL | NULL |  |  |  |  | 963 | 952 | 2011 | 2762 | 500000
456 | 978 | 2012 | 4520 | 520000 | 1227 | 42 | NULL | 9137 | NULL | NULL |  |  |  |  | 983 | 953 | 2009 | 2721 | 233000
366 | 980 | 2008 | 4520 | 121000 | 1228 | 92 | 73 | 9452 | NULL | NULL |  |  |  |  | 491 | 953 | 2009 | 2762 | 235000
367 | 980 | 2009 | 4520 | 704000 | 1229 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 984 | 953 | 2010 | 2762 | 535000
601 | 981 | 2005 | 5130 | 4668266 | 1230 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 948 | 953 | 2011 | 2299 | 8500000
602 | 981 | 2006 | 5130 | 2202653 | 1231 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 986 | 953 | 2012 | 2299 | 2000000
642 | 984 | 2005 | 4520 | 1485000 | 1232 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 971 | 954 | 2009 | 2721 | 232000
505 | 984 | 2006 | 4520 | 3217200 | 1233 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 974 | 954 | 2009 | 2762 | 235000
504 | 984 | 2006 | 5190 | 18750000 | 1234 | 82 | NULL | NULL | NULL | NULL |  |  |  |  | 972 | 954 | 2010 | 2762 | 530000
518 | 984 | 2007 | 4520 | 733000 | 1235 | 82 | NULL | NULL | NULL | NULL |  |  |  |  | 967 | 954 | 2011 | 2299 | 8500000
519 | 984 | 2007 | 5190 | 6250000 | 1236 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 1441 | 954 | 2012 | 2299 | 2000000
569 | 985 | 2005 | 4520 | 384000 | 1237 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 387 | 956 | 2006 | 2797 | 300000
464 | 985 | 2006 | 2100 | 100000 | 1238 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 388 | 956 | 2007 | 2797 | 700000
290 | 988 | 2006 | 4520 | 538500 | 1239 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 886 | 956 | 2008 | 2797 | 800000
345 | 988 | 2007 | 4520 | 357500 | 1240 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 2040 | 958 | 2014 | 2742 | 0
293 | 989 | 2006 | 4520 | 738500 | 1241 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 160 | 958 | 2016 | 2742 | 1100000
294 | 989 | 2007 | 4520 | 757500 | 1242 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 502 | 963 | 2006 | 6988 | 24600
300 | 990 | 2006 | 4520 | 98500 | 1243 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 518 | 966 | 2021 | 2260 | 36100
301 | 990 | 2007 | 4520 | 597500 | 1244 | 88 | NULL | NULL | NULL | NULL |  |  |  |  | 1631 | 966 | 2021 | 2748 | 1900
152 | 991 | 2007 | 4520 | 1000000 | 1245 | 88 | NULL | NULL | NULL | NULL |  |  |  |  | 2792 | 966 | 2022 | 2260 | 374300
153 | 991 | 2008 | 4520 | 1000000 | 1246 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 2790 | 966 | 2022 | 2748 | 19700
154 | 991 | 2009 | 4520 | 1000000 | 1247 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 463 | 968 | 2021 | 2260 | 224200
155 | 991 | 2010 | 4520 | 1000000 | 1248 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 511 | 968 | 2021 | 2748 | 11800
156 | 991 | 2011 | 4520 | 1000000 | 1249 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 2784 | 968 | 2022 | 2260 | 311600
157 | 991 | 2012 | 4520 | 1000000 | 1250 | 98 | 73 | NULL | NULL | NULL |  |  |  |  | 2785 | 968 | 2022 | 2748 | 16400
158 | 991 | 2013 | 4520 | 1000000 | 1251 | 97 | NULL | NULL | NULL | NULL |  |  |  |  | 831 | 969 | 2024 | 2260 | 1479150
659 | 992 | 2004 | 4520 | 342000 | 1252 | 00MG | NULL | NULL | NULL | NULL |  |  |  |  | 512 | 969 | 2024 | 2748 | 77850
660 | 992 | 2005 | 4520 | 50000 | 1254 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 938 | 970 | 2009 | 6998 | 20
422 | 992 | 2006 | 4520 | 105000 | 1255 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 466 | 971 | 2025 | 2260 | 137750
423 | 992 | 2007 | 4520 | 105000 | 1256 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 465 | 971 | 2025 | 2748 | 7250
424 | 992 | 2008 | 4520 | 105000 | 1257 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 468 | 972 | 2011 | 2260 | 139000
425 | 992 | 2009 | 4520 | 105000 | 1258 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 513 | 972 | 2011 | 6998 | 100000
426 | 992 | 2010 | 4520 | 105000 | 1260 | 69 | 73 | 9360 | 9000 | NULL |  |  |  |  | 646 | 973 | 2006 | 6998 | 100000
427 | 992 | 2011 | 4520 | 105000 | 1261 | 89 | NULL | NULL | NULL | NULL |  |  |  |  | 649 | 973 | 2007 | 6998 | 350000
428 | 992 | 2012 | 4520 | 50000 | 1262 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1014 | 973 | 2008 | 6998 | 277914
514 | 995 | 2004 | 4520 | 45000 | 1263 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1015 | 973 | 2009 | 6998 | 0
434 | 995 | 2006 | 4520 | 51687 | 1264 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 157 | 975 | 2006 | 6907 | 70000
508 | 995 | 2007 | 4520 | 103374 | 1265 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1002 | 978 | 2007 | 2743 | 100000
509 | 995 | 2008 | 4520 | 103374 | 1266 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 289 | 978 | 2008 | 2743 | 1020000
510 | 995 | 2009 | 4520 | 103374 | 1267 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 290 | 978 | 2009 | 2743 | 200000
511 | 995 | 2010 | 4520 | 103374 | 1268 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 291 | 978 | 2010 | 2743 | 200000
512 | 995 | 2011 | 4520 | 103374 | 1269 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 292 | 978 | 2011 | 2743 | 650000
513 | 995 | 2012 | 4520 | 1108593 | 1270 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 293 | 978 | 2012 | 2743 | 1600000
264 | 997 | 2008 | 4520 | 45000 | 1271 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 294 | 978 | 2013 | 2743 | 1600000
265 | 997 | 2009 | 4520 | 75000 | 1272 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 1312 | 978 | 2014 | 2743 | 0
486 | 998 | 2005 | 4520 | 350000 | 1273 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 1871 | 978 | 2015 | 2743 | 0
269 | 999 | 2008 | 4520 | 80000 | 1274 | 58 | NULL | NULL | NULL | NULL |  |  |  |  | 2131 | 978 | 2016 | 2743 | 2000000
268 | 999 | 2009 | 4520 | 190000 | 1275 | 2 | NULL | NULL | NULL | NULL |  |  |  |  | 2132 | 978 | 2017 | 2743 | 1600000
104 | 1000 | 2009 | 4520 | 100000 | 1276 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2289 | 978 | 2018 | 2743 | 1600000
105 | 1000 | 2010 | 4520 | 275000 | 1279 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2287 | 978 | 2019 | 2743 | 1600000
656 | 1001 | 2005 | 4520 | 100000 | 1280 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 3677 | 978 | 2020 | 2743 | 275000
143 | 1001 | 2006 | 4520 | 400800 | 1281 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 3678 | 978 | 2021 | 2743 | 725000
144 | 1002 | 2006 | 4520 | 167200 | 1282 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 3679 | 978 | 2022 | 2743 | 275000
347 | 1003 | 2006 | 4520 | 333600 | 1283 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 3680 | 978 | 2023 | 2743 | 725000
348 | 1003 | 2007 | 4520 | 333000 | 1284 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 3681 | 978 | 2024 | 2743 | 455000
349 | 1003 | 2008 | 4520 | 350000 | 1285 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 3682 | 978 | 2025 | 2722
350 | 1003 | 2009 | 4520 | 350000 | 1286 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 90 | 980 | 2007 | 1625 | 156000
351 | 1003 | 2010 | 4520 | 350000 | 1287 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 89 | 980 | 2007 | 2299 | 358000
352 | 1003 | 2011 | 4520 | 350000 | 1288 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 87 | 980 | 2007 | 6998 | 311000
353 | 1003 | 2012 | 4520 | 350000 | 1289 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 484 | 981 | 2005 | 2776 | 1417412
655 | 1007 | 2005 | 4520 | 3000000 | 1290 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 483 | 981 | 2005 | 2793 | 545854
611 | 1007 | 2006 | 4520 | 9000000 | 1292 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 482 | 981 | 2005 | 2795 | 2705000
612 | 1007 | 2007 | 4520 | 9000000 | 1293 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 485 | 981 | 2006 | 2776 | 1832588
654 | 1011 | 2005 | 4520 | 467000 | 1294 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 486 | 981 | 2006 | 6998 | 390565
176 | 1011 | 2006 | 5190 | 183800 | 1295 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 893 | 984 | 2006 | 2710 | 400000
81 | 1012 | 2009 | 2100 | 180000 | 1296 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 897 | 984 | 2006 | 2712 | 1500000
82 | 1012 | 2009 | 4520 | 20000 | 1297 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 896 | 984 | 2006 | 2742 | 2871300
83 | 1012 | 2010 | 2100 | 43000 | 1298 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 895 | 984 | 2006 | 2743 | 2908900
84 | 1012 | 2010 | 4520 | 7000 | 1299 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 105 | 984 | 2006 | 6907 | 14690460
85 | 1013 | 2008 | 2100 | 270000 | 1300 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 894 | 984 | 2006 | 6998 | 1114340
86 | 1013 | 2008 | 4520 | 30000 | 1301 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 889 | 984 | 2007 | 2712 | 133200
87 | 1013 | 2009 | 2100 | 45000 | 1302 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 891 | 984 | 2007 | 2742 | 357500
88 | 1013 | 2009 | 4520 | 5000 | 1303 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 890 | 984 | 2007 | 2743 | 937100
627 | 1016 | 2005 | 4520 | 100000 | 1304 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 892 | 984 | 2007 | 2772 | 250000
102 | 1017 | 2007 | 2100 | 83000 | 1305 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 584 | 984 | 2007 | 6907 | 9942400
103 | 1017 | 2008 | 2100 | 65000 | 1306 | 72 | 71 | 3000 | NULL | NULL |  |  |  |  | 885 | 984 | 2008 | 6907 | 250000
420 | 1017 | 2008 | 4520 | 35000 | 1309 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 887 | 984 | 2008 | 6988 | 300000
72 | 1021 | 2009 | 4520 | 200000 | 1310 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 203 | 985 | 2005 | 6998 | 384000
368 | 1033 | 2006 | 4520 | 1836000 | 1311 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 204 | 985 | 2006 | 6998 | 141000
369 | 1033 | 2007 | 4520 | 1830000 | 1312 | 49 | NULL | NULL | NULL | NULL |  |  |  |  | 163 | 988 | 2007 | 6640 | 200000
370 | 1033 | 2008 | 4520 | 2000000 | 1313 | 62 | NULL | 9279 | NULL | NULL |  |  |  |  | 164 | 988 | 2008 | 6640 | 700000
371 | 1033 | 2009 | 4520 | 2000000 | 1314 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 161 | 988 | 2008 | 6907 | 100000
372 | 1033 | 2010 | 4520 | 2000000 | 1315 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 169 | 989 | 2007 | 6640 | 320000
373 | 1033 | 2011 | 4520 | 2000000 | 1316 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 170 | 989 | 2008 | 6640 | 1120000
374 | 1033 | 2012 | 4520 | 2000000 | 1317 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 168 | 989 | 2008 | 6907 | 160000
375 | 1034 | 2006 | 4520 | 2413000 | 1318 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 196 | 990 | 2007 | 6640 | 160000
376 | 1034 | 2007 | 4520 | 2402500 | 1319 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 197 | 990 | 2008 | 6640 | 560000
377 | 1034 | 2008 | 4520 | 2700000 | 1320 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 195 | 990 | 2008 | 6907 | 80000
378 | 1034 | 2009 | 4520 | 2700000 | 1321 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 342 | 995 | 2004 | 7113 | 45000
379 | 1034 | 2010 | 4520 | 2700000 | 1322 | 49 | NULL | NULL | NULL | NULL |  |  |  |  | 343 | 995 | 2006 | 7113 | 51687
380 | 1034 | 2011 | 4520 | 2700000 | 1323 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 344 | 995 | 2007 | 7113 | 103374
381 | 1034 | 2012 | 4520 | 2700000 | 1324 | 62 | NULL | 9777 | NULL | NULL |  |  |  |  | 345 | 995 | 2008 | 7113 | 103374
658 | 1035 | 2004 | 4520 | 240000 | 1325 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 346 | 995 | 2009 | 7113 | 103374
657 | 1035 | 2005 | 4520 | 450000 | 1326 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 347 | 995 | 2010 | 7113 | 103374
605 | 1035 | 2006 | 4520 | 2633333 | 1327 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 348 | 995 | 2011 | 7113 | 103374
606 | 1035 | 2007 | 4520 | 2633333 | 1328 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 349 | 995 | 2012 | 7113 | 1108593
607 | 1035 | 2008 | 4520 | 2633333 | 1329 | 69 | 73 | NULL | NULL | NULL |  |  |  |  | 225 | 996 | 2006 | 6907 | 16000
608 | 1035 | 2009 | 4520 | 2633333 | 1330 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 120 | 997 | 2019 | 2742 | 158000
609 | 1035 | 2010 | 4520 | 2633333 | 1331 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 3379 | 997 | 2020 | 2742 | 192000
610 | 1035 | 2011 | 4520 | 2633335 | 1332 | 69 | 61 | 6100 | 7078 | NULL |  |  |  |  | 723 | 998 | 2005 | 6907 | 350000
342 | 1036 | 2006 | 4520 | 86720 | 1333 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 132 | 999 | 2010 | 6907 | 270000
343 | 1037 | 2006 | 4520 | 86720 | 1334 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 312 | 1000 | 2014 | 2159 | 100000
344 | 1037 | 2007 | 4520 | 86600 | 1335 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 313 | 1000 | 2015 | 2159 | 275000
522 | 1038 | 2006 | 4520 | 575000 | 1336 | 69 | NULL | 9777 | NULL | NULL |  |  |  |  | 611 | 1001 | 2005 | 6998 | 100000
523 | 1038 | 2007 | 4520 | 975000 | 1337 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 341 | 1001 | 2006 | 6998 | 450000
529 | 1039 | 2006 | 4520 | 1167200 | 1338 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 366 | 1002 | 2006 | 6998 | 200000
525 | 1040 | 2007 | 4520 | 2066000 | 1340 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 74 | 1003 | 2006 | 2721 | 269500
526 | 1041 | 2006 | 4520 | 975400 | 1341 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 305 | 1003 | 2006 | 2722 | 80500
524 | 1042 | 2007 | 4520 | 391500 | 1342 | 88 | NULL | NULL | NULL | NULL |  |  |  |  | 306 | 1003 | 2007 | 2721 | 269500
636 | 1044 | 2007 | 4520 | 173500 | 1343 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 307 | 1003 | 2007 | 2722 | 80500
586 | 1045 | 2008 | 4520 | 1700000 | 1344 | 88 | NULL | NULL | NULL | NULL |  |  |  |  | 446 | 1003 | 2008 | 2721 | 269500
535 | 1046 | 2008 | 4520 | 540000 | 1345 | 43 | NULL | 9245 | NULL | NULL |  |  |  |  | 447 | 1003 | 2008 | 2722 | 80500
431 | 1048 | 2007 | 4520 | 91000 | 1346 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 448 | 1003 | 2009 | 2721 | 269500
432 | 1048 | 2008 | 4520 | 275000 | 1347 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 449 | 1003 | 2009 | 2722 | 80500
476 | 1049 | 2006 | 2100 | 40000 | 1348 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 450 | 1003 | 2010 | 2721 | 269500
477 | 1049 | 2006 | 5190 | 150000 | 1349 | 62 | 40 | 9856 | NULL | NULL |  |  |  |  | 451 | 1003 | 2010 | 2722 | 80500
496 | 1051 | 2007 | 4520 | 170000 | 1350 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 452 | 1003 | 2011 | 2721 | 269500
498 | 1052 | 2008 | 4520 | 425000 | 1351 | 00CP | NULL | NULL | NULL | NULL |  |  |  |  | 453 | 1003 | 2011 | 2722 | 80500
499 | 1052 | 2009 | 4520 | 875000 | 1352 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 454 | 1003 | 2012 | 2721 | 269500
497 | 1053 | 2007 | 4520 | 170000 | 1353 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 455 | 1003 | 2012 | 2722 | 80500
500 | 1054 | 2008 | 4520 | 60000 | 1354 | 42 | NULL | 9137 | NULL | NULL |  |  |  |  | 609 | 1011 | 2005 | 2721 | 266570
501 | 1054 | 2009 | 4520 | 80000 | 1355 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 608 | 1011 | 2005 | 2762 | 200430
506 | 1055 | 2009 | 4520 | 200000 | 1356 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 403 | 1011 | 2006 | 2721 | 132800
507 | 1056 | 2010 | 4520 | 750000 | 1357 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 445 | 1011 | 2006 | 2762 | 100000
516 | 1058 | 2006 | 4520 | 93600 | 1358 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 456 | 1012 | 2012 | 2710 | 200000
520 | 1059 | 2006 | 4520 | 77000 | 1359 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 58 | 1013 | 2011 | 2710 | 300000
521 | 1059 | 2007 | 4520 | 515000 | 1360 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 59 | 1013 | 2012 | 2710 | 50000
530 | 1060 | 2005 | 4520 | 30000 | 1361 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 568 | 1016 | 2005 | 6998 | 100000
531 | 1060 | 2006 | 4520 | 418000 | 1362 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 310 | 1017 | 2017 | 2769 | 0
532 | 1061 | 2011 | 4520 | 200000 | 1363 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 311 | 1017 | 2018 | 2769 | 250000
533 | 1061 | 2012 | 4520 | 1000000 | 1364 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 115 | 1021 | 2008 | 6907 | 45000
537 | 1062 | 2008 | 4520 | 80000 | 1365 | 21 | NULL | 9283 | NULL | NULL |  |  |  |  | 996 | 1021 | 2009 | 6907 | 155000
538 | 1062 | 2009 | 4520 | 180000 | 1366 | 49 | NULL | NULL | NULL | NULL |  |  |  |  | 415 | 1033 | 2006 | 2762 | 2000000
539 | 1063 | 2009 | 4520 | 750000 | 1367 | 21 | NULL | 4220 | NULL | NULL |  |  |  |  | 416 | 1033 | 2007 | 2762 | 2000000
540 | 1063 | 2010 | 4520 | 750000 | 1368 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 542 | 1033 | 2008 | 2762 | 2670000
541 | 1063 | 2011 | 4520 | 750000 | 1369 | 62 | 40 | 9073 | NULL | NULL |  |  |  |  | 543 | 1033 | 2009 | 2762 | 2730000
542 | 1063 | 2012 | 4520 | 750000 | 1370 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 544 | 1033 | 2010 | 2762 | 1500000
543 | 1063 | 2013 | 4520 | 750000 | 1371 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 545 | 1033 | 2011 | 2762 | 2000000
544 | 1063 | 2014 | 4520 | 750000 | 1372 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 546 | 1033 | 2012 | 2762 | 2000000
545 | 1063 | 2015 | 4520 | 750000 | 1373 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 809 | 1033 | 2013 | 2762 | 2000000
546 | 1063 | 2016 | 4520 | 750000 | 1374 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 1026 | 1033 | 2014 | 2762 | 2000000
547 | 1064 | 2005 | 4520 | 300000 | 1375 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1027 | 1033 | 2015 | 2762 | 2700000
548 | 1065 | 2008 | 4520 | 490000 | 1376 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1734 | 1033 | 2016 | 2762 | 3000000
549 | 1065 | 2009 | 4520 | 980000 | 1377 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 1735 | 1033 | 2017 | 2762 | 3000000
550 | 1066 | 2009 | 4520 | 185000 | 1378 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 2513 | 1033 | 2018 | 2762 | 2250000
551 | 1066 | 2010 | 4520 | 375000 | 1379 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 2514 | 1033 | 2019 | 2762 | 2430000
552 | 1067 | 2005 | 4520 | 300000 | 1380 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 2515 | 1033 | 2020 | 2762 | 2500000
553 | 1067 | 2006 | 4520 | 250000 | 1381 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 2516 | 1033 | 2021 | 2762 | 2500000
554 | 1067 | 2007 | 4520 | 50000 | 1382 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 417 | 1034 | 2006 | 2762 | 2700000
555 | 1068 | 2005 | 4520 | 550000 | 1383 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 418 | 1034 | 2007 | 2762 | 3500000
556 | 1068 | 2006 | 4520 | 550000 | 1384 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 547 | 1034 | 2008 | 2762 | 4450000
557 | 1069 | 2005 | 4520 | 300000 | 1385 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 548 | 1034 | 2009 | 2762 | 4550000
558 | 1069 | 2006 | 4520 | 115000 | 1386 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 549 | 1034 | 2010 | 2762 | 3000000
559 | 1070 | 2008 | 4520 | 175000 | 1387 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 550 | 1034 | 2011 | 2762 | 7000000
560 | 1070 | 2009 | 4520 | 175000 | 1388 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 551 | 1034 | 2012 | 2762 | 0
561 | 1071 | 2009 | 4520 | 150000 | 1389 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 808 | 1034 | 2013 | 2762 | 0
562 | 1071 | 2010 | 4520 | 300000 | 1390 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1476 | 1034 | 2014 | 2762 | 0
563 | 1072 | 2009 | 4520 | 50000 | 1391 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1477 | 1034 | 2015 | 2762 | 1960000
564 | 1072 | 2010 | 4520 | 100000 | 1392 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1736 | 1034 | 2016 | 2762 | 5800000
623 | 1074 | 2005 | 4520 | 110000 | 1393 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1737 | 1034 | 2017 | 2762 | 5520000
576 | 1074 | 2007 | 4520 | 91500 | 1394 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 613 | 1035 | 2004 | 6998 | 240000
599 | 1075 | 2006 | 4520 | 102400 | 1395 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 614 | 1035 | 2005 | 6998 | 450000
613 | 1078 | 2009 | 4520 | 500000 | 1396 | 72 | NULL | 9182 | NULL | NULL |  |  |  |  | 528 | 1035 | 2006 | 6998 | 2633333
[5 empty] | 1397 | 49 | NULL | NULL | NULL | NULL |  |  |  |  | 529 | 1035 | 2007 | 6998 | 2633333
[5 empty] | 1398 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 530 | 1035 | 2008 | 6998 | 2633333
[5 empty] | 1399 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 531 | 1035 | 2009 | 6998 | 2633333
[5 empty] | 1400 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 532 | 1035 | 2010 | 6998 | 2633333
[5 empty] | 1401 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 533 | 1035 | 2011 | 6998 | 2633335
[5 empty] | 1402 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 407 | 1037 | 2006 | 2221 | 6000
[5 empty] | 1403 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 408 | 1037 | 2008 | 2221 | 100000
[5 empty] | 1404 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 382 | 1038 | 2006 | 2797 | 500000
[5 empty] | 1405 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 383 | 1038 | 2007 | 2797 | 1000000
[5 empty] | 1406 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 389 | 1039 | 2006 | 2797 | 1800000
[5 empty] | 1407 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 1025 | 1040 | 2009 | 2772 | 0
[5 empty] | 1408 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 385 | 1040 | 2010 | 2772 | 0
[5 empty] | 1409 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 2739 | 1040 | 2016 | 6647 | 29675
[5 empty] | 1410 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 2738 | 1040 | 2017 | 2772 | 29675
[5 empty] | 1411 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 1076 | 1040 | 2020 | 2772 | 0
[5 empty] | 1412 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 480 | 1040 | 2020 | 6647 | 0
[5 empty] | 1413 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 2506 | 1040 | 2021 | 2772 | 96250
[5 empty] | 1418 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 2507 | 1040 | 2021 | 6647 | 96250
[5 empty] | 1419 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 3659 | 1040 | 2022 | 2772 | 641250
[5 empty] | 1421 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 3660 | 1040 | 2022 | 6647 | 641250
[5 empty] | 1423 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 3661 | 1040 | 2023 | 2772 | 1800000
[5 empty] | 1424 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 3662 | 1040 | 2023 | 6647 | 1800000
[5 empty] | 1425 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 1808 | 1041 | 2011 | 2772 | 30000
[5 empty] | 1426 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 386 | 1041 | 2012 | 2772 | 30000
[5 empty] | 1427 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 481 | 1041 | 2014 | 2772 | 603000
[5 empty] | 1428 | 62 | 40 | 9856 | NULL | NULL |  |  |  |  | 384 | 1042 | 2012 | 6998 | 250000
[5 empty] | 1429 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1268 | 1044 | 2015 | 2761 | 600000
[5 empty] | 1430 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 2405 | 1045 | 2025 | 2703 | 500000
[5 empty] | 1431 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 2201 | 1045 | 2025 | 2762 | 675000
[5 empty] | 1432 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 3063 | 1045 | 2026 | 2703 | 500000
[5 empty] | 1433 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 3843 | 1045 | 2026 | 2762 | 1325000
[5 empty] | 1434 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 390 | 1048 | 2010 | 6907 | 25000
[5 empty] | 1435 | 62 | 40 | NULL | NULL | NULL |  |  |  |  | 391 | 1048 | 2011 | 6907 | 625000
[5 empty] | 1437 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 219 | 1049 | 2007 | 6907 | 75000
[5 empty] | 1438 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 635 | 1049 | 2008 | 6907 | 502000
[5 empty] | 1439 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 193 | 1051 | 2010 | 6907 | 500000
[5 empty] | 1440 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 301 | 1052 | 2009 | 2743 | 110000
[5 empty] | 1442 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 302 | 1052 | 2026 | 2743 | 580000
[5 empty] | 1443 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 3339 | 1052 | 2027 | 2743 | 720000
[5 empty] | 1446 | 62 | 40 | 9703 | NULL | NULL |  |  |  |  | 636 | 1053 | 2009 | 2742 | 250000
[5 empty] | 1448 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 187 | 1053 | 2010 | 2742 | 3750000
[5 empty] | 1449 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 227 | 1054 | 2019 | 2743 | 212500
[5 empty] | 1451 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 228 | 1054 | 2020 | 2743 | 0
[5 empty] | 1452 | 62 | 40 | 9706 | NULL | NULL |  |  |  |  | 134 | 1055 | 2020 | 2742 | 50000
[5 empty] | 1453 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 2837 | 1055 | 2021 | 2742 | 200000
[5 empty] | 1454 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2838 | 1056 | 2022 | 2742 | 50000
[5 empty] | 1455 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 153 | 1056 | 2023 | 2742 | 350000
[5 empty] | 1456 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 125 | 1058 | 2006 | 6907 | 110000
[5 empty] | 1457 | 69 | 73 | NULL | NULL | NULL |  |  |  |  | 130 | 1059 | 2006 | 6907 | 200000
[5 empty] | 1458 | 72 | 61 | 6100 | 2500 | 2430 |  |  |  |  | 131 | 1059 | 2007 | 6907 | 600000
[5 empty] | 1459 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 506 | 1060 | 2005 | 2769 | 30000
[5 empty] | 1460 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 627 | 1060 | 2007 | 2722 | 19541
[5 empty] | 1461 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 626 | 1060 | 2007 | 2742 | 414656
[5 empty] | 1462 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 507 | 1060 | 2007 | 2762 | 619423
[5 empty] | 1463 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 625 | 1060 | 2007 | 2769 | 421430
[5 empty] | 1464 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 503 | 1061 | 2011 | 2299 | 200000
[5 empty] | 1465 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 504 | 1061 | 2012 | 2299 | 1000000
[5 empty] | 1466 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 155 | 1062 | 2008 | 6907 | 80000
[5 empty] | 1467 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 156 | 1062 | 2009 | 6907 | 180000
[5 empty] | 1469 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 112 | 1063 | 2012 | 6907 | 750000
[5 empty] | 1470 | 69 | 73 | NULL | NULL | NULL |  |  |  |  | 113 | 1063 | 2013 | 6907 | 750000
[5 empty] | 1471 | 69 | 73 | NULL | NULL | NULL |  |  |  |  | 114 | 1063 | 2014 | 6907 | 750000
[5 empty] | 1472 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 122 | 1064 | 2010 | 6988 | 300000
[5 empty] | 1474 | 00MG | 29 | 365 | 1329 | 5130 |  |  |  |  | 877 | 1065 | 2010 | 6907 | 1470000
[5 empty] | 1475 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 183 | 1066 | 2008 | 6907 | 185000
[5 empty] | 1477 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 184 | 1066 | 2009 | 6907 | 375000
[5 empty] | 1484 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 374 | 1067 | 2005 | 6907 | 300000
[5 empty] | 1485 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 375 | 1067 | 2006 | 6907 | 250000
[5 empty] | 1490 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 376 | 1067 | 2007 | 6907 | 50000
[5 empty] | 1492 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 215 | 1068 | 2005 | 6907 | 550000
[5 empty] | 1493 | 62 | 40 | 9703 | NULL | NULL |  |  |  |  | 216 | 1068 | 2006 | 6907 | 550000
[5 empty] | 1497 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 303 | 1069 | 2005 | 6907 | 300000
[5 empty] | 1498 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 304 | 1069 | 2006 | 6907 | 115000
[5 empty] | 1499 | 62 | 40 | 9703 | NULL | NULL |  |  |  |  | 158 | 1070 | 2019 | 2742 | 350000
[5 empty] | 1500 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 189 | 1071 | 2008 | 6907 | 175000
[5 empty] | 1501 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 876 | 1071 | 2009 | 6907 | 300000
[5 empty] | 1502 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 151 | 1072 | 2009 | 6907 | 150000
[5 empty] | 1503 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 564 | 1074 | 2005 | 6998 | 110000
[5 empty] | 1504 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 433 | 1074 | 2007 | 6998 | 100000
[5 empty] | 1505 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 2285 | 1078 | 2025 | 2762 | 250000
[5 empty] | 1506 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 3847 | 1078 | 2026 | 2762 | 500000
[5 empty] | 1507 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 630 | 1080 | 2007 | 6907 | 30000
[5 empty] | 1508 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 629 | 1080 | 2008 | 6907 | 150000
[5 empty] | 1509 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 1981 | 1080 | 2014 | 7918 | 0
[5 empty] | 1510 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 791 | 1082 | 2007 | 2769 | 100000
[5 empty] | 1511 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 792 | 1082 | 2009 | 2769 | 1050000
[5 empty] | 1512 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 793 | 1083 | 2007 | 2769 | 50000
[5 empty] | 1513 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 794 | 1083 | 2008 | 2769 | 200000
[5 empty] | 1514 | 62 | 40 | 9703 | NULL | NULL |  |  |  |  | 950 | 1085 | 2012 | 2762 | 34000
[5 empty] | 1515 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 813 | 1085 | 2013 | 2762 | 120000
[5 empty] | 1516 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2173 | 1085 | 2014 | 2762 | 27800
[5 empty] | 1517 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2603 | 1085 | 2015 | 2762 | 10000
[5 empty] | 1518 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3487 | 1085 | 2016 | 2762 | 198100
[5 empty] | 1519 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3488 | 1085 | 2017 | 2762 | 60300
[5 empty] | 1520 | 42 | NULL | 9209 | NULL | NULL |  |  |  |  | 3484 | 1085 | 2018 | 2762 | 94600
[5 empty] | 1521 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 3355 | 1085 | 2019 | 2762 | 200000
[5 empty] | 1522 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1923 | 1085 | 2020 | 2762 | 100000
[5 empty] | 1524 | 71 | 60 | NULL | NULL | NULL |  |  |  |  | 2151 | 1085 | 2021 | 2296 | 0
[5 empty] | 1525 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 3485 | 1085 | 2021 | 2762 | 100000
[5 empty] | 1526 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 3486 | 1085 | 2022 | 2762 | 100000
[5 empty] | 1527 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 3823 | 1085 | 2023 | 2762 | 100000
[5 empty] | 1528 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 3824 | 1085 | 2024 | 2762 | 100000
[5 empty] | 1529 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 3825 | 1085 | 2025 | 2762 | 100000
[5 empty] | 1530 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 640 | 1086 | 2018 | 1625 | 25000
[5 empty] | 1532 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 641 | 1086 | 2019 | 1625 | 50000
[5 empty] | 1533 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 642 | 1087 | 2017 | 2742 | 250000
[5 empty] | 1534 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 643 | 1088 | 2007 | 6907 | 50000
[5 empty] | 1535 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 644 | 1088 | 2008 | 6907 | 850000
[5 empty] | 1536 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 2434 | 1089 | 2018 | 2742 | 125000
[5 empty] | 1537 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 648 | 1089 | 2019 | 2742 | 400000
[5 empty] | 1541 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2983 | 1089 | 2020 | 2742 | 1600000
[5 empty] | 1542 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3602 | 1089 | 2021 | 2742 | 400000
[5 empty] | 1544 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 650 | 1090 | 2022 | 2742 | 150000
[5 empty] | 1555 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 2139 | 1090 | 2023 | 2742 | 750000
[5 empty] | 1556 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2931 | 1090 | 2024 | 2742 | 750000
[5 empty] | 1557 | 2762 | NULL | 9274 | NULL | NULL |  |  |  |  | 1882 | 1091 | 2013 | 2742 | 0
[5 empty] | 1568 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1668 | 1091 | 2015 | 2742 | 30500
[5 empty] | 1569 | 25 | NULL | NULL | NULL | NULL |  |  |  |  | 654 | 1091 | 2016 | 2742 | 289500
[5 empty] | 1570 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2435 | 1091 | 2017 | 2742 | 1680000
[5 empty] | 1571 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2954 | 1091 | 2018 | 2742 | 1680000
[5 empty] | 1572 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 656 | 1092 | 2007 | 6907 | 35000
[5 empty] | 1573 | 42 | NULL | 9242 | NULL | NULL |  |  |  |  | 657 | 1092 | 2008 | 6907 | 617000
[5 empty] | 1574 | 62 | NULL | 9266 | NULL | NULL |  |  |  |  | 2135 | 1093 | 2019 | 2742 | 0
[5 empty] | 1576 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3623 | 1093 | 2022 | 2710 | 0
[5 empty] | 1577 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 658 | 1093 | 2022 | 2742 | 325000
[5 empty] | 1578 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 659 | 1094 | 2023 | 2748 | 1000000
[5 empty] | 1579 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 661 | 1095 | 2011 | 6907 | 150000
[5 empty] | 1580 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 662 | 1096 | 2007 | 6907 | 50000
[5 empty] | 1581 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 663 | 1096 | 2008 | 6907 | 400000
[5 empty] | 1582 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 664 | 1097 | 2013 | 2742 | 800000
[5 empty] | 1583 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1020 | 1097 | 2015 | 2742 | 2500000
[5 empty] | 1584 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 2436 | 1097 | 2016 | 2742 | 500000
[5 empty] | 1585 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 666 | 1098 | 2011 | 6907 | 200000
[5 empty] | 1586 | 62 | 40 | 9872 | NULL | NULL |  |  |  |  | 670 | 1099 | 2023 | 2742 | 200000
[5 empty] | 1587 | 62 | NULL | 9253 | NULL | NULL |  |  |  |  | 2078 | 1099 | 2024 | 2742 | 100000
[5 empty] | 1633 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2932 | 1099 | 2025 | 2742 | 1600000
[5 empty] | 1669 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1881 | 1100 | 2012 | 2742 | 50000
[5 empty] | 1667 | 71 | 61 | 2100 | 6237 | 2430 |  |  |  |  | 1880 | 1100 | 2013 | 2742 | 390000
[5 empty] | 1611 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 671 | 1100 | 2019 | 2742 | 0
[5 empty] | 1612 | 43 | NULL | 9248 | NULL | NULL |  |  |  |  | 672 | 1100 | 2021 | 2742 | 150000
[5 empty] | 1653 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 673 | 1100 | 2022 | 2742 | 6235000
[5 empty] | 1598 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 675 | 1101 | 2017 | 2742 | 50000
[5 empty] | 1603 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2437 | 1101 | 2018 | 2742 | 745000
[5 empty] | 1658 | 62 | NULL | 9291 | NULL | NULL |  |  |  |  | 694 | 1102 | 2009 | 2771 | 18300
[5 empty] | 1595 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 695 | 1102 | 2010 | 2771 | 1800000
[5 empty] | 1596 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1474 | 1102 | 2011 | 2771 | 300000
[5 empty] | 1593 | 42 | 40 | 9288 | NULL | NULL |  |  |  |  | 1475 | 1102 | 2012 | 2771 | 350000
[5 empty] | 1604 | 42 | 40 | NULL | NULL | NULL |  |  |  |  | 1670 | 1103 | 2026 | 2296 | 750000
[5 empty] | 1608 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 1126 | 1103 | 2026 | 2710 | 250000
[5 empty] | 1607 | 48 | 40 | NULL | NULL | 0 |  |  |  |  | 681 | 1104 | 2021 | 2742 | 50000
[5 empty] | 1682 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 2839 | 1104 | 2022 | 2742 | 225000
[5 empty] | 1614 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 2959 | 1104 | 2023 | 2742 | 75000
[5 empty] | 1590 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 682 | 1105 | 2013 | 2742 | 250000
[5 empty] | 1591 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 684 | 1107 | 2023 | 2743 | 267000
[5 empty] | 1594 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3340 | 1107 | 2024 | 2743 | 333000
[5 empty] | 1600 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3984 | 1108 | 2017 | 2743 | 18600
[5 empty] | 1610 | 43 | NULL | 9095 | NULL | NULL |  |  |  |  | 685 | 1108 | 2018 | 2743 | 227000
[5 empty] | 1613 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 2953 | 1108 | 2019 | 2743 | 654000
[5 empty] | 1615 | 43 | NULL | 9272 | NULL | NULL |  |  |  |  | 3985 | 1108 | 2020 | 2743 | 163800
[5 empty] | 1623 | 62 | NULL | 9193 | NULL | NULL |  |  |  |  | 686 | 1109 | 2012 | 6907 | 150000
[5 empty] | 1624 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 687 | 1110 | 2010 | 6907 | 22433
[5 empty] | 1625 | 62 | NULL | 9179 | NULL | NULL |  |  |  |  | 688 | 1111 | 2013 | 2743 | 0
[5 empty] | 1628 | 62 | NULL | 9225 | NULL | NULL |  |  |  |  | 1311 | 1111 | 2014 | 2743 | 0
[5 empty] | 1619 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1868 | 1111 | 2015 | 2743 | 1405000
[5 empty] | 1639 | 69 | NULL | 9087 | NULL | NULL |  |  |  |  | 1662 | 1112 | 2007 | 2743 | 53000
[5 empty] | 1643 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1663 | 1112 | 2012 | 2743 | 50000
[5 empty] | 1645 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 690 | 1113 | 2009 | 6998 | 75000
[5 empty] | 1656 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 691 | 1114 | 2019 | 2743 | 200000
[5 empty] | 1632 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 713 | 1115 | 2008 | 6907 | 250000
[5 empty] | 1655 | 10 | NULL | 263 | NULL | NULL |  |  |  |  | 692 | 1116 | 2008 | 6907 | 230000
[5 empty] | 1697 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 788 | 1117 | 2012 | 2296 | 700000
[5 empty] | 1641 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 787 | 1117 | 2012 | 2762 | 865000
[5 empty] | 1649 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 699 | 1118 | 2007 | 6998 | 130130
[5 empty] | 1695 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 696 | 1119 | 2008 | 1118 | 120000
[5 empty] | 1651 | 69 | NULL | 9179 | NULL | NULL |  |  |  |  | 700 | 1121 | 2008 | 1118 | 400000
[5 empty] | 1694 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 701 | 1121 | 2009 | 1118 | 400000
[5 empty] | 1696 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 702 | 1121 | 2010 | 1118 | 400000
[5 empty] | 1673 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 703 | 1121 | 2011 | 1118 | 400000
[5 empty] | 1652 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 704 | 1121 | 2012 | 1118 | 400000
[5 empty] | 1644 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 705 | 1122 | 2008 | 1118 | 250000
[5 empty] | 1681 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 706 | 1122 | 2009 | 1118 | 400000
[5 empty] | 1447 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 707 | 1122 | 2010 | 1118 | 200000
[5 empty] | 1620 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 708 | 1122 | 2011 | 1118 | 300000
[5 empty] | 1627 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 709 | 1122 | 2012 | 1118 | 500000
[5 empty] | 1622 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 710 | 1123 | 2008 | 1118 | 350000
[5 empty] | 1687 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 711 | 1124 | 2008 | 2771 | 150000
[5 empty] | 1686 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 712 | 1124 | 2011 | 2771 | 150000
[5 empty] | 1618 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1498 | 1124 | 2012 | 2771 | 150000
[5 empty] | 1636 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1499 | 1124 | 2013 | 2771 | 150000
[5 empty] | 1635 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1500 | 1124 | 2014 | 2771 | 0
[5 empty] | 1677 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1501 | 1124 | 2015 | 2771 | 150000
[5 empty] | 1638 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1502 | 1124 | 2016 | 2771 | 0
[5 empty] | 1575 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2737 | 1124 | 2017 | 2734 | 50000
[5 empty] | 1637 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 1538 | 1124 | 2017 | 2771 | 100000
[5 empty] | 1745 | 82 | is | the | home | fund |  |  |  |  | 2264 | 1124 | 2019 | 2771 | 150000
[5 empty] | 1743 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 3728 | 1124 | 2021 | 2734 | 75000
[5 empty] | 1735 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 2429 | 1124 | 2021 | 2771 | 75000
[5 empty] | 1734 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 3036 | 1124 | 2023 | 2771 | 150000
[5 empty] | 1825 | 48 | NULL | NULL | NULL | NULL |  |  |  |  | 3735 | 1124 | 2025 | 2771 | 150000
[5 empty] | 1670 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 714 | 1125 | 2013 | 2771 | 250000
[5 empty] | 1601 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1539 | 1125 | 2014 | 2771 | 330000
[5 empty] | 1631 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 715 | 1126 | 2009 | 6998 | 183200
[5 empty] | 1657 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 716 | 1126 | 2012 | 6998 | 183200
[5 empty] | 1617 | 62 | NULL | 9137 | NULL | NULL |  |  |  |  | 717 | 1127 | 2015 | 2743 | 0
[5 empty] | 1616 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 718 | 1127 | 2019 | 2743 | 950000
[5 empty] | 1597 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 719 | 1128 | 2023 | 2180 | 736000
[5 empty] | 1683 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 2308 | 1128 | 2023 | 2324 | 92000
[5 empty] | 1887 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1650 | 1128 | 2023 | 2710 | 92000
[5 empty] | 1759 | 69 | NULL | 9193 | NULL | NULL |  |  |  |  | 720 | 1129 | 2008 | 2710 | 200000
[5 empty] | 1781 | 69 | 73 | 9258 | NULL | NULL |  |  |  |  | 779 | 1130 | 2012 | 2721 | 50000
[5 empty] | 1782 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 780 | 1130 | 2013 | 2721 | 50000
[5 empty] | 1783 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 781 | 1130 | 2014 | 2762 | 50000
[5 empty] | 1784 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 782 | 1130 | 2015 | 2710 | 0
[5 empty] | 1785 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2276 | 1130 | 2016 | 2710 | 50000
[5 empty] | 1786 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2277 | 1130 | 2017 | 2710 | 50000
[5 empty] | 1787 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2278 | 1130 | 2018 | 2710 | 50000
[5 empty] | 1788 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 2279 | 1130 | 2019 | 2721 | 50000
[5 empty] | 1789 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 865 | 1131 | 2008 | 2769 | 85000
[5 empty] | 1790 | 69 | NULL | 9223 | NULL | NULL |  |  |  |  | 866 | 1131 | 2009 | 2769 | 90000
[5 empty] | 1791 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 805 | 1131 | 2009 | 27CP | 300000
[5 empty] | 1861 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 937 | 1132 | 2007 | 6907 | 250000
[5 empty] | 1862 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 769 | 1133 | 2006 | 6998 | 18000
[5 empty] | 1863 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 770 | 1133 | 2007 | 6998 | 180000
[5 empty] | 1872 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 721 | 1134 | 2008 | 6907 | 60000
[5 empty] | 1873 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 722 | 1134 | 2009 | 6907 | 615000
[5 empty] | 1874 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 725 | 1135 | 2009 | 6907 | 200000
[5 empty] | 1880 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 726 | 1136 | 2009 | 6907 | 50000
[5 empty] | 1888 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1655 | 1137 | 2015 | 2742 | 1200000
[5 empty] | 1758 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 729 | 1138 | 2010 | 6907 | 330000
[5 empty] | 1798 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 730 | 1139 | 2011 | 2742 | 100000
[5 empty] | 1799 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 731 | 1140 | 2011 | 6907 | 200000
[5 empty] | 1800 | 42 | NULL | 9277 | NULL | NULL |  |  |  |  | 732 | 1141 | 2008 | 6907 | 250000
[5 empty] | 1801 | 42 | NULL | 9193 | NULL | NULL |  |  |  |  | 733 | 1141 | 2009 | 6907 | 250000
[5 empty] | 1802 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 734 | 1142 | 2011 | 2742 | 225000
[5 empty] | 1803 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 735 | 1143 | 2008 | 6907 | 200000
[5 empty] | 1804 | 42 | NULL | 9268 | NULL | NULL |  |  |  |  | 736 | 1144 | 2018 | 2742 | 0
[5 empty] | 1805 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 4007 | 1144 | 2021 | 2742 | 100000
[5 empty] | 1806 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 737 | 1145 | 2007 | 2742 | 5000
[5 empty] | 1896 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1658 | 1145 | 2008 | 2742 | 75000
[5 empty] | 1897 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1660 | 1145 | 2012 | 2742 | 400000
[5 empty] | 1944 | 42 | NULL | 9245 | NULL | NULL |  |  |  |  | 738 | 1146 | 2009 | 6907 | 55000
[5 empty] | 1902 | 42 | NULL | 9226 | NULL | NULL |  |  |  |  | 740 | 1147 | 2015 | 2742 | 0
[5 empty] | 2004 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 739 | 1147 | 2016 | 2742 | 67800
[5 empty] | 1999 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2974 | 1147 | 2017 | 2742 | 440000
[5 empty] | 1933 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 741 | 1148 | 2010 | 6907 | 240000
[5 empty] | 2026 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 742 | 1149 | 2012 | 6907 | 120000
[5 empty] | 1901 | 42 | NULL | 9245 | NULL | NULL |  |  |  |  | 743 | 1150 | 2007 | 6998 | 380000
[5 empty] | 2062 | NULL | NULL | 9407 | NULL | NULL |  |  |  |  | 1228 | 1150 | 2008 | 2769 | 0
[5 empty] | 1988 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 744 | 1150 | 2008 | 2774 | 0
[5 empty] | 1991 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 745 | 1150 | 2008 | 6998 | 1610015
[5 empty] | 1989 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 746 | 1151 | 2005 | 6998 | 25000
[5 empty] | 1990 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 810 | 1151 | 2007 | 6998 | 253000
[5 empty] | 2003 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 812 | 1151 | 2008 | 6998 | 300000
[5 empty] | 2002 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 748 | 1151 | 2009 | 2299 | 560000
[5 empty] | 2054 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 750 | 1152 | 2008 | 2762 | 100000
[5 empty] | 1993 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 752 | 1152 | 2009 | 2296 | 1600000
[5 empty] | 1992 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 749 | 1152 | 2009 | 2762 | 2250000
[5 empty] | 2051 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 754 | 1152 | 2010 | 2296 | 1650000
[5 empty] | 1935 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 751 | 1152 | 2010 | 2762 | 1000000
[5 empty] | 1900 | 42 | NULL | 9275 | NULL | NULL |  |  |  |  | 756 | 1153 | 2016 | 2769 | 300000
[5 empty] | 1903 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 757 | 1154 | 2015 | 2769 | 0
[5 empty] | 1905 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1535 | 1154 | 2016 | 2769 | 0
[5 empty] | 1908 | 42 | NULL | 9245 | NULL | NULL |  |  |  |  | 1536 | 1154 | 2018 | 2769 | 0
[5 empty] | 1943 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2146 | 1154 | 2019 | 2769 | 0
[5 empty] | 1945 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3159 | 1154 | 2024 | 2769 | 395400
[5 empty] | 1983 | NULL | NULL | 9233 | NULL | NULL |  |  |  |  | 3160 | 1154 | 2025 | 2769 | 443100
[5 empty] | 1994 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 761 | 1155 | 2010 | 2769 | 100000
[5 empty] | 1995 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 766 | 1156 | 2018 | 2159 | 645600
[5 empty] | 1996 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 767 | 1156 | 2019 | 2159 | 4340400
[5 empty] | 2025 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 772 | 1157 | 2007 | 6907 | 3200000
[5 empty] | 2037 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 773 | 1157 | 2008 | 6907 | 5000000
[5 empty] | 2039 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 774 | 1157 | 2009 | 6907 | 1200000
[5 empty] | 2040 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1116 | 1157 | 2010 | 6907 | 1450000
[5 empty] | 2046 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1117 | 1157 | 2011 | 6907 | 200000
[5 empty] | 2047 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2299 | 1157 | 2014 | 6907 | 1300000
[5 empty] | 2048 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 784 | 1158 | 2009 | 2299 | 478800
[5 empty] | 2049 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1439 | 1158 | 2009 | 6998 | 48000
[5 empty] | 2053 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 785 | 1159 | 2007 | 2299 | 20000
[5 empty] | 2059 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 786 | 1159 | 2008 | 2299 | 197100
[5 empty] | 2064 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1461 | 1159 | 2008 | 6998 | 38772
[5 empty] | 2060 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 789 | 1160 | 2007 | 2299 | 128000
[5 empty] | 2061 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 816 | 1160 | 2007 | 2721 | 32000
[5 empty] | 1922 | 62 | NULL | 9240 | NULL | NULL |  |  |  |  | 790 | 1161 | 2007 | 2299 | 174400
[5 empty] | 1954 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 815 | 1161 | 2007 | 2721 | 43600
[5 empty] | 2044 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 795 | 1162 | 2009 | 2769 | 25000
[5 empty] | 1864 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 796 | 1162 | 2010 | 2769 | 110000
[5 empty] | 1951 | 62 | NULL | 9251 | NULL | NULL |  |  |  |  | 797 | 1163 | 2009 | 6998 | 200000
[5 empty] | 1978 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 799 | 1164 | 2008 | 6988 | 15000
[5 empty] | 1979 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 798 | 1164 | 2008 | 6998 | 15000
[5 empty] | 1977 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1004 | 1164 | 2009 | 6988 | 60000
[5 empty] | 1865 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1003 | 1164 | 2009 | 6998 | 60000
[5 empty] | 1953 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 3797 | 1165 | 2022 | 2762 | 80000
[5 empty] | 1750 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 800 | 1165 | 2022 | 2769 | 180000
[5 empty] | 2069 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 3799 | 1165 | 2023 | 2762 | 80000
[5 empty] | 1964 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 3798 | 1165 | 2023 | 2769 | 180000
[5 empty] | 1920 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 801 | 1166 | 2017 | 2769 | 0
[5 empty] | 2031 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 1731 | 1166 | 2018 | 2296 | 0
[5 empty] | 2033 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 802 | 1166 | 2019 | 2769 | 165000
[5 empty] | 1915 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 936 | 1168 | 2008 | 6998 | 750000
[5 empty] | 2029 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 806 | 1168 | 2010 | 1118 | 300000
[5 empty] | 1947 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 807 | 1169 | 2016 | 6998 | 400000
[5 empty] | 1821 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 817 | 1170 | 2012 | 2771 | 25000
[5 empty] | 1956 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 825 | 1171 | 2016 | 6998 | 250000
[5 empty] | 1950 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 826 | 1172 | 2012 | 1118 | 250000
[5 empty] | 2071 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 834 | 1173 | 2010 | 1625 | 60000
[5 empty] | 1948 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 836 | 1173 | 2010 | 2296 | 10000
[5 empty] | 1932 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 835 | 1173 | 2010 | 2710 | 60000
[5 empty] | 2067 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 837 | 1173 | 2011 | 1625 | 60000
[5 empty] | 2066 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 839 | 1173 | 2011 | 2296 | 10000
[5 empty] | 2073 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 838 | 1173 | 2011 | 2710 | 60000
[5 empty] | 2074 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 840 | 1173 | 2012 | 1625 | 60000
[5 empty] | 1971 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 842 | 1173 | 2012 | 2296 | 10000
[5 empty] | 1967 | NULL | NULL | NULL | NULL | NULL |  |  |  |  | 841 | 1173 | 2012 | 2710 | 60000
[5 empty] | 1926 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 843 | 1173 | 2013 | 1625 | 60000
[5 empty] | 1939 | 43 | NULL | 9245 | NULL | NULL |  |  |  |  | 845 | 1173 | 2013 | 2296 | 10000
[5 empty] | 2035 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 844 | 1173 | 2013 | 2710 | 60000
[5 empty] | 1946 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 847 | 1174 | 2012 | 2299 | 1875000
[5 empty] | 1938 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 848 | 1175 | 2007 | 2721 | 14000
[5 empty] | 1941 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 850 | 1175 | 2015 | 2299 | 120000
[5 empty] | 2065 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1485 | 1175 | 2015 | 2721 | 94000
[5 empty] | 2068 | 42 | NULL | 9284 | NULL | NULL |  |  |  |  | 853 | 1176 | 2013 | 6988 | 150000
[5 empty] | 1709 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 854 | 1177 | 2008 | 6907 | 19200000
[5 empty] | 1958 | 2710 | NULL | NULL | NULL | NULL |  |  |  |  | 856 | 1178 | 2012 | 2762 | 30000
[5 empty] | 1936 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 857 | 1178 | 2013 | 2762 | 170000
[5 empty] | 1894 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 858 | 1179 | 2011 | 2721 | 10000
[5 empty] | 1848 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 859 | 1179 | 2012 | 2762 | 20000
[5 empty] | 1849 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 860 | 1179 | 2013 | 2762 | 100000
[5 empty] | 1853 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 861 | 1180 | 2017 | 2743 | 250000
[5 empty] | 1854 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 862 | 1180 | 2018 | 2743 | 2500000
[5 empty] | 1855 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 863 | 1181 | 2008 | 6907 | 2450000
[5 empty] | 1856 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 868 | 1182 | 2008 | 2769 | 30000
[5 empty] | 1857 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 1690 | 1182 | 2011 | 2762 | 37500
[5 empty] | 1899 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 1665 | 1182 | 2011 | 2769 | 49000
[5 empty] | 2045 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 1691 | 1182 | 2012 | 2762 | 12500
[5 empty] | 2050 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 1666 | 1182 | 2012 | 2769 | 16000
[5 empty] | 2028 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 869 | 1183 | 2015 | 2769 | 200000
[5 empty] | 1889 | 70 | NULL | NULL | NULL | NULL |  |  |  |  | 870 | 1184 | 2009 | 6907 | 2700000
[5 empty] | 2056 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 871 | 1184 | 2010 | 6907 | 2700000
[5 empty] | 2085 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 872 | 1184 | 2011 | 6907 | 2700000
[5 empty] | 1744 | 62 | NULL | 9097 | NULL | NULL |  |  |  |  | 873 | 1184 | 2012 | 6907 | 2700000
[5 empty] | 2088 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 874 | 1184 | 2013 | 6907 | 2700000
[5 empty] | 2090 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 879 | 1185 | 2025 | 2742 | 642500
[5 empty] | 2091 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 3233 | 1185 | 2026 | 2742 | 557500
[5 empty] | 2089 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 880 | 1186 | 2025 | 2742 | 235000
[5 empty] | 2095 | 62 | NULL | 9263 | NULL | NULL |  |  |  |  | 881 | 1187 | 2008 | 2769 | 100000
[5 empty] | 1962 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 883 | 1187 | 2009 | 2296 | 880000
[5 empty] | 2125 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 882 | 1187 | 2009 | 2769 | 220000
[5 empty] | 2124 | 96 | 73 | 9290 | NULL | NULL |  |  |  |  | 884 | 1188 | 2009 | 6998 | 75000
[5 empty] | 2188 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 898 | 1189 | 2012 | 2772 | 25000
[5 empty] | 2225 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 902 | 1191 | 2007 | 2703 | 5000000
[5 empty] | 2226 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 903 | 1192 | 2009 | 2703 | 500000
[5 empty] | 2227 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 904 | 1192 | 2011 | 2703 | 1500000
[5 empty] | 2228 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 906 | 1193 | 2008 | 2260 | 4000000
[5 empty] | 2229 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 905 | 1193 | 2008 | 2703 | 4000000
[5 empty] | 2230 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 907 | 1194 | 2008 | 6998 | 1000000
[5 empty] | 2182 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 908 | 1194 | 2009 | 6998 | 1000000
[5 empty] | 2030 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 909 | 1194 | 2010 | 6998 | 100000
[5 empty] | 2157 | 69 | NULL | 9412 | NULL | NULL |  |  |  |  | 910 | 1194 | 2011 | 6998 | 100000
[5 empty] | 2156 | 10 | NULL | 9412 | NULL | NULL |  |  |  |  | 911 | 1194 | 2012 | 6998 | 100000
[5 empty] | 2134 | 69 | NULL | 9269 | NULL | NULL |  |  |  |  | 1478 | 1194 | 2013 | 6998 | 100000
[5 empty] | 2220 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1479 | 1194 | 2014 | 6998 | 100000
[5 empty] | 2239 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1480 | 1194 | 2015 | 6998 | 100000
[5 empty] | 2240 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 912 | 1195 | 2013 | 6907 | 10000000
[5 empty] | 2241 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 916 | 1196 | 2012 | 6998 | 250000
[5 empty] | 2233 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 918 | 1196 | 2013 | 6998 | 1210000
[5 empty] | 2235 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 919 | 1197 | 2007 | 6907 | 1475000
[5 empty] | 2234 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 927 | 1198 | 2011 | 2742 | 3600000
[5 empty] | 2224 | 72 | NULL | 9270 | NULL | NULL |  |  |  |  | 929 | 1199 | 2009 | 2710 | 430000
[5 empty] | 2098 | 62 | NULL | 9271 | NULL | NULL |  |  |  |  | 930 | 1199 | 2010 | 2710 | 430000
[5 empty] | 2083 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 931 | 1199 | 2011 | 2175 | 300000
[5 empty] | 2106 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1580 | 1199 | 2014 | 2710 | 0
[5 empty] | 2104 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 934 | 1200 | 2008 | 6998 | 525000
[5 empty] | 2105 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 935 | 1201 | 2008 | 6998 | 250000
[5 empty] | 2103 | 61 | NULL | NULL | NULL | NULL |  |  |  |  | 940 | 1202 | 2014 | 2743 | 0
[5 empty] | 2180 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 941 | 1202 | 2019 | 2743 | 1300000
[5 empty] | 2186 | 3 | NULL | NULL | NULL | NULL |  |  |  |  | 943 | 1203 | 2008 | 6907 | 250000
[5 empty] | 2153 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 945 | 1204 | 2011 | 1118 | 150000
[5 empty] | 2171 | $no$ | NULL | NULL | NULL | NULL |  |  |  |  | 947 | 1205 | 2011 | 6998 | 200000
[5 empty] | 2172 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 954 | 1206 | 2008 | 2771 | 125000
[5 empty] | 2148 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 951 | 1206 | 2009 | 2771 | 125000
[5 empty] | 2177 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 1858 | 1206 | 2012 | 2771 | 150000
[5 empty] | 2173 | 36 | NULL | NULL | NULL | NULL |  |  |  |  | 1859 | 1206 | 2013 | 2771 | 100000
[5 empty] | 2176 | 99 | NULL | NULL | NULL | NULL |  |  |  |  | 1800 | 1206 | 2014 | 2771 | 470000
[5 empty] | 2174 | 36 | NULL | NULL | NULL | NULL |  |  |  |  | 1801 | 1206 | 2015 | 2771 | 235000
[5 empty] | 2152 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1802 | 1206 | 2016 | 2771 | 250000
[5 empty] | 2244 | 63 | NULL | NULL | NULL | NULL |  |  |  |  | 1803 | 1206 | 2017 | 2771 | 200000
[5 empty] | 2123 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 2251 | 1206 | 2018 | 2771 | 250000
[5 empty] | 2164 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 2252 | 1206 | 2019 | 2771 | 400000
[5 empty] | 2131 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2412 | 1206 | 2020 | 2771 | 250000
[5 empty] | 2129 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3872 | 1206 | 2021 | 2260 | 150000
[5 empty] | 2136 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2413 | 1206 | 2021 | 2771 | 250000
[5 empty] | 2133 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3034 | 1206 | 2022 | 2771 | 250000
[5 empty] | 2109 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 3035 | 1206 | 2023 | 2771 | 250000
[5 empty] | 2130 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 3725 | 1206 | 2024 | 2771 | 250000
[5 empty] | 2110 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 3726 | 1206 | 2025 | 2771 | 250000
[5 empty] | 2108 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 993 | 1208 | 2010 | 2705 | 20000
[5 empty] | 2119 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 992 | 1208 | 2010 | 2721 | 50000
[5 empty] | 2116 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 995 | 1208 | 2011 | 2705 | 20000
[5 empty] | 2111 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 994 | 1208 | 2011 | 2721 | 50000
[5 empty] | 2114 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 998 | 1209 | 2008 | 2762 | 100000
[5 empty] | 2113 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 999 | 1209 | 2009 | 2762 | 250000
[5 empty] | 2112 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1000 | 1209 | 2010 | 2299 | 400000
[5 empty] | 2221 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1001 | 1209 | 2010 | 2762 | 100000
[5 empty] | 1976 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 1006 | 1210 | 2010 | 2742 | 500000
[5 empty] | 1975 | 21 | NULL | NULL | NULL | NULL |  |  |  |  | 1008 | 1211 | 2006 | 2718 | 500
[5 empty] | 2246 | 42 | NULL | 9275 | NULL | NULL |  |  |  |  | 1009 | 1211 | 2007 | 2703 | 5000
[5 empty] | 2247 | 43 | NULL | 9295 | NULL | NULL |  |  |  |  | 1010 | 1211 | 2007 | 6988 | 5000
[5 empty] | 1678 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1011 | 1211 | 2008 | 2703 | 75000
[5 empty] | 1642 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1012 | 1211 | 2008 | 6988 | 75000
[5 empty] | 1640 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1013 | 1212 | 2010 | 6907 | 0
[5 empty] | 1685 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1244 | 1217 | 2008 | 2296 | 850000
[5 empty] | 1629 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1245 | 1217 | 2008 | 2762 | 1754000
[5 empty] | 1688 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1248 | 1218 | 2009 | 2296 | 1194904
[5 empty] | 1684 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1246 | 1218 | 2009 | 2762 | 500000
[5 empty] | 1706 | 10 | NULL | NULL | NULL | NULL |  |  |  |  | 1249 | 1218 | 2010 | 2296 | 1810043
[5 empty] | 1690 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 1247 | 1218 | 2010 | 2762 | 3115000
[5 empty] | 1664 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 2972 | 1219 | 2015 | 2762 | 389300
[5 empty] | 1663 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 1518 | 1219 | 2016 | 2762 | 629800
[5 empty] | 1708 | 42 | NULL | 9225 | NULL | NULL |  |  |  |  | 2890 | 1219 | 2017 | 1625 | 19700
[5 empty] | 1605 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2404 | 1219 | 2017 | 2296 | 1840000
[5 empty] | 1602 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2402 | 1219 | 2017 | 2762 | 4492650
[5 empty] | 1609 | 72 | NULL | NULL | NULL | NULL |  |  |  |  | 2965 | 1219 | 2018 | 2296 | 788600
[5 empty] | 1621 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 2887 | 1219 | 2018 | 2762 | 922600
[5 empty] | 1626 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1023 | 1220 | 2009 | 6998 | 350000
[5 empty] | 1705 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1024 | 1220 | 2010 | 6998 | 5000
[5 empty] | 1703 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1075 | 1220 | 2011 | 6998 | 20000
[5 empty] | 1704 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1074 | 1220 | 2012 | 6998 | 462000
[5 empty] | 1599 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1121 | 1221 | 2009 | 6998 | 100000
[5 empty] | 1662 | $NO$ | NULL | NULL | NULL | NULL |  |  |  |  | 1120 | 1221 | 2010 | 6998 | 525000
[5 empty] | 1606 | 42 | NULL | 9286 | NULL | NULL |  |  |  |  | 1085 | 1222 | 2009 | 2296 | 15000
[5 empty] | 2036 | 42 | NULL | 9263 | NULL | NULL |  |  |  |  | 1086 | 1222 | 2009 | 2769 | 250000
[5 empty] | 1931 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1087 | 1222 | 2009 | 2782 | 80000
[5 empty] | 1955 | 62 | NULL | 9291 | NULL | NULL |  |  |  |  | 1302 | 1223 | 2010 | 2296 | 350000
[5 empty] | 1924 | 71 | NULL | NULL | NULL | NULL |  |  |  |  | 1300 | 1223 | 2010 | 2769 | 410000
[5 empty] | 2181 | 69 | NULL | NULL | NULL | NULL |  |  |  |  | 1301 | 1223 | 2010 | 2782 | 85000
[5 empty] | 1807 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2971 | 1224 | 2015 | 2769 | 59500
[5 empty] | 1808 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2893 | 1224 | 2016 | 2769 | 73300
[5 empty] | 1810 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 2894 | 1224 | 2017 | 2769 | 1342700
[5 empty] | 1809 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1328 | 1225 | 2009 | 6907 | 250000
[5 empty] | 1811 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1017 | 1226 | 2010 | 6907 | 675000
[5 empty] | 1812 | 92 | 73 | 9219 | NULL | NULL |  |  |  |  | 1701 | 1227 | 2015 | 2742 | 155000
[5 empty] | 1813 | 42 | NULL | 9213 | NULL | NULL |  |  |  |  | 2138 | 1227 | 2016 | 2742 | 2290000
[5 empty] | 1814 | 42 | NULL | 9218 | NULL | NULL |  |  |  |  | 1021 | 1228 | 2009 | 6907 | 600000
[5 empty] | 1815 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1083 | 1229 | 2010 | 2742 | 283000
[5 empty] | 1816 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1256 | 1230 | 2022 | 2748 | 1000000
[5 empty] | 1817 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1035 | 1231 | 2011 | 6998 | 150000
[5 empty] | 1818 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1037 | 1231 | 2012 | 2296 | 1323000
[5 empty] | 1819 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1036 | 1231 | 2012 | 6998 | 540000
[5 empty] | 1822 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1038 | 1232 | 2011 | 6998 | 100000
[5 empty] | 1828 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1039 | 1232 | 2012 | 6998 | 100000
[5 empty] | 1835 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1041 | 1232 | 2013 | 2296 | 1150000
[5 empty] | 1836 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1040 | 1232 | 2013 | 6998 | 435000
[5 empty] | 1838 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1059 | 1233 | 2011 | 2743 | 60000
[5 empty] | 1839 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1065 | 1234 | 2011 | 6907 | 20000
[5 empty] | 1840 | 42 | NULL | 9276 | NULL | NULL |  |  |  |  | 1066 | 1234 | 2012 | 6907 | 15000
[5 empty] | 1841 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1067 | 1234 | 2013 | 6907 | 297000
[5 empty] | 1842 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1068 | 1235 | 2011 | 6907 | 40000
[5 empty] | 1843 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1069 | 1235 | 2012 | 6907 | 400000
[5 empty] | 1844 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1028 | 1236 | 2010 | 2762 | 75000
[5 empty] | 1860 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1029 | 1236 | 2011 | 2762 | 1500000
[5 empty] | 1837 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1030 | 1236 | 2012 | 2296 | 0
[5 empty] | 1867 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1031 | 1237 | 2011 | 6998 | 90000
[5 empty] | 1876 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1032 | 1237 | 2012 | 6998 | 90000
[5 empty] | 1883 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1033 | 1237 | 2013 | 2296 | 1400000
[5 empty] | 1884 | 42 | NULL | NULL | NULL | NULL |  |  |  |  | 1034 | 1237 | 2013 | 6998 | 550000
[5 empty] | 1760 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1720 | 1238 | 2011 | 2160 | 216907
[5 empty] | 1761 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1267 | 1238 | 2011 | 2769 | 72303
[5 empty] | 1792 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1721 | 1238 | 2012 | 2769 | 30000
[5 empty] | 1793 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1070 | 1239 | 2009 | 2769 | 30000
[5 empty] | 1794 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1072 | 1239 | 2012 | 2769 | 150000
[5 empty] | 1795 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1073 | 1239 | 2013 | 2769 | 1110000
[5 empty] | 1796 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1161 | 1240 | 2009 | 2762 | 145000
[5 empty] | 1823 | 43 | NULL | 9296 | NULL | NULL |  |  |  |  | 1574 | 1240 | 2012 | 2762 | 100000
[5 empty] | 1824 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1575 | 1240 | 2013 | 2762 | 2955000
[5 empty] | 1829 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1049 | 1241 | 2013 | 2769 | 0
[5 empty] | 1830 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1050 | 1241 | 2015 | 2769 | 902000
[5 empty] | 1831 | 43 | NULL | 9252 | NULL | NULL |  |  |  |  | 1051 | 1241 | 2016 | 2769 | 810000
[5 empty] | 1832 | 43 | NULL | 9273 | NULL | NULL |  |  |  |  | 1052 | 1241 | 2017 | 2769 | 780000
[5 empty] | 1845 | 43 | NULL | 9245 | NULL | NULL |  |  |  |  | 1061 | 1242 | 2011 | 2743 | 230000
[5 empty] | 1846 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1870 | 1242 | 2012 | 2743 | 10000
[5 empty] | 1859 | 43 | NULL | NULL | NULL | NULL |  |  |  |  | 1046 | 1243 | 2014 | 2762 | 100000
[5 empty] | 1763 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1047 | 1243 | 2015 | 2762 | 1000000
[5 empty] | 1764 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1063 | 1244 | 2010 | 6907 | 32000
[5 empty] | 1765 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1064 | 1244 | 2011 | 6907 | 353000
[5 empty] | 1766 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 1053 | 1245 | 2010 | 6907 | 750000
[5 empty] | 1767 | 62 | NULL | 9276 | NULL | NULL |  |  |  |  | 1054 | 1246 | 2012 | 2743 | 275000
[5 empty] | 1768 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 2008 | 1246 | 2013 | 2743 | 50000
[5 empty] | 1769 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 2009 | 1246 | 2014 | 2743 | 275000
[5 empty] | 1770 | 62 | NULL | NULL | NULL | NULL |  |  |  |  | 2133 | 1246 | 2016 | 2743 | 275000
[15 empty] | 2134 | 1246 | 2018 | 2743 | 400000
[15 empty] | 2955 | 1246 | 2019 | 2743 | 400000
[15 empty] | 2627 | 1246 | 2020 | 2743 | 400000
[15 empty] | 2956 | 1246 | 2021 | 2743 | 400000
[15 empty] | 2957 | 1246 | 2022 | 2743 | 400000
[15 empty] | 2958 | 1246 | 2023 | 2743 | 400000
[15 empty] | 4038 | 1246 | 2024 | 2743 | 400000
[15 empty] | 4039 | 1246 | 2025 | 2743 | 400000
[15 empty] | 1055 | 1247 | 2021 | 2710 | 25000
[15 empty] | 2438 | 1247 | 2021 | 2742 | 25000
[15 empty] | 2840 | 1247 | 2022 | 2710 | 375000
[15 empty] | 2841 | 1247 | 2022 | 2742 | 375000
[15 empty] | 1056 | 1248 | 2013 | 2710 | 350000
[15 empty] | 1057 | 1249 | 2016 | 2710 | 600000
[15 empty] | 1058 | 1250 | 2017 | 2742 | 3000000
[15 empty] | 1077 | 1251 | 2010 | 6998 | 2030000
[15 empty] | 1078 | 1251 | 2011 | 6998 | 3500000
[15 empty] | 1112 | 1252 | 2014 | 2175 | 100000
[15 empty] | 1111 | 1252 | 2015 | 2175 | 245000
[15 empty] | 2433 | 1252 | 2016 | 2175 | 100000
[15 empty] | 1084 | 1254 | 2009 | 6907 | 25000000
[15 empty] | 1865 | 1254 | 2012 | 6907 | 25000000
[15 empty] | 1088 | 1255 | 2010 | 6998 | 572018
[15 empty] | 1089 | 1256 | 2015 | 2743 | 0
[15 empty] | 1534 | 1256 | 2024 | 2743 | 930000
[15 empty] | 3173 | 1256 | 2025 | 2743 | 1170000
[15 empty] | 1093 | 1257 | 2010 | 6998 | 4211242
[15 empty] | 1148 | 1258 | 2011 | 2710 | 85000
[15 empty] | 1100 | 1260 | 2010 | 2769 | 62260
[15 empty] | 1325 | 1261 | 2013 | 6907 | 515000
[15 empty] | 1327 | 1262 | 2025 | 2742 | 485000
[15 empty] | 3247 | 1262 | 2026 | 2742 | 615000
[15 empty] | 1094 | 1263 | 2009 | 2260 | 20000
[15 empty] | 1095 | 1263 | 2009 | 2769 | 101975
[15 empty] | 1096 | 1263 | 2009 | 2771 | 8700
[15 empty] | 1097 | 1263 | 2009 | 6998 | 112175
[15 empty] | 1099 | 1263 | 2010 | 2771 | 25000
[15 empty] | 1255 | 1264 | 2022 | 2748 | 180000
[15 empty] | 3551 | 1264 | 2023 | 2748 | 150000
[15 empty] | 1151 | 1265 | 2014 | 2710 | 175000
[15 empty] | 1146 | 1266 | 2016 | 2710 | 90000
[15 empty] | 1147 | 1267 | 2018 | 2710 | 280000
[15 empty] | 1136 | 1268 | 2013 | 2160 | 116940
[15 empty] | 1142 | 1268 | 2013 | 2712 | 7310
[15 empty] | 1138 | 1268 | 2013 | 2721 | 7310
[15 empty] | 1141 | 1268 | 2013 | 2722 | 7310
[15 empty] | 1137 | 1268 | 2013 | 2769 | 7310
[15 empty] | 1156 | 1269 | 2009 | 2710 | 615000
[15 empty] | 1133 | 1269 | 2010 | 2710 | 150000
[15 empty] | 1102 | 1270 | 2024 | 2769 | 420000
[15 empty] | 3174 | 1270 | 2025 | 2769 | 522000
[15 empty] | 1260 | 1271 | 2010 | 2299 | 263250
[15 empty] | 1259 | 1271 | 2010 | 6998 | 6750
[15 empty] | 1258 | 1272 | 2021 | 2260 | 3670800
[15 empty] | 1257 | 1272 | 2021 | 2748 | 193200
[15 empty] | 1813 | 1273 | 2013 | 27X2 | 250000
[15 empty] | 1815 | 1273 | 2014 | 27X2 | 260000
[15 empty] | 1109 | 1274 | 2010 | 27X2 | 100000
[15 empty] | 1293 | 1275 | 2013 | 27X2 | 0
[15 empty] | 1292 | 1275 | 2014 | 27X2 | 0
[15 empty] | 1145 | 1275 | 2015 | 27X2 | 0
[15 empty] | 1290 | 1275 | 2016 | 27X2 | 0
[15 empty] | 1291 | 1275 | 2017 | 27X2 | 30000
[15 empty] | 2481 | 1275 | 2018 | 27X2 | 30000
[15 empty] | 1122 | 1276 | 2019 | 2769 | 200000
[15 empty] | 1125 | 1279 | 2011 | 2742 | 90000
[15 empty] | 1272 | 1279 | 2011 | 2743 | 20000
[15 empty] | 1273 | 1279 | 2011 | 2769 | 0
[15 empty] | 1127 | 1280 | 2016 | 2761 | 0
[15 empty] | 1648 | 1280 | 2017 | 2761 | 0
[15 empty] | 2229 | 1280 | 2018 | 2761 | 400000
[15 empty] | 2230 | 1280 | 2019 | 2761 | 400000
[15 empty] | 2559 | 1280 | 2020 | 2761 | 3600000
[15 empty] | 1128 | 1281 | 2009 | 2761 | 600000
[15 empty] | 1129 | 1281 | 2012 | 2180 | 870000
[15 empty] | 1130 | 1281 | 2015 | 2180 | 2030000
[15 empty] | 1131 | 1282 | 2014 | 2761 | 40000
[15 empty] | 1132 | 1282 | 2015 | 2761 | 153000
[15 empty] | 1134 | 1283 | 2013 | 2761 | 0
[15 empty] | 1135 | 1283 | 2014 | 2761 | 40000
[15 empty] | 1140 | 1284 | 2017 | 2761 | 0
[15 empty] | 3407 | 1284 | 2022 | 2296 | 0
[15 empty] | 1139 | 1284 | 2022 | 2761 | 198500
[15 empty] | 1143 | 1285 | 2012 | 2761 | 40000
[15 empty] | 1144 | 1285 | 2013 | 2180 | 106000
[15 empty] | 1149 | 1286 | 2016 | 2761 | 30000
[15 empty] | 1150 | 1286 | 2017 | 2761 | 63000
[15 empty] | 1152 | 1287 | 2013 | 2761 | 40000
[15 empty] | 1153 | 1287 | 2014 | 2761 | 157000
[15 empty] | 1154 | 1288 | 2014 | 2296 | 0
[15 empty] | 3211 | 1288 | 2015 | 2336 | 20000
[15 empty] | 2329 | 1288 | 2015 | 2761 | 7700
[15 empty] | 1155 | 1288 | 2020 | 2296 | 122150
[15 empty] | 3213 | 1288 | 2020 | 2761 | 122150
[15 empty] | 1157 | 1289 | 2023 | 2296 | 100000
[15 empty] | 1158 | 1289 | 2024 | 2296 | 250000
[15 empty] | 1159 | 1289 | 2025 | 2296 | 3090000
[15 empty] | 3938 | 1289 | 2025 | 2324 | 0
[15 empty] | 1162 | 1290 | 2014 | 2180 | 100000
[15 empty] | 1163 | 1290 | 2015 | 2180 | 200000
[15 empty] | 1164 | 1290 | 2016 | 2180 | 2060000
[15 empty] | 1165 | 1292 | 2014 | 2180 | 100000
[15 empty] | 1166 | 1292 | 2015 | 2180 | 150000
[15 empty] | 1167 | 1292 | 2016 | 2180 | 1030000
[15 empty] | 1168 | 1293 | 2023 | 2296 | 100000
[15 empty] | 1169 | 1293 | 2024 | 2296 | 200000
[15 empty] | 1170 | 1293 | 2025 | 2296 | 2060000
[15 empty] | 3939 | 1293 | 2025 | 2324 | 0
[15 empty] | 1173 | 1294 | 2010 | 1625 | 30000
[15 empty] | 1171 | 1294 | 2010 | 2761 | 10000
[15 empty] | 1172 | 1294 | 2011 | 1625 | 30000
[15 empty] | 1174 | 1294 | 2011 | 2761 | 10000
[15 empty] | 1175 | 1294 | 2012 | 1625 | 30000
[15 empty] | 1176 | 1294 | 2012 | 2761 | 10000
[15 empty] | 1177 | 1294 | 2013 | 1625 | 30000
[15 empty] | 1178 | 1294 | 2013 | 2761 | 10000
[15 empty] | 1179 | 1294 | 2016 | 1625 | 30000
[15 empty] | 1180 | 1294 | 2016 | 2761 | 0
[15 empty] | 1528 | 1294 | 2017 | 1625 | 30000
[15 empty] | 1529 | 1294 | 2017 | 2761 | 0
[15 empty] | 2593 | 1294 | 2018 | 1625 | 30000
[15 empty] | 2595 | 1294 | 2019 | 1625 | 30000
[15 empty] | 2596 | 1294 | 2020 | 1625 | 30000
[15 empty] | 2597 | 1294 | 2021 | 1625 | 30000
[15 empty] | 1181 | 1295 | 2010 | 1625 | 30000
[15 empty] | 1182 | 1295 | 2010 | 2761 | 10000
[15 empty] | 1183 | 1295 | 2011 | 1625 | 30000
[15 empty] | 1184 | 1295 | 2011 | 2761 | 10000
[15 empty] | 1185 | 1295 | 2012 | 1625 | 30000
[15 empty] | 1186 | 1295 | 2012 | 2761 | 10000
[15 empty] | 1187 | 1295 | 2013 | 1625 | 30000
[15 empty] | 1188 | 1295 | 2013 | 2761 | 10000
[15 empty] | 1189 | 1295 | 2016 | 1625 | 30000
[15 empty] | 1190 | 1295 | 2016 | 2761 | 0
[15 empty] | 1524 | 1295 | 2017 | 1625 | 30000
[15 empty] | 1525 | 1295 | 2017 | 2761 | 0
[15 empty] | 2585 | 1295 | 2018 | 1625 | 30000
[15 empty] | 2586 | 1295 | 2019 | 1625 | 30000
[15 empty] | 2587 | 1295 | 2020 | 1625 | 30000
[15 empty] | 2588 | 1295 | 2021 | 1625 | 30000
[15 empty] | 1191 | 1296 | 2010 | 1625 | 30000
[15 empty] | 1192 | 1296 | 2010 | 2299 | 10000
[15 empty] | 1193 | 1296 | 2011 | 1625 | 30000
[15 empty] | 1194 | 1296 | 2011 | 2299 | 10000
[15 empty] | 1195 | 1296 | 2012 | 1625 | 30000
[15 empty] | 1196 | 1296 | 2012 | 2299 | 10000
[15 empty] | 1197 | 1296 | 2013 | 1625 | 30000
[15 empty] | 1198 | 1296 | 2013 | 2299 | 10000
[15 empty] | 1199 | 1296 | 2016 | 1625 | 30000
[15 empty] | 1200 | 1296 | 2016 | 2299 | 0
[15 empty] | 1526 | 1296 | 2017 | 1625 | 30000
[15 empty] | 1527 | 1296 | 2017 | 2299 | 0
[15 empty] | 2589 | 1296 | 2018 | 1625 | 30000
[15 empty] | 2590 | 1296 | 2019 | 1625 | 30000
[15 empty] | 2591 | 1296 | 2020 | 1625 | 30000
[15 empty] | 2592 | 1296 | 2021 | 1625 | 30000
[15 empty] | 1201 | 1297 | 2010 | 2180 | 70000
[15 empty] | 1202 | 1297 | 2010 | 2721 | 18000
[15 empty] | 1204 | 1297 | 2011 | 2180 | 200000
[15 empty] | 1205 | 1297 | 2011 | 2721 | 48000
[15 empty] | 1208 | 1298 | 2010 | 2710 | 107000
[15 empty] | 1209 | 1298 | 2010 | 6999 | 320000
[15 empty] | 1206 | 1298 | 2011 | 2710 | 53000
[15 empty] | 1207 | 1298 | 2011 | 6999 | 160000
[15 empty] | 1210 | 1299 | 2016 | 2180 | 100000
[15 empty] | 1211 | 1300 | 2011 | 2180 | 100000
[15 empty] | 1213 | 1300 | 2012 | 2180 | 200000
[15 empty] | 1215 | 1301 | 2012 | 2721 | 100000
[15 empty] | 1282 | 1302 | 2009 | 2761 | 20000
[15 empty] | 1283 | 1302 | 2010 | 2721 | 54650
[15 empty] | 1776 | 1302 | 2010 | 2745 | 104700
[15 empty] | 1284 | 1302 | 2010 | 2761 | 54650
[15 empty] | 1777 | 1302 | 2010 | 6647 | 1258400
[15 empty] | 1778 | 1302 | 2010 | 6999 | 43700
[15 empty] | 1780 | 1302 | 2011 | 6647 | 1551100
[15 empty] | 1779 | 1302 | 2011 | 6999 | 30700
[15 empty] | 1781 | 1302 | 2012 | 6647 | 26736600
[15 empty] | 1783 | 1302 | 2012 | 6999 | 49700
[15 empty] | 1782 | 1302 | 2013 | 6647 | 13348300
[15 empty] | 1784 | 1302 | 2013 | 6999 | 24800
[15 empty] | 1216 | 1303 | 2016 | 2180 | 0
[15 empty] | 1217 | 1303 | 2018 | 2296 | 540000
[15 empty] | 1219 | 1304 | 2016 | 2772 | 500000
[15 empty] | 2755 | 1304 | 2017 | 2772 | 1000000
[15 empty] | 1220 | 1305 | 2015 | 2772 | 0
[15 empty] | 2529 | 1305 | 2016 | 2772 | 50000
[15 empty] | 3099 | 1305 | 2017 | 2772 | 80000
[15 empty] | 3040 | 1305 | 2020 | 2772 | 470000
[15 empty] | 3041 | 1305 | 2021 | 2772 | 705000
[15 empty] | 1221 | 1306 | 2010 | 2772 | 204000
[15 empty] | 1222 | 1306 | 2011 | 2772 | 182000
[15 empty] | 1223 | 1306 | 2012 | 2772 | 88000
[15 empty] | 1224 | 1306 | 2013 | 2772 | 82500
[15 empty] | 1225 | 1307 | 2009 | 6998 | 252000
[15 empty] | 1761 | 1307 | 2012 | 6998 | 273000
[15 empty] | 1226 | 1308 | 2010 | 6998 | 1264524
[15 empty] | 1234 | 1309 | 2012 | 2769 | 50000
[15 empty] | 1890 | 1309 | 2013 | 2769 | 300000
[15 empty] | 1231 | 1310 | 2013 | 2769 | 100000
[15 empty] | 1232 | 1310 | 2014 | 2769 | 0
[15 empty] | 1233 | 1310 | 2015 | 2769 | 100000
[15 empty] | 1785 | 1310 | 2016 | 2769 | 100000
[15 empty] | 1786 | 1310 | 2017 | 2769 | 100000
[15 empty] | 2144 | 1310 | 2018 | 2769 | 100000
[15 empty] | 2145 | 1310 | 2019 | 2769 | 100000
[15 empty] | 2686 | 1310 | 2020 | 2769 | 150000
[15 empty] | 2687 | 1310 | 2021 | 2769 | 150000
[15 empty] | 3154 | 1310 | 2022 | 2769 | 150000
[15 empty] | 3155 | 1310 | 2023 | 2769 | 150000
[15 empty] | 3182 | 1310 | 2024 | 2769 | 150000
[15 empty] | 3183 | 1310 | 2025 | 2769 | 150000
[15 empty] | 1235 | 1311 | 2010 | 2159 | 50000
[15 empty] | 1236 | 1311 | 2011 | 2159 | 250000
[15 empty] | 1237 | 1311 | 2012 | 2159 | 1400000
[15 empty] | 1254 | 1312 | 2012 | 6988 | 1900000
[15 empty] | 1238 | 1313 | 2014 | 2762 | 0
[15 empty] | 1239 | 1313 | 2015 | 2762 | 0
[15 empty] | 2234 | 1313 | 2016 | 2762 | 50000
[15 empty] | 3048 | 1313 | 2017 | 2762 | 66200
[15 empty] | 2235 | 1313 | 2017 | 6814 | 500000
[15 empty] | 3320 | 1313 | 2018 | 2762 | 54000
[15 empty] | 2236 | 1313 | 2018 | 6814 | 240000
[15 empty] | 2274 | 1313 | 2019 | 6814 | 150000
[15 empty] | 2578 | 1313 | 2020 | 2762 | 150000
[15 empty] | 2579 | 1313 | 2021 | 2762 | 150000
[15 empty] | 3511 | 1313 | 2022 | 2762 | 150000
[15 empty] | 3512 | 1313 | 2023 | 2762 | 150000
[15 empty] | 1340 | 1315 | 2010 | 2180 | 31000000
[15 empty] | 1339 | 1315 | 2010 | 2710 | 1000000
[15 empty] | 1342 | 1315 | 2011 | 2180 | 31000000
[15 empty] | 1341 | 1315 | 2011 | 2710 | 1000000
[15 empty] | 1281 | 1316 | 2024 | 2180 | 143000000
[15 empty] | 2309 | 1316 | 2024 | 2324 | 180000
[15 empty] | 2310 | 1316 | 2024 | 2703 | 90000
[15 empty] | 2311 | 1316 | 2024 | 2710 | 90000
[15 empty] | 1240 | 1318 | 2013 | 2721 | 50000
[15 empty] | 1241 | 1319 | 2016 | 2721 | 3200000
[15 empty] | 1242 | 1320 | 2016 | 2721 | 50000
[15 empty] | 1243 | 1321 | 2016 | 2721 | 750000
[15 empty] | 1253 | 1322 | 2013 | 6988 | 2000000
[15 empty] | 1252 | 1323 | 2010 | 2296 | 5700000
[15 empty] | 1251 | 1323 | 2010 | 6998 | 500000
[15 empty] | 1264 | 1324 | 2010 | 2762 | 0
[15 empty] | 1265 | 1324 | 2011 | 2762 | 0
[15 empty] | 1738 | 1324 | 2013 | 2762 | 0
[15 empty] | 1739 | 1324 | 2014 | 2762 | 180000
[15 empty] | 1740 | 1324 | 2015 | 2762 | 1463250
[15 empty] | 2508 | 1324 | 2016 | 2762 | 2384250
[15 empty] | 2646 | 1324 | 2017 | 2762 | 1463250
[15 empty] | 1570 | 1325 | 2012 | 2762 | 50000
[15 empty] | 1263 | 1325 | 2013 | 2762 | 200000
[15 empty] | 1823 | 1325 | 2014 | 2296 | 1600000
[15 empty] | 1520 | 1325 | 2014 | 2762 | 400000
[15 empty] | 1824 | 1325 | 2015 | 2296 | 1280000
[15 empty] | 1521 | 1325 | 2015 | 2762 | 320000
[15 empty] | 1262 | 1326 | 2022 | 2260 | 183350
[15 empty] | 1261 | 1326 | 2022 | 2748 | 9650
[15 empty] | 1270 | 1327 | 2010 | 2721 | 12000
[15 empty] | 1271 | 1328 | 2015 | 2721 | 75000
[15 empty] | 1274 | 1329 | 2010 | 2742 | 60000
[15 empty] | 1276 | 1330 | 2014 | 2721 | 350000
[15 empty] | 1277 | 1330 | 2015 | 2721 | 500000
[15 empty] | 2203 | 1331 | 2013 | 2721 | 15000
[15 empty] | 2335 | 1331 | 2014 | 2296 | 62580
[15 empty] | 1278 | 1331 | 2014 | 2762 | 27645
[15 empty] | 1296 | 1332 | 2011 | 2769 | 60000
[15 empty] | 1297 | 1332 | 2012 | 2769 | 315000
[15 empty] | 1298 | 1332 | 2013 | 2769 | 300000
[15 empty] | 1583 | 1332 | 2014 | 2769 | 300000
[15 empty] | 2069 | 1332 | 2015 | 2769 | 300000
[15 empty] | 2070 | 1332 | 2016 | 2769 | 414000
[15 empty] | 2631 | 1332 | 2017 | 2769 | 414000
[15 empty] | 2632 | 1332 | 2018 | 2769 | 414000
[15 empty] | 2633 | 1332 | 2019 | 2769 | 414000
[15 empty] | 2634 | 1332 | 2020 | 2769 | 414000
[15 empty] | 1303 | 1333 | 2012 | 2769 | 1000000
[15 empty] | 2179 | 1333 | 2013 | 2769 | 922000
[15 empty] | 2701 | 1333 | 2015 | 2769 | 578000
[15 empty] | 1304 | 1334 | 2014 | 2769 | 0
[15 empty] | 1889 | 1334 | 2015 | 2769 | 500000
[15 empty] | 1626 | 1334 | 2016 | 2769 | 0
[15 empty] | 1305 | 1335 | 2011 | 2769 | 500000
[15 empty] | 1757 | 1336 | 2014 | 2769 | 50000
[15 empty] | 1306 | 1336 | 2015 | 2769 | 1950000
[15 empty] | 1891 | 1337 | 2012 | 2769 | 200000
[15 empty] | 1307 | 1337 | 2013 | 2769 | 20000
[15 empty] | 1560 | 1337 | 2014 | 2769 | 1980000
[15 empty] | 1308 | 1338 | 2015 | 2159 | 5500000
[15 empty] | 1309 | 1340 | 2011 | 2769 | 230000
[15 empty] | 1313 | 1341 | 2014 | 2743 | 550000
[15 empty] | 1314 | 1342 | 2010 | 6907 | 400000
[15 empty] | 1789 | 1343 | 2016 | 2743 | 100000
[15 empty] | 1315 | 1343 | 2017 | 2743 | 750000
[15 empty] | 1316 | 1344 | 2011 | 6907 | 100000
[15 empty] | 1317 | 1344 | 2012 | 6907 | 550000
[15 empty] | 1318 | 1345 | 2017 | 2743 | 10000
[15 empty] | 2938 | 1345 | 2018 | 2743 | 310000
[15 empty] | 3454 | 1345 | 2019 | 2743 | 0
[15 empty] | 1319 | 1346 | 2019 | 2743 | 725000
[15 empty] | 1320 | 1347 | 2017 | 2743 | 175000
[15 empty] | 1323 | 1348 | 2013 | 2769 | 776250
[15 empty] | 2215 | 1349 | 2012 | 2762 | 100000
[15 empty] | 2216 | 1349 | 2013 | 2762 | 1607800
[15 empty] | 1329 | 1350 | 2010 | 2742 | 245000
[15 empty] | 1330 | 1351 | 2010 | 2710 | 400000
[15 empty] | 1331 | 1352 | 2011 | 2742 | 60000
[15 empty] | 1758 | 1352 | 2012 | 2742 | 750000
[15 empty] | 1332 | 1353 | 2011 | 2742 | 97000
[15 empty] | 2970 | 1354 | 2015 | 2742 | 83800
[15 empty] | 2964 | 1354 | 2016 | 2742 | 134600
[15 empty] | 2896 | 1354 | 2017 | 2742 | 1257890
[15 empty] | 1334 | 1355 | 2012 | 2742 | 420000
[15 empty] | 1335 | 1356 | 2026 | 2742 | 325000
[15 empty] | 1883 | 1357 | 2013 | 2742 | 0
[15 empty] | 1336 | 1357 | 2015 | 2742 | 120000
[15 empty] | 2613 | 1357 | 2016 | 2742 | 1351300
[15 empty] | 2614 | 1357 | 2016 | 2762 | 684000
[15 empty] | 1548 | 1358 | 2012 | 2742 | 100000
[15 empty] | 1549 | 1358 | 2013 | 2742 | 1100000
[15 empty] | 1338 | 1359 | 2025 | 2742 | 106000
[15 empty] | 3391 | 1359 | 2026 | 2742 | 129000
[15 empty] | 1343 | 1360 | 2010 | 2710
[15 empty] | 1346 | 1360 | 2011 | 2180
[15 empty] | 1345 | 1360 | 2011 | 2710
[15 empty] | 1344 | 1360 | 2024 | 2710 | 250000
[15 empty] | 1347 | 1361 | 2010 | 2762 | 560000
[15 empty] | 1348 | 1361 | 2011 | 2762 | 560000
[15 empty] | 1349 | 1361 | 2012 | 2762 | 560000
[15 empty] | 1350 | 1361 | 2013 | 2762 | 624000
[15 empty] | 1351 | 1361 | 2014 | 2762 | 928000
[15 empty] | 1352 | 1361 | 2015 | 2762 | 1350000
[15 empty] | 2014 | 1361 | 2016 | 2762 | 1340000
[15 empty] | 2076 | 1361 | 2017 | 2762 | 500000
[15 empty] | 2985 | 1361 | 2018 | 2721 | 50000
[15 empty] | 2984 | 1361 | 2018 | 2722 | 30000
[15 empty] | 1353 | 1362 | 2010 | 2703 | 1500000
[15 empty] | 1596 | 1362 | 2012 | 2703 | 135000
[15 empty] | 1926 | 1362 | 2013 | 2703 | 265000
[15 empty] | 1355 | 1363 | 2010 | 2296 | 1250000
[15 empty] | 1356 | 1364 | 2014 | 2721 | 150000
[15 empty] | 1357 | 1364 | 2015 | 2721 | 150000
[15 empty] | 1358 | 1364 | 2016 | 2721 | 150000
[15 empty] | 1359 | 1364 | 2017 | 2721 | 150000
[15 empty] | 1360 | 1364 | 2018 | 2721 | 150000
[15 empty] | 1361 | 1364 | 2019 | 2721 | 150000
[15 empty] | 1364 | 1365 | 2010 | 2721 | 90000
[15 empty] | 1365 | 1365 | 2011 | 2721 | 90000
[15 empty] | 1366 | 1365 | 2012 | 2721 | 80000
[15 empty] | 1367 | 1365 | 2013 | 2721 | 80000
[15 empty] | 1368 | 1365 | 2014 | 2721 | 95000
[15 empty] | 1369 | 1365 | 2015 | 2721 | 95000
[15 empty] | 2100 | 1365 | 2016 | 2721 | 95000
[15 empty] | 2101 | 1365 | 2017 | 2721 | 95000
[15 empty] | 2103 | 1365 | 2018 | 2721 | 95000
[15 empty] | 2104 | 1365 | 2019 | 2721 | 95000
[15 empty] | 2567 | 1365 | 2020 | 2721 | 95000
[15 empty] | 2569 | 1365 | 2021 | 2721 | 95000
[15 empty] | 3065 | 1365 | 2022 | 2721 | 95000
[15 empty] | 3066 | 1365 | 2023 | 2721 | 95000
[15 empty] | 3934 | 1365 | 2024 | 2721 | 95000
[15 empty] | 3935 | 1365 | 2025 | 2721 | 95000
[15 empty] | 1370 | 1366 | 2022 | 6988 | 1500000
[15 empty] | 1371 | 1367 | 2019 | 2721 | 150000
[15 empty] | 1372 | 1368 | 2010 | 2762 | 85000
[15 empty] | 1894 | 1369 | 2013 | 2159 | 1292000
[15 empty] | 1571 | 1369 | 2013 | 2296 | 372900
[15 empty] | 1373 | 1369 | 2013 | 2762 | 50000
[15 empty] | 2211 | 1369 | 2014 | 2296 | 100000
[15 empty] | 2213 | 1369 | 2014 | 2299 | 115000
[15 empty] | 2210 | 1369 | 2014 | 2762 | 1125000
[15 empty] | 1374 | 1370 | 2014 | 2762 | 150000
[15 empty] | 1375 | 1370 | 2015 | 2762 | 150000
[15 empty] | 1376 | 1370 | 2016 | 2762 | 150000
[15 empty] | 1377 | 1370 | 2017 | 2762 | 150000
[15 empty] | 1378 | 1370 | 2018 | 2762 | 150000
[15 empty] | 1379 | 1370 | 2019 | 2762 | 150000
[15 empty] | 1380 | 1370 | 2020 | 2762 | 150000
[15 empty] | 1381 | 1370 | 2021 | 2762 | 150000
[15 empty] | 1382 | 1371 | 2010 | 2771 | 0
[15 empty] | 1383 | 1371 | 2011 | 2771 | 207000
[15 empty] | 1384 | 1371 | 2012 | 2771 | 207000
[15 empty] | 1385 | 1371 | 2013 | 2771 | 150000
[15 empty] | 1386 | 1371 | 2014 | 2771 | 75000
[15 empty] | 2426 | 1371 | 2015 | 2734 | 75000
[15 empty] | 1387 | 1371 | 2015 | 2771 | 75000
[15 empty] | 2247 | 1371 | 2016 | 2771 | 75000
[15 empty] | 2248 | 1371 | 2017 | 2771 | 75000
[15 empty] | 2249 | 1371 | 2018 | 2771 | 100000
[15 empty] | 2250 | 1371 | 2019 | 2771 | 100000
[15 empty] | 2500 | 1371 | 2020 | 2771 | 100000
[15 empty] | 2501 | 1371 | 2021 | 2771 | 50000
[15 empty] | 3871 | 1371 | 2021 | 6988 | 50000
[15 empty] | 3032 | 1371 | 2022 | 2771 | 100000
[15 empty] | 3033 | 1371 | 2023 | 2771 | 100000
[15 empty] | 3723 | 1371 | 2024 | 2771 | 100000
[15 empty] | 3724 | 1371 | 2025 | 2771 | 100000
[15 empty] | 1388 | 1372 | 2010 | 2771 | 150000
[15 empty] | 1389 | 1372 | 2012 | 2771 | 250000
[15 empty] | 1390 | 1372 | 2013 | 2771 | 250000
[15 empty] | 1391 | 1372 | 2014 | 2771 | 80000
[15 empty] | 1392 | 1372 | 2015 | 2771 | 140000
[15 empty] | 1393 | 1372 | 2016 | 2771 | 0
[15 empty] | 2259 | 1372 | 2017 | 2771 | 100000
[15 empty] | 2260 | 1372 | 2018 | 2771 | 250000
[15 empty] | 2261 | 1372 | 2019 | 2771 | 320000
[15 empty] | 2427 | 1372 | 2020 | 2771 | 450000
[15 empty] | 2428 | 1372 | 2021 | 2771 | 300000
[15 empty] | 3730 | 1372 | 2023 | 2771 | 150000
[15 empty] | 3731 | 1372 | 2024 | 2771 | 150000
[15 empty] | 3732 | 1372 | 2025 | 2771 | 150000
[15 empty] | 1537 | 1373 | 2007 | 2718 | 102000
[15 empty] | 1394 | 1373 | 2018 | 2771 | 250000
[15 empty] | 1395 | 1373 | 2019 | 2260 | 2500000
[15 empty] | 1396 | 1374 | 2008 | 2718 | 154000
[15 empty] | 1397 | 1374 | 2011 | 6998 | 250000
[15 empty] | 1398 | 1374 | 2013 | 6998 | 250000
[15 empty] | 1399 | 1374 | 2015 | 6998 | 250000
[15 empty] | 1400 | 1374 | 2017 | 6998 | 250000
[15 empty] | 1401 | 1375 | 2022 | 2710 | 100000
[15 empty] | 1403 | 1376 | 2010 | 2180
[15 empty] | 1531 | 1376 | 2011 | 2710
[15 empty] | 1406 | 1376 | 2012 | 2180
[15 empty] | 1408 | 1376 | 2017 | 2180 | 400000
[15 empty] | 1649 | 1376 | 2017 | 2336 | 2480000
[15 empty] | 1533 | 1376 | 2017 | 2703 | 60000
[15 empty] | 1532 | 1376 | 2017 | 2710 | 60000
[15 empty] | 1409 | 1377 | 2010 | 2299 | 6000000
[15 empty] | 1410 | 1377 | 2010 | 6998 | 1000000
[15 empty] | 1411 | 1378 | 2012 | 2299 | 2000000
[15 empty] | 1413 | 1379 | 2016 | 2299 | 300000
[15 empty] | 1414 | 1380 | 2017 | 2761 | 0
[15 empty] | 1652 | 1380 | 2025 | 2296 | 750000
[15 empty] | 1651 | 1380 | 2025 | 2710 | 150000
[15 empty] | 1416 | 1381 | 2021 | 2180 | 250000000
[15 empty] | 3412 | 1381 | 2021 | 2324 | 30000000
[15 empty] | 3410 | 1381 | 2021 | 2336 | 200000000
[15 empty] | 3411 | 1381 | 2021 | 2703 | 10000000
[15 empty] | 1415 | 1381 | 2021 | 2710 | 10000000
[15 empty] | 1419 | 1382 | 2014 | 2710 | 150000
[15 empty] | 2290 | 1382 | 2015 | 2710 | 150000
[15 empty] | 1420 | 1383 | 2014 | 2721 | 0
[15 empty] | 1421 | 1383 | 2015 | 2721 | 0
[15 empty] | 1422 | 1383 | 2016 | 2721 | 0
[15 empty] | 1423 | 1383 | 2017 | 2721 | 0
[15 empty] | 1424 | 1383 | 2018 | 2721 | 0
[15 empty] | 2140 | 1383 | 2019 | 2721 | 0
[15 empty] | 3649 | 1383 | 2020 | 2721 | 50000
[15 empty] | 3650 | 1383 | 2021 | 2721 | 50000
[15 empty] | 1425 | 1384 | 2014 | 2721 | 0
[15 empty] | 1427 | 1384 | 2015 | 2721 | 0
[15 empty] | 1426 | 1384 | 2016 | 2721 | 150000
[15 empty] | 1428 | 1384 | 2017 | 2721 | 150000
[15 empty] | 1429 | 1384 | 2018 | 2721 | 150000
[15 empty] | 2141 | 1384 | 2019 | 2721 | 150000
[15 empty] | 1430 | 1385 | 2014 | 2721 | 127500
[15 empty] | 1431 | 1385 | 2015 | 2721 | 127500
[15 empty] | 1432 | 1385 | 2016 | 2721 | 127500
[15 empty] | 1433 | 1385 | 2017 | 2721 | 127500
[15 empty] | 1434 | 1385 | 2018 | 2721 | 127500
[15 empty] | 1435 | 1386 | 2015 | 2721 | 47000
[15 empty] | 1436 | 1387 | 2019 | 2721 | 50000
[15 empty] | 1437 | 1388 | 2022 | 2721 | 200000
[15 empty] | 1438 | 1389 | 2013 | 6998 | 90000
[15 empty] | 1448 | 1390 | 2010 | 2721 | 100000
[15 empty] | 2237 | 1391 | 2016 | 2299 | 0
[15 empty] | 2238 | 1391 | 2017 | 2299 | 0
[15 empty] | 2098 | 1391 | 2018 | 2299 | 0
[15 empty] | 1452 | 1391 | 2019 | 2299 | 0
[15 empty] | 2275 | 1391 | 2020 | 2299 | 1100000
[15 empty] | 2580 | 1391 | 2021 | 2299 | 1100000
[15 empty] | 2583 | 1391 | 2022 | 2299 | 1100000
[15 empty] | 3201 | 1391 | 2023 | 2299 | 1100000
[15 empty] | 3202 | 1391 | 2024 | 2299 | 15700000
[15 empty] | 1819 | 1392 | 2013 | 1628 | 0
[15 empty] | 1453 | 1392 | 2019 | 1628 | 350000
[15 empty] | 1455 | 1393 | 2014 | 2721 | 0
[15 empty] | 1456 | 1393 | 2014 | 2762 | 12100
[15 empty] | 1458 | 1393 | 2015 | 2296 | 2090580
[15 empty] | 1457 | 1393 | 2015 | 2762 | 1226000
[15 empty] | 1702 | 1393 | 2016 | 2762 | 0
[15 empty] | 2105 | 1393 | 2017 | 2721 | 0
[15 empty] | 2106 | 1393 | 2017 | 2762 | 0
[15 empty] | 1459 | 1394 | 2013 | 2721 | 40000
[15 empty] | 1460 | 1395 | 2015 | 2180 | 1500000
[15 empty] | 1463 | 1396 | 2016 | 2772 | 31000
[15 empty] | 1464 | 1396 | 2017 | 2772 | 302000
[15 empty] | 2239 | 1396 | 2018 | 2772 | 100000
[15 empty] | 2240 | 1396 | 2019 | 2772 | 450000
[15 empty] | 1468 | 1397 | 2018 | 6988 | 0
[15 empty] | 3102 | 1397 | 2024 | 1626 | 1125000
[15 empty] | 1470 | 1398 | 2013 | 2703 | 25000
[15 empty] | 1472 | 1398 | 2016 | 2703 | 0
[15 empty] | 1597 | 1398 | 2019 | 2703 | 25000
[15 empty] | 1481 | 1399 | 2013 | 2762 | 50000
[15 empty] | 1482 | 1399 | 2014 | 2762 | 150000
[15 empty] | 2028 | 1399 | 2015 | 2762 | 1530000
[15 empty] | 1484 | 1400 | 2007 | 2771 | 15000
[15 empty] | 1546 | 1400 | 2012 | 2771 | 15000
[15 empty] | 1545 | 1400 | 2013 | 2771 | 75000
[15 empty] | 1486 | 1401 | 2010 | 2771 | 250000
[15 empty] | 1487 | 1401 | 2011 | 2771 | 255000
[15 empty] | 1490 | 1401 | 2014 | 2771 | 150000
[15 empty] | 2430 | 1401 | 2015 | 2296 | 0
[15 empty] | 1491 | 1401 | 2015 | 2771 | 0
[15 empty] | 2735 | 1401 | 2016 | 2296 | 447500
[15 empty] | 2117 | 1401 | 2016 | 2771 | 350000
[15 empty] | 2736 | 1401 | 2017 | 2734 | 50000
[15 empty] | 2118 | 1401 | 2017 | 2771 | 100000
[15 empty] | 2119 | 1401 | 2018 | 2771 | 150000
[15 empty] | 2120 | 1401 | 2019 | 2771 | 200000
[15 empty] | 2431 | 1401 | 2020 | 2771 | 100000
[15 empty] | 3869 | 1401 | 2020 | 6814 | 100000
[15 empty] | 2432 | 1401 | 2021 | 2771 | 200000
[15 empty] | 3037 | 1401 | 2022 | 2771 | 200000
[15 empty] | 3038 | 1401 | 2023 | 2771 | 200000
[15 empty] | 3736 | 1401 | 2024 | 2771 | 200000
[15 empty] | 3737 | 1401 | 2025 | 2771 | 200000
[15 empty] | 1493 | 1402 | 2013 | 2771 | 150000
[15 empty] | 1494 | 1402 | 2014 | 2771 | 0
[15 empty] | 1495 | 1402 | 2015 | 2771 | 0
[15 empty] | 1496 | 1402 | 2016 | 2771 | 0
[15 empty] | 1497 | 1402 | 2017 | 2771 | 0
[15 empty] | 1817 | 1402 | 2018 | 2771 | 0
[15 empty] | 2265 | 1402 | 2019 | 2771 | 0
[15 empty] | 1503 | 1403 | 2014 | 2771 | 20000
[15 empty] | 2124 | 1403 | 2016 | 2771 | 25000
[15 empty] | 1504 | 1404 | 2013 | 2771 | 200000
[15 empty] | 2266 | 1404 | 2015 | 2771 | 100000
[15 empty] | 2414 | 1404 | 2017 | 2734 | 200000
[15 empty] | 3030 | 1404 | 2018 | 2771 | 0
[15 empty] | 3722 | 1404 | 2020 | 2734 | 50000
[15 empty] | 3031 | 1404 | 2020 | 2771 | 50000
[15 empty] | 3733 | 1404 | 2022 | 2771 | 100000
[15 empty] | 3734 | 1404 | 2024 | 2771 | 100000
[15 empty] | 1505 | 1405 | 2010 | 2771 | 6000
[15 empty] | 1540 | 1405 | 2011 | 2771 | 50000
[15 empty] | 1541 | 1405 | 2012 | 2771 | 300000
[15 empty] | 1542 | 1405 | 2013 | 2260 | 300000
[15 empty] | 1506 | 1406 | 2014 | 6998 | 225000
[15 empty] | 1507 | 1407 | 2014 | 6998 | 100000
[15 empty] | 1508 | 1408 | 2012 | 2771 | 250000
[15 empty] | 1509 | 1408 | 2013 | 2771 | 250000
[15 empty] | 1510 | 1408 | 2014 | 2771 | 150000
[15 empty] | 1511 | 1408 | 2015 | 2771 | 0
[15 empty] | 2262 | 1408 | 2017 | 2771 | 150000
[15 empty] | 2263 | 1408 | 2018 | 2771 | 150000
[15 empty] | 3000 | 1408 | 2022 | 2771 | 150000
[15 empty] | 2415 | 1409 | 2018 | 2734 | 0
[15 empty] | 1514 | 1409 | 2018 | 2771 | 200000
[15 empty] | 2417 | 1409 | 2019 | 2260 | 0
[15 empty] | 2416 | 1409 | 2019 | 2296 | 0
[15 empty] | 1812 | 1409 | 2019 | 2771 | 300000
[15 empty] | 3721 | 1410 | 2022 | 2260 | 100000
[15 empty] | 1515 | 1410 | 2022 | 2771 | 300000
[15 empty] | 3002 | 1410 | 2023 | 2771 | 400000
[15 empty] | 1516 | 1411 | 2011 | 6998 | 450000
[15 empty] | 1522 | 1412 | 2014 | 6998 | 300000
[15 empty] | 1544 | 1413 | 2017 | 2771 | 0
[15 empty] | 1523 | 1413 | 2024 | 2771 | 50000
[15 empty] | 2502 | 1413 | 2025 | 2771 | 500000
[15 empty] | 2066 | 1418 | 2014 | 2260 | 157700
[15 empty] | 1730 | 1418 | 2014 | 2748 | 8300
[15 empty] | 1834 | 1419 | 2011 | 2761 | 6000
[15 empty] | 1835 | 1419 | 2012 | 2299 | 70000
[15 empty] | 1836 | 1421 | 2011 | 2761 | 30000
[15 empty] | 1837 | 1421 | 2012 | 2299 | 157555
[15 empty] | 2197 | 1423 | 2022 | 2298 | 0
[15 empty] | 3403 | 1423 | 2022 | 2336 | 0
[15 empty] | 3834 | 1423 | 2024 | 2336 | 195000
[15 empty] | 3042 | 1423 | 2024 | 2762 | 195000
[15 empty] | 1550 | 1424 | 2010 | 2762 | 60000
[15 empty] | 1745 | 1424 | 2011 | 2762 | 550000
[15 empty] | 2366 | 1425 | 2014 | 2703 | 90000
[15 empty] | 2155 | 1425 | 2014 | 2762 | 362000
[15 empty] | 1563 | 1426 | 2012 | 2762 | 330000
[15 empty] | 2914 | 1427 | 2016 | 2762 | 52000
[15 empty] | 2154 | 1427 | 2017 | 2762 | 13000
[15 empty] | 2365 | 1427 | 2018 | 2703 | 0
[15 empty] | 2915 | 1427 | 2018 | 6814 | 0
[15 empty] | 3494 | 1427 | 2026 | 2762 | 700000
[15 empty] | 1555 | 1428 | 2011 | 2762 | 895000
[15 empty] | 1567 | 1429 | 2012 | 2762 | 200000
[15 empty] | 1922 | 1429 | 2013 | 2762 | 1500000
[15 empty] | 2153 | 1430 | 2013 | 2762 | 883000
[15 empty] | 1568 | 1431 | 2010 | 2762 | 100000
[15 empty] | 1742 | 1431 | 2011 | 2296 | 800000
[15 empty] | 1741 | 1431 | 2011 | 2762 | 500000
[15 empty] | 1703 | 1432 | 2012 | 2762 | 1100000
[15 empty] | 2202 | 1433 | 2015 | 2721 | 240000
[15 empty] | 1744 | 1435 | 2014 | 2762 | 0
[15 empty] | 2364 | 1435 | 2016 | 2703 | 50000
[15 empty] | 1743 | 1435 | 2016 | 2762 | 890000
[15 empty] | 1638 | 1437 | 2010 | 2762 | 64600
[15 empty] | 1641 | 1437 | 2012 | 2762 | 15000
[15 empty] | 1639 | 1437 | 2013 | 2762 | 1000000
[15 empty] | 1640 | 1437 | 2014 | 2762 | 200000
[15 empty] | 2195 | 1438 | 2016 | 2298 | 237500
[15 empty] | 2194 | 1438 | 2016 | 2762 | 237500
[15 empty] | 1602 | 1439 | 1998 | 2763 | 15000000
[15 empty] | 1601 | 1439 | 2012 | 2763 | 2000000
[15 empty] | 1603 | 1439 | 2013 | 2763 | 2000000
[15 empty] | 1604 | 1439 | 2017 | 2763 | 4000000
[15 empty] | 1653 | 1440 | 2018 | 2180 | 350000
[15 empty] | 1654 | 1440 | 2019 | 2324 | 1500000
[15 empty] | 1605 | 1442 | 2012 | 2769 | 390000
[15 empty] | 1723 | 1443 | 2012 | 2769 | 300000
[15 empty] | 1724 | 1443 | 2013 | 2769 | 600000
[15 empty] | 1725 | 1443 | 2014 | 2769 | 500000
[15 empty] | 1726 | 1443 | 2015 | 2769 | 500000
[15 empty] | 1727 | 1443 | 2016 | 2769 | 300000
[15 empty] | 1728 | 1443 | 2017 | 2769 | 300000
[15 empty] | 1729 | 1443 | 2018 | 2769 | 500000
[15 empty] | 2057 | 1443 | 2019 | 2769 | 500000
[15 empty] | 2681 | 1443 | 2020 | 2769 | 500000
[15 empty] | 2682 | 1443 | 2021 | 2769 | 500000
[15 empty] | 3117 | 1443 | 2022 | 2769 | 500000
[15 empty] | 3118 | 1443 | 2023 | 2769 | 500000
[15 empty] | 3179 | 1443 | 2024 | 2769 | 500000
[15 empty] | 3180 | 1443 | 2025 | 2769 | 500000
[15 empty] | 3181 | 1443 | 2026 | 2769 | 0
[15 empty] | 1704 | 1446 | 2011 | 2769 | 1395000
[15 empty] | 1888 | 1446 | 2012 | 2769 | 125000
[15 empty] | 2149 | 1447 | 2013 | 2769 | 40000
[15 empty] | 1893 | 1448 | 2012 | 2762 | 300000
[15 empty] | 1556 | 1448 | 2012 | 2769 | 455999
[15 empty] | 1554 | 1449 | 2013 | 2159 | 225000
[15 empty] | 2039 | 1449 | 2013 | 2769 | 225000
[15 empty] | 1772 | 1451 | 2025 | 2769 | 538000
[15 empty] | 1773 | 1451 | 2026 | 2769 | 762000
[15 empty] | 1632 | 1452 | 2009 | 2762 | 5500
[15 empty] | 1633 | 1452 | 2012 | 2299 | 0
[15 empty] | 1634 | 1452 | 2014 | 2299 | 0
[15 empty] | 1830 | 1453 | 2017 | 2769 | 400000
[15 empty] | 1722 | 1454 | 2025 | 2769 | 125000
[15 empty] | 3096 | 1454 | 2026 | 2769 | 175000
[15 empty] | 1831 | 1455 | 2016 | 2769 | 350000
[15 empty] | 1766 | 1456 | 2012 | 2769 | 60000
[15 empty] | 1606 | 1457 | 2012 | 2769 | 150000
[15 empty] | 1612 | 1458 | 2012 | 2772 | 125000
[15 empty] | 1614 | 1458 | 2013 | 2769 | 200000
[15 empty] | 1613 | 1458 | 2013 | 2772 | 175000
[15 empty] | 1593 | 1459 | 2012 | 2159 | 280000
[15 empty] | 1594 | 1459 | 2012 | 2245 | 280000
[15 empty] | 1558 | 1460 | 2012 | 2769 | 170000
[15 empty] | 1809 | 1460 | 2013 | 2245 | 170000
[15 empty] | 1680 | 1461 | 2012 | 2159 | 2200000
[15 empty] | 1681 | 1461 | 2012 | 2245 | 2200000
[15 empty] | 1764 | 1462 | 2016 | 2769 | 300000
[15 empty] | 1765 | 1462 | 2017 | 2159 | 1447000
[15 empty] | 1671 | 1463 | 2014 | 2159 | 1775000
[15 empty] | 1696 | 1464 | 2013 | 2159 | 0
[15 empty] | 3129 | 1464 | 2022 | 2769 | 0
[15 empty] | 1697 | 1464 | 2023 | 2769 | 710000
[15 empty] | 1693 | 1465 | 2013 | 2159 | 0
[15 empty] | 2186 | 1465 | 2019 | 2769 | 0
[15 empty] | 1694 | 1465 | 2021 | 2769 | 670000
[15 empty] | 1682 | 1466 | 2018 | 2159 | 300000
[15 empty] | 1810 | 1467 | 2012 | 2159 | 490000
[15 empty] | 1623 | 1467 | 2012 | 2245 | 490000
[15 empty] | 1769 | 1469 | 2012 | 2159 | 150000
[15 empty] | 1610 | 1470 | 2015 | 2159 | 0
[15 empty] | 1611 | 1470 | 2015 | 2769 | 170000
[15 empty] | 2698 | 1470 | 2017 | 2769 | 170000
[15 empty] | 3162 | 1470 | 2018 | 2769 | 170000
[15 empty] | 3163 | 1470 | 2019 | 2769 | 170000
[15 empty] | 3164 | 1470 | 2020 | 2769 | 170000
[15 empty] | 3165 | 1470 | 2021 | 2769 | 170000
[15 empty] | 3166 | 1470 | 2022 | 2769 | 170000
[15 empty] | 3167 | 1470 | 2023 | 2769 | 170000
[15 empty] | 3185 | 1470 | 2024 | 2769 | 170000
[15 empty] | 3186 | 1470 | 2025 | 2769 | 170000
[15 empty] | 3187 | 1470 | 2026 | 2769 | 170000
[15 empty] | 1615 | 1471 | 2012 | 7113 | 20000
[15 empty] | 1617 | 1471 | 2013 | 2743 | 40000
[15 empty] | 1618 | 1471 | 2013 | 2769 | 40000
[15 empty] | 1620 | 1472 | 2014 | 2769 | 180000
[15 empty] | 1579 | 1474 | 2011 | 2175 | 108000
[15 empty] | 1624 | 1475 | 2012 | 2772 | 100000
[15 empty] | 1971 | 1475 | 2014 | 2772 | 40000
[15 empty] | 1972 | 1475 | 2015 | 2772 | 40000
[15 empty] | 1973 | 1475 | 2016 | 2772 | 40000
[15 empty] | 1974 | 1475 | 2017 | 2772 | 40000
[15 empty] | 1975 | 1475 | 2018 | 2772 | 40000
[15 empty] | 2298 | 1475 | 2019 | 2772 | 40000
[15 empty] | 1598 | 1477 | 2010 | 2763 | 800000
[15 empty] | 1599 | 1477 | 2011 | 2763 | 800000
[15 empty] | 1600 | 1477 | 2014 | 2763 | 400000
[15 empty] | 2013 | 1477 | 2015 | 2763 | 450000
[15 empty] | 2356 | 1477 | 2017 | 2763 | 984768
[15 empty] | 2531 | 1477 | 2018 | 2763 | 1181490
[15 empty] | 2532 | 1477 | 2019 | 2763 | 0
[15 empty] | 2533 | 1477 | 2020 | 2763 | 0
[15 empty] | 3578 | 1477 | 2024 | 2763 | 1832497
[15 empty] | 1645 | 1484 | 2017 | 2761 | 0
[15 empty] | 1646 | 1484 | 2025 | 2710 | 125000
[15 empty] | 1647 | 1484 | 2026 | 2299 | 1000000
[15 empty] | 1716 | 1485 | 2012 | 2180 | 1200000
[15 empty] | 1715 | 1485 | 2012 | 6988 | 270000
[15 empty] | 1717 | 1485 | 2013 | 2710 | 15000
[15 empty] | 1719 | 1485 | 2014 | 2710 | 15000
[15 empty] | 1676 | 1490 | 2014 | 2710 | 200000
[15 empty] | 1677 | 1490 | 2015 | 2710 | 200000
[15 empty] | 1678 | 1490 | 2016 | 2710 | 200000
[15 empty] | 1679 | 1490 | 2017 | 2710 | 200000
[15 empty] | 1643 | 1492 | 2012 | 2743 | 1665000
[15 empty] | 1869 | 1492 | 2013 | 2743 | 85000
[15 empty] | 1705 | 1493 | 2011 | 2743 | 113000
[15 empty] | 1867 | 1493 | 2012 | 2743 | 30000
[15 empty] | 1557 | 1497 | 2012 | 2742 | 300000
[15 empty] | 1669 | 1498 | 2012 | 2742 | 170000
[15 empty] | 1706 | 1499 | 2011 | 2742 | 957000
[15 empty] | 1876 | 1499 | 2012 | 2742 | 125000
[15 empty] | 1877 | 1499 | 2013 | 2742 | 50000
[15 empty] | 1674 | 1500 | 2018 | 2710 | 300000
[15 empty] | 1635 | 1501 | 2014 | 2710 | 600000
[15 empty] | 2163 | 1502 | 2015 | 2710 | 38000
[15 empty] | 1636 | 1502 | 2016 | 2710 | 0
[15 empty] | 1637 | 1503 | 2017 | 2710 | 200000
[15 empty] | 1762 | 1504 | 2015 | 2710 | 400000
[15 empty] | 2720 | 1504 | 2016 | 2710
[15 empty] | 1767 | 1505 | 2018 | 2710 | 650000
[15 empty] | 1768 | 1505 | 2019 | 2710 | 4350000
[15 empty] | 1753 | 1506 | 2015 | 2721 | 70000
[15 empty] | 1754 | 1506 | 2016 | 2721 | 70000
[15 empty] | 1755 | 1506 | 2017 | 2721 | 70000
[15 empty] | 1756 | 1506 | 2018 | 2721 | 70000
[15 empty] | 2231 | 1506 | 2019 | 2721 | 70000
[15 empty] | 2232 | 1506 | 2020 | 2721 | 650000
[15 empty] | 1841 | 1507 | 2012 | 2159 | 1500000
[15 empty] | 1840 | 1507 | 2012 | 6988 | 500000
[15 empty] | 1839 | 1508 | 2016 | 2299 | 100000
[15 empty] | 1838 | 1508 | 2016 | 2721 | 10000
[15 empty] | 1814 | 1509 | 2018 | 2772 | 120000
[15 empty] | 3933 | 1509 | 2019 | 2772 | 280000
[15 empty] | 2952 | 1509 | 2020 | 2772 | 880000
[15 empty] | 2015 | 1510 | 2012 | 2743 | 50000
[15 empty] | 1553 | 1510 | 2013 | 2743 | 150000
[15 empty] | 1827 | 1511 | 2014 | 2743 | 250000
[15 empty] | 1582 | 1512 | 2014 | 2743 | 80000
[15 empty] | 2107 | 1512 | 2017 | 2743 | 0
[15 empty] | 1829 | 1513 | 2013 | 2743 | 1000000
[15 empty] | 1711 | 1514 | 2006 | 2721 | 509000
[15 empty] | 1712 | 1514 | 2006 | 2761 | 319000
[15 empty] | 1709 | 1514 | 2006 | 2762 | 602000
[15 empty] | 1710 | 1514 | 2010 | 2762 | 255000
[15 empty] | 1713 | 1514 | 2011 | 2299 | 16192905
[15 empty] | 2097 | 1514 | 2012 | 2742 | 195700
[15 empty] | 2095 | 1514 | 2012 | 2762 | 4614395
[15 empty] | 2096 | 1514 | 2012 | 2768 | 312000
[15 empty] | 1547 | 1515 | 2013 | 2742 | 2100000
[15 empty] | 1584 | 1516 | 2024 | 2742 | 750000
[15 empty] | 3218 | 1516 | 2025 | 2742 | 950000
[15 empty] | 1656 | 1517 | 2025 | 2742 | 140000
[15 empty] | 3378 | 1517 | 2026 | 2742 | 210000
[15 empty] | 1581 | 1518 | 2015 | 2742 | 600000
[15 empty] | 2480 | 1518 | 2015 | 2762 | 1300000
[15 empty] | 1625 | 1519 | 2011 | 2742 | 700000
[15 empty] | 1657 | 1520 | 2017 | 2742 | 119000
[15 empty] | 3225 | 1520 | 2018 | 2742 | 620300
[15 empty] | 3226 | 1520 | 2019 | 2742 | 500700
[15 empty] | 3353 | 1520 | 2019 | 2762 | 570000
[15 empty] | 1590 | 1521 | 2014 | 2710 | 0
[15 empty] | 1873 | 1521 | 2014 | 2742 | 0
[15 empty] | 1874 | 1521 | 2022 | 2710 | 50000
[15 empty] | 1875 | 1521 | 2022 | 2742 | 50000
[15 empty] | 2833 | 1521 | 2023 | 2710 | 350000
[15 empty] | 2834 | 1521 | 2023 | 2742 | 350000
[15 empty] | 2933 | 1521 | 2024 | 2710 | 350000
[15 empty] | 2934 | 1521 | 2024 | 2742 | 350000
[15 empty] | 1591 | 1522 | 2022 | 2710 | 100000
[15 empty] | 2842 | 1522 | 2023 | 2710 | 640000
[15 empty] | 2935 | 1522 | 2024 | 2710 | 210000
[15 empty] | 1627 | 1524 | 2012 | 1125 | 0
[15 empty] | 1771 | 1525 | 2016 | 2771 | 100000
[15 empty] | 2734 | 1525 | 2017 | 2703 | 0
[15 empty] | 1770 | 1525 | 2017 | 2771 | 50000
[15 empty] | 2418 | 1525 | 2018 | 2734 | 0
[15 empty] | 2562 | 1525 | 2018 | 6999 | 0
[15 empty] | 3452 | 1525 | 2020 | 2734 | 200000
[15 empty] | 3451 | 1525 | 2020 | 6999 | 750000
[15 empty] | 1825 | 1526 | 2011 | 2771 | 50000
[15 empty] | 1775 | 1527 | 2011 | 2742 | 300000
[15 empty] | 1774 | 1527 | 2011 | 2771 | 878160
[15 empty] | 1628 | 1528 | 2012 | 2771 | 100000
[15 empty] | 1857 | 1528 | 2013 | 2771 | 50000
[15 empty] | 2121 | 1528 | 2016 | 2771 | 150000
[15 empty] | 2123 | 1528 | 2017 | 2771 | 150000
[15 empty] | 2731 | 1528 | 2018 | 2771 | 0
[15 empty] | 3004 | 1528 | 2021 | 2771 | 0
[15 empty] | 2246 | 1528 | 2022 | 2771 | 150000
[15 empty] | 3729 | 1528 | 2025 | 2771 | 150000
[15 empty] | 1585 | 1529 | 2012 | 2743 | 225000
[15 empty] | 1586 | 1530 | 2013 | 2743 | 180000
[15 empty] | 1587 | 1532 | 2014 | 2743 | 180000
[15 empty] | 1828 | 1533 | 2014 | 2743 | 135000
[15 empty] | 1732 | 1534 | 2013 | 2743 | 560000
[15 empty] | 1826 | 1535 | 2014 | 2743 | 125000
[15 empty] | 1675 | 1536 | 2012 | 2743 | 260000
[15 empty] | 1816 | 1537 | 2019 | 2721 | 150000
[15 empty] | 1672 | 1541 | 2012 | 2159 | 825000
[15 empty] | 1673 | 1541 | 2012 | 2245 | 825000
[15 empty] | 1644 | 1542 | 2012 | 2742 | 160000
[15 empty] | 1664 | 1542 | 2013 | 2742 | 15000
[15 empty] | 1685 | 1544 | 2011 | 2762 | 246535
[15 empty] | 1683 | 1544 | 2012 | 2296 | 2353425
[15 empty] | 1684 | 1544 | 2012 | 2762 | 100000
[15 empty] | 1921 | 1544 | 2013 | 2762 | 600000
[15 empty] | 1749 | 1555 | 2013 | 2180 | 2240000
[15 empty] | 1750 | 1555 | 2013 | 2299 | 550000
[15 empty] | 1763 | 1555 | 2013 | 2761 | 10000
[15 empty] | 1751 | 1556 | 2011 | 2769 | 100000
[15 empty] | 1752 | 1556 | 2012 | 2769 | 1800000
[15 empty] | 1832 | 1557 | 2016 | 2762 | 0
[15 empty] | 2855 | 1557 | 2018 | 2762 | 60000
[15 empty] | 1833 | 1557 | 2018 | 6814 | 0
[15 empty] | 3503 | 1557 | 2020 | 2324 | 60000
[15 empty] | 1842 | 1568 | 2015 | 2769 | 95000
[15 empty] | 1843 | 1569 | 2012 | 2769 | 25000
[15 empty] | 1844 | 1569 | 2013 | 1125 | 110000
[15 empty] | 1845 | 1570 | 2012 | 2769 | 100000
[15 empty] | 1846 | 1570 | 2013 | 2159 | 1000000
[15 empty] | 1847 | 1571 | 2012 | 2742 | 1000000
[15 empty] | 2963 | 1572 | 2023 | 2742 | 0
[15 empty] | 1879 | 1572 | 2024 | 2742 | 1100000
[15 empty] | 2960 | 1572 | 2025 | 2742 | 1480000
[15 empty] | 1848 | 1573 | 2018 | 2742 | 0
[15 empty] | 2986 | 1573 | 2019 | 2742 | 1258560
[15 empty] | 3631 | 1573 | 2020 | 2742 | 314640
[15 empty] | 1851 | 1574 | 2013 | 2762 | 1090000
[15 empty] | 1852 | 1574 | 2014 | 2762 | 1272000
[15 empty] | 1853 | 1574 | 2015 | 2762 | 1632000
[15 empty] | 1854 | 1574 | 2016 | 2762 | 1350000
[15 empty] | 1855 | 1574 | 2017 | 2762 | 1050000
[15 empty] | 2574 | 1574 | 2018 | 2762 | 1375000
[15 empty] | 2575 | 1574 | 2019 | 2762 | 1175000
[15 empty] | 2576 | 1574 | 2020 | 2762 | 1050000
[15 empty] | 2577 | 1574 | 2021 | 2762 | 1050000
[15 empty] | 2853 | 1574 | 2022 | 2762 | 1050000
[15 empty] | 2854 | 1574 | 2023 | 2762 | 1050000
[15 empty] | 3956 | 1574 | 2024 | 2762 | 750000
[15 empty] | 3957 | 1574 | 2025 | 2762 | 750000
[15 empty] | 1856 | 1575 | 2014 | 2742 | 825000
[15 empty] | 1878 | 1576 | 2013 | 2742 | 50000
[15 empty] | 2077 | 1576 | 2015 | 2742 | 100000
[15 empty] | 2665 | 1576 | 2024 | 2742 | 192000
[15 empty] | 3364 | 1576 | 2025 | 2742 | 258000
[15 empty] | 1866 | 1577 | 2013 | 2743 | 2500000
[15 empty] | 1860 | 1578 | 2012 | 2771 | 7500
[15 empty] | 2341 | 1578 | 2025 | 2260 | 70000
[15 empty] | 1861 | 1578 | 2025 | 2771 | 70000
[15 empty] | 1862 | 1579 | 2013 | 2771 | 350000
[15 empty] | 1863 | 1580 | 2019 | 2771 | 34000
[15 empty] | 3864 | 1580 | 2020 | 2734 | 100000
[15 empty] | 2895 | 1580 | 2020 | 2771 | 300000
[15 empty] | 3865 | 1580 | 2020 | 6988 | 200000
[15 empty] | 3866 | 1580 | 2021 | 2734 | 50000
[15 empty] | 3621 | 1580 | 2021 | 2771 | 250000
[15 empty] | 3868 | 1580 | 2021 | 6988 | 200000
[15 empty] | 1895 | 1581 | 2012 | 2762 | 500000
[15 empty] | 1897 | 1581 | 2013 | 2296 | 1120000
[15 empty] | 1896 | 1581 | 2013 | 2762 | 850000
[15 empty] | 1898 | 1581 | 2014 | 2762 | 100000
[15 empty] | 1903 | 1582 | 2012 | 2762 | 10000
[15 empty] | 1904 | 1582 | 2013 | 2762 | 16000
[15 empty] | 1900 | 1582 | 2014 | 2296 | 0
[15 empty] | 1899 | 1582 | 2014 | 2762 | 1000000
[15 empty] | 1901 | 1583 | 2014 | 2762 | 100000
[15 empty] | 1902 | 1584 | 2014 | 2762 | 400000
[15 empty] | 1905 | 1585 | 2012 | 2762 | 100000
[15 empty] | 1906 | 1585 | 2013 | 2762 | 500000
[15 empty] | 1909 | 1586 | 2012 | 2742 | 25000
[15 empty] | 1907 | 1586 | 2012 | 2762 | 75000
[15 empty] | 1912 | 1586 | 2012 | 6988 | 500000
[15 empty] | 1910 | 1586 | 2013 | 2159 | 145000
[15 empty] | 1928 | 1586 | 2013 | 2296 | 320000
[15 empty] | 1927 | 1586 | 2013 | 2299 | 1400000
[15 empty] | 2214 | 1586 | 2013 | 2742 | 415000
[15 empty] | 1908 | 1586 | 2013 | 2762 | 105000
[15 empty] | 1916 | 1587 | 2014 | 2762 | 1850000
[15 empty] | 1917 | 1587 | 2015 | 2762 | 2700000
[15 empty] | 1918 | 1587 | 2016 | 2762 | 3000000
[15 empty] | 1919 | 1587 | 2017 | 2762 | 3000000
[15 empty] | 1920 | 1587 | 2018 | 2762 | 2650000
[15 empty] | 2284 | 1587 | 2019 | 2762 | 2430000
[15 empty] | 3086 | 1587 | 2020 | 2762 | 2670000
[15 empty] | 3087 | 1587 | 2021 | 2762 | 3200000
[15 empty] | 4053 | 1587 | 2021 | 6814 | 1500000
[15 empty] | 3088 | 1587 | 2022 | 2762 | 3450000
[15 empty] | 4054 | 1587 | 2022 | 6814 | 1500000
[15 empty] | 3089 | 1587 | 2023 | 2762 | 3800000
[15 empty] | 4055 | 1587 | 2023 | 6814 | 1500000
[15 empty] | 3813 | 1587 | 2024 | 2762 | 3900000
[15 empty] | 4056 | 1587 | 2024 | 6814 | 1500000
[15 empty] | 3814 | 1587 | 2025 | 2762 | 3900000
[15 empty] | 4057 | 1587 | 2025 | 6814 | 1500000
[15 empty] | 2042 | 1590 | 2014 | 2742 | 100000
[15 empty] | 2041 | 1591 | 2014 | 2742 | 70000
[15 empty] | 2338 | 1591 | 2015 | 2742 | 100000
[15 empty] | 2339 | 1591 | 2016 | 2742 | 100000
[15 empty] | 3535 | 1593 | 2018 | 2742 | 0
[15 empty] | 3536 | 1593 | 2019 | 2742 | 0
[15 empty] | 2191 | 1593 | 2025 | 2742 | 520000
[15 empty] | 2192 | 1593 | 2026 | 2742 | 780000
[15 empty] | 2136 | 1594 | 2026 | 2742 | 292000
[15 empty] | 2137 | 1595 | 2023 | 2742 | 250000
[15 empty] | 3367 | 1596 | 2021 | 2742 | 879000
[15 empty] | 2055 | 1596 | 2022 | 2742 | 711000
[15 empty] | 3820 | 1596 | 2022 | 2762 | 250000
[15 empty] | 2056 | 1597 | 2025 | 2742 | 347000
[15 empty] | 2043 | 1598 | 2013 | 2742 | 15000
[15 empty] | 2044 | 1598 | 2014 | 2742 | 85000
[15 empty] | 2291 | 1599 | 2014 | 2742 | 650000
[15 empty] | 2030 | 1600 | 2015 | 2742 | 300000
[15 empty] | 2479 | 1600 | 2015 | 2762 | 512000
[15 empty] | 2071 | 1601 | 2014 | 2742 | 1000000
[15 empty] | 2271 | 1602 | 2019 | 2742 | 600000
[15 empty] | 2046 | 1603 | 2013 | 2742 | 0
[15 empty] | 2049 | 1603 | 2017 | 2742 | 300000
[15 empty] | 2207 | 1604 | 2019 | 2742 | 0
[15 empty] | 3272 | 1604 | 2020 | 2742 | 0
[15 empty] | 2270 | 1605 | 2019 | 2742 | 0
[15 empty] | 3248 | 1605 | 2022 | 2742 | 1050000
[15 empty] | 3897 | 1605 | 2023 | 2742 | 1050000
[15 empty] | 2303 | 1606 | 2015 | 2742 | 0
[15 empty] | 2292 | 1606 | 2015 | 2743 | 0
[15 empty] | 2304 | 1606 | 2016 | 2742 | 0
[15 empty] | 2293 | 1606 | 2016 | 2743 | 0
[15 empty] | 2305 | 1606 | 2017 | 2742 | 0
[15 empty] | 2294 | 1606 | 2017 | 2743 | 0
[15 empty] | 2306 | 1606 | 2018 | 2742 | 125000
[15 empty] | 2295 | 1606 | 2018 | 2743 | 125000
[15 empty] | 2307 | 1606 | 2019 | 2742 | 1250000
[15 empty] | 2296 | 1606 | 2019 | 2743 | 1250000
[15 empty] | 2725 | 1606 | 2020 | 2742 | 1250000
[15 empty] | 2726 | 1606 | 2020 | 2743 | 1250000
[15 empty] | 2727 | 1606 | 2021 | 2742 | 1250000
[15 empty] | 2728 | 1606 | 2021 | 2743 | 1250000
[15 empty] | 2729 | 1606 | 2022 | 2742 | 1250000
[15 empty] | 2730 | 1606 | 2022 | 2743 | 1250000
[15 empty] | 2067 | 1607 | 2025 | 2260 | 1102000
[15 empty] | 2793 | 1607 | 2025 | 2748 | 58000
[15 empty] | 2065 | 1608 | 2016 | 2772 | 80000
[15 empty] | 2530 | 1608 | 2018 | 2772 | 450000
[15 empty] | 2208 | 1609 | 2018 | 2772 | 250000
[15 empty] | 2029 | 1610 | 2015 | 2743 | 22900
[15 empty] | 2761 | 1610 | 2016 | 2743 | 26600
[15 empty] | 3322 | 1610 | 2017 | 2743 | 44300
[15 empty] | 2891 | 1610 | 2019 | 7119 | 125000
[15 empty] | 4047 | 1610 | 2020 | 7119 | 425000
[15 empty] | 2010 | 1611 | 2014 | 2743 | 98000
[15 empty] | 3456 | 1612 | 2018 | 2743 | 250000
[15 empty] | 2011 | 1612 | 2019 | 2743 | 525000
[15 empty] | 2926 | 1612 | 2024 | 2743 | 300000
[15 empty] | 3674 | 1612 | 2025 | 2743 | 800000
[15 empty] | 3675 | 1612 | 2026 | 2743 | 1800000
[15 empty] | 2286 | 1613 | 2013 | 2743 | 250000
[15 empty] | 2126 | 1613 | 2014 | 2743 | 1100000
[15 empty] | 2127 | 1614 | 2015 | 2743 | 0
[15 empty] | 2128 | 1614 | 2016 | 2743 | 0
[15 empty] | 2129 | 1614 | 2017 | 2743 | 0
[15 empty] | 2130 | 1614 | 2019 | 2743 | 150000
[15 empty] | 2762 | 1614 | 2020 | 2743 | 1050000
[15 empty] | 2927 | 1614 | 2021 | 2743 | 950000
[15 empty] | 2406 | 1614 | 2022 | 2743 | 500000
[15 empty] | 2288 | 1615 | 2014 | 2743 | 750000
[15 empty] | 2110 | 1615 | 2015 | 2743 | 1500000
[15 empty] | 2617 | 1615 | 2016 | 2743 | 1250000
[15 empty] | 2618 | 1615 | 2017 | 2743 | 1250000
[15 empty] | 2111 | 1615 | 2018 | 2743 | 1500000
[15 empty] | 2619 | 1615 | 2019 | 2743 | 1500000
[15 empty] | 2620 | 1615 | 2020 | 2743 | 1500000
[15 empty] | 2621 | 1615 | 2021 | 2743 | 1500000
[15 empty] | 4048 | 1615 | 2022 | 2743 | 1500000
[15 empty] | 4049 | 1615 | 2023 | 2743 | 1500000
[15 empty] | 2074 | 1616 | 2018 | 6814 | 210000
[15 empty] | 2017 | 1617 | 2013 | 2762 | 153125
[15 empty] | 2019 | 1617 | 2014 | 2762 | 380735
[15 empty] | 2206 | 1617 | 2015 | 2296 | 1150000
[15 empty] | 2602 | 1617 | 2015 | 2762 | 2223940
[15 empty] | 2403 | 1617 | 2016 | 2296 | 200000
[15 empty] | 2241 | 1618 | 2013 | 2762 | 247000
[15 empty] | 2204 | 1618 | 2014 | 2762 | 1728000
[15 empty] | 2026 | 1619 | 2013 | 2762 | 750000
[15 empty] | 2027 | 1619 | 2014 | 2762 | 0
[15 empty] | 2152 | 1620 | 2022 | 2762 | 450000
[15 empty] | 3835 | 1620 | 2023 | 2762 | 800000
[15 empty] | 2156 | 1621 | 2013 | 2762 | 605000
[15 empty] | 2453 | 1622 | 2021 | 2730 | 1000000
[15 empty] | 3043 | 1622 | 2021 | 2762 | 310000
[15 empty] | 2159 | 1622 | 2022 | 2762 | 620000
[15 empty] | 2330 | 1623 | 2016 | 2762 | 32200
[15 empty] | 3483 | 1623 | 2017 | 2730 | 93000
[15 empty] | 2025 | 1623 | 2017 | 2762 | 129000
[15 empty] | 2368 | 1623 | 2018 | 2730 | 1613125
[15 empty] | 2322 | 1623 | 2018 | 2762 | 550000
[15 empty] | 3482 | 1623 | 2019 | 2730 | 1764860
[15 empty] | 3481 | 1623 | 2019 | 2762 | 950000
[15 empty] | 2031 | 1624 | 2013 | 2762 | 150000
[15 empty] | 2034 | 1624 | 2014 | 2296 | 960000
[15 empty] | 2032 | 1624 | 2014 | 2762 | 600000
[15 empty] | 2918 | 1625 | 2016 | 2762 | 7600
[15 empty] | 2037 | 1625 | 2017 | 2762 | 110500
[15 empty] | 2919 | 1625 | 2018 | 2296 | 900000
[15 empty] | 2038 | 1625 | 2018 | 2762 | 790000
[15 empty] | 2989 | 1625 | 2018 | 2769 | 0
[15 empty] | 2988 | 1625 | 2018 | 6640 | 66150
[15 empty] | 2158 | 1626 | 2016 | 2762 | 1565000
[15 empty] | 2157 | 1627 | 2015 | 2722 | 560000
[15 empty] | 2035 | 1628 | 2017 | 2762 | 97150
[15 empty] | 3345 | 1628 | 2018 | 2296 | 575000
[15 empty] | 2036 | 1628 | 2018 | 2762 | 239000
[15 empty] | 3495 | 1628 | 2019 | 2762 | 239000
[15 empty] | 2198 | 1629 | 2015 | 2159 | 580000
[15 empty] | 2073 | 1631 | 2016 | 2762 | 0
[15 empty] | 2072 | 1631 | 2024 | 2762 | 0
[15 empty] | 2326 | 1631 | 2026 | 2762 | 800000
[15 empty] | 2045 | 1632 | 2021 | 2710 | 70000
[15 empty] | 2482 | 1632 | 2022 | 2710 | 180000
[15 empty] | 2822 | 1632 | 2023 | 2710 | 1375000
[15 empty] | 2823 | 1632 | 2024 | 2710 | 1375000
[15 empty] | 2162 | 1633 | 2016 | 2742 | 0
[15 empty] | 2161 | 1633 | 2021 | 2742 | 75000
[15 empty] | 2164 | 1635 | 2017 | 2710 | 221000
[15 empty] | 2160 | 1636 | 2015 | 2710 | 0
[15 empty] | 2314 | 1636 | 2016 | 2710 | 133000
[15 empty] | 2283 | 1637 | 2014 | 2703 | 420000
[15 empty] | 2337 | 1637 | 2015 | 2703 | 160000
[15 empty] | 2281 | 1638 | 2015 | 2180 | 100000
[15 empty] | 2282 | 1638 | 2019 | 2180 | 0
[15 empty] | 2109 | 1639 | 2014 | 2769 | 0
[15 empty] | 2336 | 1639 | 2015 | 2769 | 6700
[15 empty] | 2760 | 1639 | 2016 | 2769 | 28400
[15 empty] | 3127 | 1639 | 2017 | 2769 | 184900
[15 empty] | 3128 | 1639 | 2018 | 2769 | 5000
[15 empty] | 3873 | 1639 | 2019 | 2769 | 523600
[15 empty] | 3874 | 1639 | 2020 | 2769 | 90000
[15 empty] | 2177 | 1640 | 2013 | 2159 | 150000
[15 empty] | 2178 | 1640 | 2013 | 2741 | 150000
[15 empty] | 2171 | 1641 | 2016 | 2159 | 0
[15 empty] | 3097 | 1641 | 2023 | 2769 | 0
[15 empty] | 2170 | 1641 | 2024 | 2769 | 2770000
[15 empty] | 2176 | 1642 | 2014 | 2769 | 200000
[15 empty] | 2064 | 1643 | 2016 | 2769 | 30000
[15 empty] | 2189 | 1644 | 2014 | 2769 | 50000
[15 empty] | 2061 | 1645 | 2016 | 2769 | 0
[15 empty] | 2062 | 1645 | 2018 | 2769 | 300000
[15 empty] | 2063 | 1645 | 2019 | 2769 | 300000
[15 empty] | 2693 | 1645 | 2020 | 2769 | 300000
[15 empty] | 3092 | 1645 | 2021 | 2769 | 300000
[15 empty] | 3144 | 1645 | 2022 | 2769 | 300000
[15 empty] | 3145 | 1645 | 2023 | 2769 | 300000
[15 empty] | 3146 | 1645 | 2024 | 2769 | 300000
[15 empty] | 3147 | 1645 | 2025 | 2769 | 300000
[15 empty] | 3148 | 1645 | 2026 | 2769 | 300000
[15 empty] | 2174 | 1649 | 2016 | 2159 | 400000
[15 empty] | 2175 | 1649 | 2016 | 2769 | 900000
[15 empty] | 2182 | 1651 | 2017 | 2769 | 0
[15 empty] | 2183 | 1651 | 2018 | 2769 | 0
[15 empty] | 3883 | 1651 | 2019 | 2769 | 245550
[15 empty] | 2297 | 1652 | 2013 | 2769 | 200000
[15 empty] | 2012 | 1653 | 2014 | 2703 | 30000
[15 empty] | 2080 | 1655 | 2013 | 2161 | 1462000
[15 empty] | 2079 | 1655 | 2013 | 2710 | 593300
[15 empty] | 3015 | 1655 | 2017 | 2710 | 151600
[15 empty] | 3597 | 1655 | 2018 | 2710 | 69200
[15 empty] | 3598 | 1655 | 2019 | 2710 | 110000
[15 empty] | 2116 | 1656 | 2014 | 2761 | 28000
[15 empty] | 2112 | 1656 | 2015 | 2299 | 172000
[15 empty] | 2462 | 1656 | 2015 | 2761 | 21000
[15 empty] | 2016 | 1657 | 2013 | 2710 | 15000
[15 empty] | 2387 | 1657 | 2014 | 2710 | 50000
[15 empty] | 2492 | 1657 | 2015 | 1625 | 4000
[15 empty] | 2497 | 1657 | 2015 | 2296 | 200000
[15 empty] | 2491 | 1657 | 2015 | 2710 | 177000
[15 empty] | 2493 | 1657 | 2016 | 2710 | 30000
[15 empty] | 2050 | 1658 | 2020 | 2296 | 42500
[15 empty] | 2099 | 1658 | 2020 | 2762 | 42500
[15 empty] | 3945 | 1658 | 2021 | 2296 | 42500
[15 empty] | 2584 | 1658 | 2021 | 2762 | 42500
[15 empty] | 1999 | 1661 | 2012 | 6988 | 125000
[15 empty] | 1993 | 1661 | 2013 | 1111 | 10000
[15 empty] | 1978 | 1661 | 2014 | 1518 | 15000
[15 empty] | 1998 | 1661 | 2014 | 2710 | 500000
[15 empty] | 1979 | 1661 | 2015 | 1512 | 15000
[15 empty] | 2000 | 1661 | 2015 | 6988 | 125000
[15 empty] | 1992 | 1661 | 2016 | 2710 | 40000
[15 empty] | 2257 | 1662 | 2025 | 2151 | 300000
[15 empty] | 2258 | 1663 | 2022 | 2771 | 200000
[15 empty] | 2256 | 1664 | 2016 | 2771 | 250000
[15 empty] | 2006 | 1667 | 2013 | 1125 | 1658000
[15 empty] | 2007 | 1667 | 2014 | 1125 | 0
[15 empty] | 2001 | 1669 | 2014 | 2710 | 50000
[15 empty] | 2003 | 1669 | 2015 | 6988 | 250000
[15 empty] | 2004 | 1670 | 2015 | 2710 | 200000
[15 empty] | 2005 | 1670 | 2016 | 1111 | 300000
[15 empty] | 2165 | 1677 | 2015 | 2710 | 100000
[15 empty] | 2332 | 1677 | 2017 | 2710 | 100000
[15 empty] | 2168 | 1678 | 2016 | 2159 | 150000
[15 empty] | 2169 | 1678 | 2016 | 2741 | 150000
[15 empty] | 2084 | 1681 | 2014 | 2180 | 500000
[15 empty] | 2094 | 1681 | 2014 | 2336 | 0
[15 empty] | 2086 | 1681 | 2014 | 2761 | 125000
[15 empty] | 2085 | 1681 | 2015 | 2180 | 100000
[15 empty] | 2087 | 1681 | 2015 | 2761 | 25000
[15 empty] | 3566 | 1682 | 2020 | 2710 | 0
[15 empty] | 2081 | 1682 | 2021 | 2161 | 3528000
[15 empty] | 2312 | 1682 | 2021 | 2710 | 882000
[15 empty] | 3599 | 1682 | 2022 | 2161 | 4116000
[15 empty] | 3600 | 1682 | 2022 | 2710 | 1029000
[15 empty] | 3601 | 1682 | 2023 | 2161 | 4116000
[15 empty] | 3756 | 1682 | 2023 | 2710 | 1029000
[15 empty] | 2082 | 1683 | 2024 | 2161 | 13666880
[15 empty] | 2083 | 1683 | 2024 | 2710 | 3416720
[15 empty] | 3757 | 1683 | 2025 | 2161 | 27333760
[15 empty] | 3758 | 1683 | 2025 | 2710 | 6833440
[15 empty] | 3759 | 1683 | 2026 | 2161 | 27333760
[15 empty] | 3760 | 1683 | 2026 | 2710 | 7483440
[15 empty] | 2205 | 1684 | 2015 | 2159 | 350000
[15 empty] | 2193 | 1685 | 2015 | 2721 | 200000
[15 empty] | 2199 | 1686 | 2018 | 2762 | 2100000
[15 empty] | 2242 | 1687 | 2018 | 2762 | 4000000
[15 empty] | 2200 | 1688 | 2022 | 2762 | 450000
[15 empty] | 3831 | 1688 | 2023 | 2762 | 850000
[15 empty] | 2253 | 1690 | 2017 | 2260 | 0
[15 empty] | 2503 | 1690 | 2022 | 2771 | 175000
[15 empty] | 2184 | 1694 | 2015 | 2159 | 400000
[15 empty] | 2185 | 1694 | 2015 | 2769 | 400000
[15 empty] | 2181 | 1695 | 2016 | 2159 | 0
[15 empty] | 2180 | 1695 | 2022 | 2769 | 320000
[15 empty] | 3095 | 1695 | 2023 | 2769 | 330000
[15 empty] | 2187 | 1696 | 2017 | 2159 | 300000
[15 empty] | 2188 | 1696 | 2017 | 2769 | 300000
[15 empty] | 2167 | 1697 | 2022 | 2769 | 1200000
[15 empty] | 2143 | 1697 | 2023 | 2769 | 0
[15 empty] | 2190 | 1703 | 2013 | 2159 | 200000
[15 empty] | 2150 | 1703 | 2013 | 2769 | 200000
[15 empty] | 2225 | 1704 | 2015 | 2742 | 446900
[15 empty] | 2226 | 1704 | 2016 | 2742 | 178900
[15 empty] | 2228 | 1704 | 2017 | 2742 | 397200
[15 empty] | 2220 | 1705 | 2014 | 2762 | 247000
[15 empty] | 2221 | 1705 | 2015 | 2762 | 617000
[15 empty] | 2222 | 1705 | 2016 | 2762 | 815000
[15 empty] | 2223 | 1705 | 2017 | 2762 | 790000
[15 empty] | 2243 | 1706 | 2007 | 2718 | 50000
[15 empty] | 3870 | 1706 | 2019 | 2771 | 12500
[15 empty] | 2244 | 1706 | 2021 | 2771 | 250000
[15 empty] | 3006 | 1706 | 2021 | 6814 | 280000
[15 empty] | 3944 | 1706 | 2022 | 2296 | 1000000
[15 empty] | 3010 | 1706 | 2022 | 2710 | 1000000
[15 empty] | 2245 | 1706 | 2022 | 6814 | 1970000
[15 empty] | 2267 | 1708 | 2015 | 2742 | 0
[15 empty] | 2268 | 1708 | 2018 | 2742 | 290300
[15 empty] | 3223 | 1708 | 2019 | 2742 | 1109700
[15 empty] | 2302 | 1709 | 2024 | 2260 | 400000
[15 empty] | 2316 | 1711 | 2014 | 2762 | 350000
[15 empty] | 2317 | 1711 | 2015 | 2762 | 350000
[15 empty] | 2318 | 1711 | 2016 | 2762 | 350000
[15 empty] | 2319 | 1711 | 2017 | 2762 | 350000
[15 empty] | 2320 | 1711 | 2018 | 2762 | 350000
[15 empty] | 2321 | 1711 | 2019 | 2762 | 350000
[15 empty] | 2323 | 1712 | 2014 | 2769 | 150000
[15 empty] | 2324 | 1713 | 2013 | 2769 | 300000
[15 empty] | 2342 | 1715 | 2014 | 27XX | 300000
[15 empty] | 2343 | 1716 | 2014 | 27XX | 300000
[15 empty] | 2344 | 1717 | 2014 | 27XX | 300000
[15 empty] | 2345 | 1718 | 2014 | 27XX | 300000
[15 empty] | 2346 | 1719 | 2014 | 27XX | 240000
[15 empty] | 2348 | 1720 | 2015 | 27XX | 4000000
[15 empty] | 2347 | 1721 | 2015 | 27XX | 12000000
[15 empty] | 2349 | 1722 | 2015 | 27XX | 5000000
[15 empty] | 2350 | 1723 | 2015 | 27XX | 1367000
[15 empty] | 2351 | 1724 | 2016 | 27XX | 10260000
[15 empty] | 2352 | 1725 | 2015 | 27XX | 4000000
[15 empty] | 2355 | 1726 | 2016 | 27XX | 2000000
[15 empty] | 2354 | 1727 | 2016 | 27XX | 4000000
[15 empty] | 2353 | 1728 | 2017 | 27XX | 8250000
[15 empty] | 2357 | 1729 | 2014 | 2703 | 150000
[15 empty] | 2358 | 1730 | 2016 | 2703 | 175000
[15 empty] | 2359 | 1730 | 2017 | 2730 | 1177800
[15 empty] | 3504 | 1730 | 2018 | 2730 | 610100
[15 empty] | 2360 | 1732 | 2016 | 2763 | 2605990
[15 empty] | 2723 | 1732 | 2017 | 2763 | 1766440
[15 empty] | 2612 | 1733 | 2021 | 2703 | 250000
[15 empty] | 2361 | 1734 | 2014 | 2703 | 50000
[15 empty] | 2362 | 1734 | 2015 | 2703 | 50000
[15 empty] | 2706 | 1734 | 2019 | 2703 | 16200
[15 empty] | 3981 | 1734 | 2020 | 2703 | 15000
[15 empty] | 3982 | 1734 | 2021 | 2703 | 15000
[15 empty] | 2881 | 1735 | 2016 | 2703 | 30000
[15 empty] | 2363 | 1735 | 2018 | 2703 | 0
[15 empty] | 2371 | 1738 | 2024 | 2730 | 500000
[15 empty] | 2372 | 1739 | 2014 | 1119 | 0
[15 empty] | 2373 | 1739 | 2015 | 1119 | 30000
[15 empty] | 2374 | 1739 | 2016 | 2703 | 30000
[15 empty] | 2375 | 1739 | 2017 | 2703 | 30000
[15 empty] | 2376 | 1739 | 2018 | 2703 | 30000
[15 empty] | 2377 | 1739 | 2019 | 2703 | 30000
[15 empty] | 2541 | 1739 | 2020 | 2703 | 30000
[15 empty] | 2542 | 1739 | 2021 | 2703 | 30000
[15 empty] | 2370 | 1741 | 2015 | 27XX | 5000000
[15 empty] | 2369 | 1742 | 2015 | 27XX | 4000000
[15 empty] | 2378 | 1743 | 2018 | 2703 | 1934000
[15 empty] | 2367 | 1744 | 2015 | 2762 | 100000
[15 empty] | 2386 | 1745 | 2015 | 2296 | 10000
[15 empty] | 2399 | 1745 | 2016 | 2159 | 100000
[15 empty] | 2398 | 1745 | 2017 | 2170 | 50000
[15 empty] | 2400 | 1745 | 2017 | 9999 | 1000000
[15 empty] | 2389 | 1747 | 2015 | 2762 | 1200000
[15 empty] | 2390 | 1747 | 2016 | 2762 | 500000
[15 empty] | 3357 | 1747 | 2017 | 2296 | 290000
[15 empty] | 2391 | 1747 | 2017 | 2762 | 165000
[15 empty] | 3084 | 1747 | 2018 | 2296 | 0
[15 empty] | 2392 | 1747 | 2018 | 2762 | 400000
[15 empty] | 3085 | 1747 | 2019 | 2721 | 2520000
[15 empty] | 3903 | 1747 | 2019 | 2722 | 1853500
[15 empty] | 2393 | 1747 | 2019 | 2762 | 675000
[15 empty] | 3904 | 1747 | 2020 | 2721 | 650000
[15 empty] | 3343 | 1747 | 2020 | 2722 | 1263500
[15 empty] | 2394 | 1747 | 2020 | 2762 | 1490000
[15 empty] | 3905 | 1747 | 2021 | 2721 | 650000
[15 empty] | 3910 | 1747 | 2021 | 2722 | 300000
[15 empty] | 3081 | 1747 | 2021 | 2762 | 1000000
[15 empty] | 3915 | 1747 | 2022 | 2296 | 400000
[15 empty] | 3906 | 1747 | 2022 | 2721 | 650000
[15 empty] | 3911 | 1747 | 2022 | 2722 | 300000
[15 empty] | 3082 | 1747 | 2022 | 2762 | 1000000
[15 empty] | 3916 | 1747 | 2023 | 2296 | 645000
[15 empty] | 3907 | 1747 | 2023 | 2721 | 650000
[15 empty] | 3912 | 1747 | 2023 | 2722 | 300000
[15 empty] | 3083 | 1747 | 2023 | 2762 | 1000000
[15 empty] | 3908 | 1747 | 2024 | 2721 | 650000
[15 empty] | 3913 | 1747 | 2024 | 2722 | 300000
[15 empty] | 3815 | 1747 | 2024 | 2762 | 1000000
[15 empty] | 3909 | 1747 | 2025 | 2721 | 650000
[15 empty] | 3914 | 1747 | 2025 | 2722 | 300000
[15 empty] | 3816 | 1747 | 2025 | 2762 | 1000000
[15 empty] | 2395 | 1748 | 2014 | 2742 | 250000
[15 empty] | 3493 | 1750 | 2020 | 2762 | 45000
[15 empty] | 2488 | 1750 | 2021 | 1625 | 0
[15 empty] | 2487 | 1750 | 2021 | 2762 | 468000
[15 empty] | 2483 | 1751 | 2016 | 2710 | 230000
[15 empty] | 2484 | 1751 | 2017 | 2710 | 100000
[15 empty] | 2485 | 1751 | 2019 | 2710 | 100000
[15 empty] | 2486 | 1751 | 2020 | 2710 | 100000
[15 empty] | 2560 | 1752 | 2016 | 2296 | 62550
[15 empty] | 2561 | 1752 | 2016 | 2762 | 65000
[15 empty] | 2702 | 1753 | 2016 | 2710 | 423000
[15 empty] | 2601 | 1753 | 2016 | 2772 | 824500
[15 empty] | 2703 | 1753 | 2016 | 6907 | 500000
[15 empty] | 3502 | 1754 | 2017 | 2762 | 30000
[15 empty] | 3501 | 1754 | 2018 | 2762 | 40000
[15 empty] | 2495 | 1754 | 2019 | 1625 | 0
[15 empty] | 3009 | 1754 | 2019 | 2296 | 100000
[15 empty] | 2496 | 1754 | 2019 | 2762 | 32500
[15 empty] | 3415 | 1755 | 2018 | 2296 | 457500
[15 empty] | 2565 | 1755 | 2018 | 2721 | 82500
[15 empty] | 3475 | 1755 | 2018 | 2762 | 100000
[15 empty] | 2660 | 1758 | 2024 | 2742 | 350000
[15 empty] | 3992 | 1758 | 2025 | 2742 | 450000
[15 empty] | 2685 | 1759 | 2017 | 2769 | 0
[15 empty] | 2993 | 1759 | 2018 | 2769 | 192100
[15 empty] | 2999 | 1759 | 2019 | 2769 | 598500
[15 empty] | 2641 | 1760 | 2019 | 2743 | 50000
[15 empty] | 3455 | 1760 | 2020 | 2743
[15 empty] | 2499 | 1761 | 2015 | 2743 | 900000
[15 empty] | 2610 | 1762 | 2021 | 2703 | 300000
[15 empty] | 3045 | 1763 | 2018 | 6814 | 455000
[15 empty] | 2553 | 1764 | 2017 | 2762 | 975000
[15 empty] | 2554 | 1765 | 2017 | 2762 | 230000
[15 empty] | 2548 | 1766 | 2016 | 2762 | 121000
[15 empty] | 3479 | 1767 | 2018 | 2762 | 60000
[15 empty] | 2552 | 1767 | 2019 | 2762 | 445000
[15 empty] | 3750 | 1767 | 2020 | 2762 | 445000
[15 empty] | 2546 | 1768 | 2023 | 2762 | 242000
[15 empty] | 2558 | 1769 | 2020 | 6814 | 275000
[15 empty] | 3811 | 1769 | 2021 | 6814 | 490000
[15 empty] | 3514 | 1770 | 2019 | 2762 | 0
[15 empty] | 2563 | 1770 | 2021 | 2762 | 750000
[15 empty] | 3812 | 1770 | 2022 | 2762 | 810000
[15 empty] | 3022 | 1771 | 2022 | 2762 | 200000
[15 empty] | 3842 | 1771 | 2023 | 2762 | 275000
[15 empty] | 2611 | 1772 | 2015 | 2159 | 200000
[15 empty] | 3024 | 1773 | 2019 | 2721 | 185000
[15 empty] | 2564 | 1774 | 2023 | 2762 | 250000
[15 empty] | 3832 | 1774 | 2024 | 2762 | 320000
[15 empty] | 2556 | 1775 | 2019 | 6814 | 810000
[15 empty] | 2545 | 1776 | 2023 | 2762 | 200000
[15 empty] | 3747 | 1776 | 2024 | 2762 | 200000
[15 empty] | 2420 | 1778 | 2018 | 2771 | 100000
[15 empty] | 2421 | 1778 | 2019 | 2771 | 100000
[15 empty] | 2422 | 1779 | 2016 | 2771 | 150000
[15 empty] | 2424 | 1779 | 2017 | 2260 | 300000
[15 empty] | 2423 | 1779 | 2017 | 2734 | 550000
[15 empty] | 2425 | 1780 | 2017 | 2771 | 75000
[15 empty] | 3104 | 1781 | 2017 | 2160 | 360855
[15 empty] | 3105 | 1781 | 2017 | 2761 | 78800
[15 empty] | 2470 | 1781 | 2017 | 2769 | 147200
[15 empty] | 2471 | 1781 | 2018 | 2160 | 80645
[15 empty] | 2472 | 1781 | 2018 | 2296 | 0
[15 empty] | 2473 | 1781 | 2018 | 2761 | 96000
[15 empty] | 3106 | 1781 | 2018 | 2769 | 0
[15 empty] | 3108 | 1781 | 2019 | 2160 | 1635350
[15 empty] | 3525 | 1781 | 2019 | 2260 | 300000
[15 empty] | 3110 | 1781 | 2019 | 2296 | 1286250
[15 empty] | 3526 | 1781 | 2019 | 2710 | 0
[15 empty] | 3521 | 1781 | 2019 | 2761 | 405000
[15 empty] | 3109 | 1781 | 2019 | 2769 | 698650
[15 empty] | 3792 | 1781 | 2020 | 2160 | 1635350
[15 empty] | 3965 | 1781 | 2020 | 2761 | 73170
[15 empty] | 3793 | 1781 | 2020 | 2769 | 564500
[15 empty] | 3964 | 1781 | 2022 | 2296 | 0
[15 empty] | 2475 | 1782 | 2019 | 2769 | 0
[15 empty] | 2474 | 1782 | 2020 | 2769 | 1500000
[15 empty] | 2477 | 1783 | 2024 | 2769 | 650000
[15 empty] | 2478 | 1783 | 2025 | 2769 | 0
[15 empty] | 2688 | 1784 | 2021 | 2769 | 1220000
[15 empty] | 3130 | 1784 | 2022 | 2769 | 0
[15 empty] | 2694 | 1785 | 2016 | 2769 | 7000
[15 empty] | 2695 | 1785 | 2017 | 2769 | 144900
[15 empty] | 2717 | 1785 | 2018 | 2769 | 208000
[15 empty] | 3884 | 1785 | 2019 | 2769 | 244100
[15 empty] | 2683 | 1786 | 2015 | 2769 | 73300
[15 empty] | 2684 | 1786 | 2016 | 2769 | 420000
[15 empty] | 2776 | 1786 | 2017 | 2769 | 206700
[15 empty] | 3690 | 1787 | 2018 | 2769 | 0
[15 empty] | 2707 | 1787 | 2019 | 2769 | 350000
[15 empty] | 3691 | 1787 | 2020 | 2769 | 2850000
[15 empty] | 2689 | 1788 | 2024 | 2769 | 5155000
[15 empty] | 3143 | 1788 | 2025 | 2769 | 0
[15 empty] | 2690 | 1789 | 2025 | 2769 | 1170000
[15 empty] | 3131 | 1789 | 2026 | 2769 | 0
[15 empty] | 2691 | 1790 | 2017 | 2769 | 30000
[15 empty] | 2692 | 1790 | 2018 | 2769 | 220000
[15 empty] | 2696 | 1791 | 2019 | 2769 | 1000000
[15 empty] | 2697 | 1791 | 2020 | 2769 | 750000
[15 empty] | 2630 | 1792 | 2016 | 2743 | 100000
[15 empty] | 2780 | 1792 | 2017 | 2743 | 3000
[15 empty] | 2616 | 1793 | 2016 | 2743 | 100000
[15 empty] | 2781 | 1793 | 2017 | 2743 | 10500
[15 empty] | 2615 | 1794 | 2016 | 2743 | 95000
[15 empty] | 2711 | 1795 | 2016 | 2743 | 100000
[15 empty] | 2782 | 1795 | 2017 | 2743 | 109000
[15 empty] | 2624 | 1796 | 2016 | 2743 | 20000
[15 empty] | 2783 | 1796 | 2017 | 2743 | 80000
[15 empty] | 2667 | 1798 | 2024 | 2742 | 755000
[15 empty] | 3388 | 1798 | 2025 | 2742 | 945000
[15 empty] | 2489 | 1799 | 2016 | 2742 | 0
[15 empty] | 2490 | 1799 | 2025 | 2742 | 500000
[15 empty] | 3275 | 1799 | 2026 | 2742 | 750000
[15 empty] | 2649 | 1800 | 2019 | 2742 | 350000
[15 empty] | 3274 | 1800 | 2020 | 2742 | 500000
[15 empty] | 3542 | 1800 | 2020 | 2762 | 475000
[15 empty] | 3005 | 1801 | 2017 | 2742 | 28000
[15 empty] | 2651 | 1801 | 2018 | 2742 | 218300
[15 empty] | 3892 | 1801 | 2019 | 2742 | 767700
[15 empty] | 2461 | 1802 | 2014 | 2742 | 200000
[15 empty] | 2661 | 1803 | 2024 | 2742 | 440000
[15 empty] | 3374 | 1803 | 2025 | 2742 | 660000
[15 empty] | 3821 | 1803 | 2025 | 2762 | 205000
[15 empty] | 3818 | 1804 | 2018 | 2742 | 65000
[15 empty] | 3817 | 1804 | 2018 | 2762 | 0
[15 empty] | 2664 | 1804 | 2019 | 2742 | 1827500
[15 empty] | 3629 | 1804 | 2019 | 2762 | 330000
[15 empty] | 2663 | 1804 | 2020 | 2742 | 1827500
[15 empty] | 3630 | 1804 | 2020 | 2762 | 330000
[15 empty] | 3550 | 1805 | 2021 | 2762 | 0
[15 empty] | 3235 | 1805 | 2023 | 2742 | 442000
[15 empty] | 2658 | 1805 | 2024 | 2742 | 558000
[15 empty] | 2659 | 1806 | 2023 | 2742 | 500000
[15 empty] | 2655 | 1807 | 2025 | 2742 | 265000
[15 empty] | 3993 | 1807 | 2026 | 2742 | 335000
[15 empty] | 2662 | 1808 | 2024 | 2742 | 880000
[15 empty] | 3249 | 1808 | 2025 | 2742 | 1120000
[15 empty] | 3546 | 1809 | 2022 | 2762 | 0
[15 empty] | 2670 | 1809 | 2025 | 2742 | 660000
[15 empty] | 3252 | 1809 | 2026 | 2742 | 840000
[15 empty] | 2671 | 1810 | 2025 | 2742 | 300000
[15 empty] | 2669 | 1811 | 2025 | 2742 | 300000
[15 empty] | 2832 | 1812 | 2018 | 2742 | 0
[15 empty] | 2648 | 1812 | 2019 | 2742 | 25000
[15 empty] | 2439 | 1812 | 2020 | 2742 | 100000
[15 empty] | 2442 | 1812 | 2021 | 2742 | 750000
[15 empty] | 2444 | 1812 | 2022 | 2742 | 1500000
[15 empty] | 2445 | 1812 | 2023 | 2742 | 3500000
[15 empty] | 2647 | 1812 | 2024 | 2742 | 2200000
[15 empty] | 2946 | 1812 | 2025 | 2742 | 75000000
[15 empty] | 2446 | 1813 | 2017 | 2742 | 0
[15 empty] | 2449 | 1813 | 2018 | 2742 | 50000
[15 empty] | 2928 | 1813 | 2019 | 2742 | 150000
[15 empty] | 3534 | 1813 | 2020 | 2742 | 1800000
[15 empty] | 2450 | 1814 | 2017 | 2742
[15 empty] | 2929 | 1814 | 2018 | 2742 | 250000
[15 empty] | 2451 | 1814 | 2019 | 2742 | 300000
[15 empty] | 2920 | 1814 | 2020 | 2742 | 1700000
[15 empty] | 3533 | 1814 | 2021 | 2742 | 300000
[15 empty] | 2454 | 1815 | 2017 | 2742 | 50000
[15 empty] | 2455 | 1815 | 2018 | 2742 | 50000
[15 empty] | 3532 | 1815 | 2019 | 2742 | 350000
[15 empty] | 2930 | 1815 | 2020 | 2742 | 350000
[15 empty] | 2976 | 1815 | 2022 | 2742 | 150000
[15 empty] | 3620 | 1815 | 2023 | 2742 | 1000000
[15 empty] | 2668 | 1816 | 2021 | 2742 | 200000
[15 empty] | 2673 | 1817 | 2026 | 2742 | 1760000
[15 empty] | 2674 | 1817 | 2027 | 2742 | 2240000
[15 empty] | 3548 | 1818 | 2024 | 2762 | 0
[15 empty] | 2666 | 1818 | 2025 | 2742 | 818000
[15 empty] | 3377 | 1818 | 2026 | 2742 | 1032000
[15 empty] | 2657 | 1819 | 2024 | 2742 | 1188000
[15 empty] | 3266 | 1819 | 2025 | 2742 | 1512000
[15 empty] | 2710 | 1821 | 2026 | 2710 | 220000
[15 empty] | 2452 | 1822 | 2016 | 2742 | 250000
[15 empty] | 2642 | 1823 | 2020 | 2743 | 180000
[15 empty] | 2947 | 1823 | 2021 | 2743 | 270000
[15 empty] | 2637 | 1824 | 2016 | 2743 | 200000
[15 empty] | 2786 | 1825 | 2020 | 2260 | 164350
[15 empty] | 2705 | 1825 | 2020 | 2748 | 8650
[15 empty] | 2467 | 1827 | 2020 | 2160
[15 empty] | 2465 | 1827 | 2020 | 2721
[15 empty] | 2463 | 1827 | 2020 | 2722
[15 empty] | 2468 | 1827 | 2020 | 2769
[15 empty] | 2466 | 1827 | 2020 | 2772
[15 empty] | 2469 | 1827 | 2022 | 2712 | 400000
[15 empty] | 2979 | 1828 | 2017 | 2710 | 10000
[15 empty] | 2980 | 1828 | 2017 | 2742 | 10000
[15 empty] | 2458 | 1828 | 2018 | 2710 | 60000
[15 empty] | 2457 | 1828 | 2018 | 2742 | 60000
[15 empty] | 2460 | 1828 | 2019 | 2710 | 20000
[15 empty] | 2459 | 1828 | 2019 | 2742 | 20000
[15 empty] | 2922 | 1828 | 2020 | 2710 | 125000
[15 empty] | 2923 | 1828 | 2020 | 2742 | 125000
[15 empty] | 2977 | 1828 | 2022 | 2710 | 800000
[15 empty] | 2978 | 1828 | 2022 | 2742 | 800000
[15 empty] | 2635 | 1829 | 2016 | 2743 | 528000
[15 empty] | 2629 | 1830 | 2016 | 2743 | 9300
[15 empty] | 2715 | 1830 | 2017 | 2743 | 455200
[15 empty] | 2716 | 1830 | 2018 | 2743 | 400000
[15 empty] | 2622 | 1831 | 2016 | 2743 | 66000
[15 empty] | 2623 | 1831 | 2017 | 2743 | 18000
[15 empty] | 2948 | 1831 | 2018 | 7119 | 21000
[15 empty] | 3457 | 1831 | 2019 | 7119 | 1429000
[15 empty] | 2639 | 1832 | 2019 | 7119 | 600000
[15 empty] | 2640 | 1832 | 2020 | 7119 | 1250000
[15 empty] | 2638 | 1832 | 2021 | 7119 | 1250000
[15 empty] | 3665 | 1832 | 2022 | 7119 | 650000
[15 empty] | 2504 | 1833 | 2016 | 2770 | 13500000
[15 empty] | 2505 | 1834 | 2019 | 2770 | 8000000
[15 empty] | 3594 | 1834 | 2020 | 2770 | 1000000
[15 empty] | 2544 | 1835 | 2017 | 2742 | 40000
[15 empty] | 2917 | 1835 | 2018 | 2742 | 38000
[15 empty] | 3537 | 1835 | 2026 | 2742 | 450000
[15 empty] | 2654 | 1836 | 2025 | 2742 | 300000
[15 empty] | 2650 | 1837 | 2023 | 2742 | 88000
[15 empty] | 3267 | 1837 | 2024 | 2742 | 112000
[15 empty] | 2656 | 1838 | 2025 | 2742 | 100000
[15 empty] | 3545 | 1838 | 2025 | 2762 | 0
[15 empty] | 2652 | 1839 | 2024 | 2742 | 572000
[15 empty] | 3268 | 1839 | 2025 | 2742 | 728000
[15 empty] | 2653 | 1840 | 2019 | 2742 | 400000
[15 empty] | 3269 | 1840 | 2020 | 2742 | 600000
[15 empty] | 2606 | 1841 | 2021 | 2742 | 1050000
[15 empty] | 2987 | 1841 | 2022 | 2742 | 1050000
[15 empty] | 2605 | 1842 | 2022 | 2742 | 442000
[15 empty] | 3222 | 1842 | 2023 | 2742 | 558000
[15 empty] | 2607 | 1843 | 2023 | 2742 | 221000
[15 empty] | 3224 | 1843 | 2024 | 2742 | 279000
[15 empty] | 2572 | 1844 | 2020 | 2742 | 625000
[15 empty] | 3232 | 1844 | 2021 | 2742 | 625000
[15 empty] | 2636 | 1845 | 2018 | 2743 | 250000
[15 empty] | 2628 | 1846 | 2020 | 2743 | 300000
[15 empty] | 3676 | 1846 | 2021 | 2743 | 100000
[15 empty] | 2527 | 1847 | 2016 | 2763 | 289305
[15 empty] | 3425 | 1848 | 2016 | 2763 | 47957
[15 empty] | 2536 | 1848 | 2017 | 2763 | 547594
[15 empty] | 2718 | 1848 | 2018 | 2763 | 3520
[15 empty] | 2862 | 1848 | 2022 | 2763 | 436800
[15 empty] | 3569 | 1848 | 2024 | 2763 | 648764
[15 empty] | 3570 | 1848 | 2025 | 2763 | 590843
[15 empty] | 2748 | 1849 | 2016 | 2763 | 22350
[15 empty] | 2539 | 1849 | 2017 | 2763 | 1400
[15 empty] | 2749 | 1849 | 2018 | 2763 | 515400
[15 empty] | 2865 | 1849 | 2019 | 2763 | 276555
[15 empty] | 3428 | 1849 | 2020 | 2763 | 486328
[15 empty] | 3572 | 1849 | 2021 | 2763 | 579444
[15 empty] | 3573 | 1849 | 2023 | 2763 | 695060
[15 empty] | 3574 | 1849 | 2024 | 2763 | 821988
[15 empty] | 2722 | 1850 | 2016 | 2763 | 0
[15 empty] | 2524 | 1850 | 2017 | 2763 | 0
[15 empty] | 2741 | 1850 | 2018 | 2763 | 0
[15 empty] | 2742 | 1850 | 2019 | 2763 | 0
[15 empty] | 2746 | 1850 | 2021 | 2763 | 0
[15 empty] | 2747 | 1850 | 2022 | 2763 | 0
[15 empty] | 2535 | 1851 | 2018 | 2763 | 563625
[15 empty] | 2537 | 1852 | 2019 | 2763 | 527200
[15 empty] | 2901 | 1853 | 2017 | 2763 | 0
[15 empty] | 2864 | 1853 | 2020 | 2763 | 243270
[15 empty] | 2538 | 1853 | 2023 | 2763 | 409400
[15 empty] | 3577 | 1853 | 2024 | 2763 | 1628400
[15 empty] | 2523 | 1854 | 2016 | 2763 | 247534
[15 empty] | 2721 | 1854 | 2017 | 2763 | 0
[15 empty] | 3422 | 1854 | 2018 | 2763 | 42750
[15 empty] | 2743 | 1854 | 2019 | 2763 | 341136
[15 empty] | 2744 | 1854 | 2021 | 2763 | 1408934
[15 empty] | 3568 | 1854 | 2025 | 2763 | 716199
[15 empty] | 2724 | 1855 | 2016 | 2763 | 306401
[15 empty] | 3426 | 1855 | 2018 | 2336 | 0
[15 empty] | 3427 | 1855 | 2018 | 2763 | 0
[15 empty] | 2924 | 1855 | 2019 | 2336 | 0
[15 empty] | 2534 | 1855 | 2019 | 2763 | 0
[15 empty] | 2925 | 1855 | 2021 | 2336 | 0
[15 empty] | 2774 | 1855 | 2021 | 2763 | 657815
[15 empty] | 3576 | 1855 | 2025 | 2763 | 2089791
[15 empty] | 3423 | 1856 | 2018 | 2763 | 0
[15 empty] | 2859 | 1856 | 2019 | 2763 | 0
[15 empty] | 2860 | 1856 | 2020 | 2763 | 0
[15 empty] | 2528 | 1856 | 2022 | 2763 | 772800
[15 empty] | 3424 | 1856 | 2023 | 2763 | 933800
[15 empty] | 2856 | 1857 | 2018 | 2763 | 243248
[15 empty] | 2857 | 1857 | 2019 | 2763 | 662702
[15 empty] | 2526 | 1857 | 2021 | 2763 | 0
[15 empty] | 2858 | 1857 | 2022 | 2763 | 648704
[15 empty] | 3575 | 1857 | 2023 | 2763 | 1026260
[15 empty] | 2525 | 1858 | 2021 | 2763 | 910000
[15 empty] | 2643 | 1859 | 2017 | 2743 | 112500
[15 empty] | 2936 | 1860 | 2017 | 2742 | 56250
[15 empty] | 2498 | 1860 | 2018 | 2742 | 56250
[15 empty] | 2543 | 1861 | 2017 | 2769
[15 empty] | 2916 | 1861 | 2026 | 2769 | 450000
[15 empty] | 2675 | 1862 | 2016 | 2769 | 365000
[15 empty] | 2676 | 1862 | 2017 | 2769 | 414000
[15 empty] | 2677 | 1862 | 2018 | 2769 | 414000
[15 empty] | 2678 | 1862 | 2019 | 2769 | 414000
[15 empty] | 2679 | 1862 | 2020 | 2769 | 414000
[15 empty] | 2680 | 1862 | 2021 | 2769 | 414000
[15 empty] | 3468 | 1862 | 2022 | 2769 | 414000
[15 empty] | 3469 | 1862 | 2023 | 2769 | 414000
[15 empty] | 3470 | 1862 | 2024 | 2769 | 414000
[15 empty] | 3801 | 1862 | 2025 | 2769 | 414000
[15 empty] | 2570 | 1864 | 2016 | 2710 | 300000
[15 empty] | 2550 | 1865 | 2019 | 2762 | 0
[15 empty] | 2566 | 1865 | 2020 | 2296 | 0
[15 empty] | 2875 | 1865 | 2026 | 2762 | 100000
[15 empty] | 3489 | 1865 | 2027 | 2762 | 1818000
[15 empty] | 3490 | 1865 | 2028 | 2762 | 0
[15 empty] | 2510 | 1867 | 2016 | 2742 | 23300
[15 empty] | 2973 | 1867 | 2017 | 2742 | 500000
[15 empty] | 2598 | 1868 | 2016 | 2772 | 90000
[15 empty] | 2521 | 1869 | 2016 | 2772 | 73000
[15 empty] | 2522 | 1869 | 2017 | 2772 | 1027000
[15 empty] | 3100 | 1869 | 2018 | 2772 | 400000
[15 empty] | 2712 | 1872 | 2020 | 2769 | 442000
[15 empty] | 3151 | 1872 | 2021 | 2769 | 558000
[15 empty] | 2708 | 1874 | 2019 | 2769 | 0
[15 empty] | 2709 | 1874 | 2024 | 2769 | 135000
[15 empty] | 3168 | 1874 | 2025 | 2769 | 165000
[15 empty] | 2509 | 1875 | 2016 | 2762 | 350000
[15 empty] | 2511 | 1876 | 2016 | 2742 | 600000
[15 empty] | 2754 | 1877 | 2016 | 2762 | 200000
[15 empty] | 2551 | 1877 | 2017 | 2762 | 900000
[15 empty] | 2775 | 1877 | 2017 | 6988 | 1025460
[15 empty] | 2557 | 1878 | 2018 | 2762 | 350000
[15 empty] | 2704 | 1879 | 2022 | 2710 | 50000
[15 empty] | 2573 | 1880 | 2022 | 2769 | 250000
[15 empty] | 2600 | 1881 | 2016 | 2710 | 300000
[15 empty] | 2599 | 1882 | 2020 | 2772 | 250000
[15 empty] | 2609 | 1883 | 2022 | 2742 | 450000
[15 empty] | 3236 | 1883 | 2023 | 2742 | 450000
[15 empty] | 2604 | 1884 | 2022 | 2742 | 0
[15 empty] | 3227 | 1884 | 2023 | 2742 | 0
[15 empty] | 2608 | 1885 | 2019 | 6814 | 550000
[15 empty] | 2644 | 1886 | 2022 | 2710 | 400000
[15 empty] | 2645 | 1886 | 2023 | 2710 | 400000
[15 empty] | 2713 | 1887 | 2016 | 2710 | 200000
[15 empty] | 2714 | 1888 | 2015 | 2769 | 120000
[15 empty] | 3453 | 1889 | 2018 | 2159 | 200000
[15 empty] | 2719 | 1889 | 2019 | 2770 | 7800000
[15 empty] | 3595 | 1889 | 2020 | 2770 | 1000000
[15 empty] | 2777 | 1890 | 2016 | 2710 | 140000
[15 empty] | 2740 | 1892 | 2016 | 2772 | 100000
[15 empty] | 2750 | 1893 | 2016 | 2159 | 2400000
[15 empty] | 2751 | 1894 | 2016 | 2762 | 30000
[15 empty] | 2752 | 1894 | 2017 | 2762 | 150000
[15 empty] | 2753 | 1895 | 2016 | 2762 | 1050900
[15 empty] | 2900 | 1896 | 2021 | 2742 | 495700
[15 empty] | 2759 | 1897 | 2016 | 2742 | 49800
[15 empty] | 2975 | 1897 | 2017 | 2742 | 21200
[15 empty] | 2765 | 1898 | 2017 | 2710 | 48500
[15 empty] | 2766 | 1898 | 2017 | 6999 | 25000
[15 empty] | 2763 | 1898 | 2018 | 2296 | 125500
[15 empty] | 2764 | 1898 | 2018 | 2771 | 42000
[15 empty] | 2910 | 1898 | 2018 | 6999 | 15000
[15 empty] | 2767 | 1899 | 2016 | 2763 | 163806
[15 empty] | 2768 | 1899 | 2017 | 2763 | 95703
[15 empty] | 2769 | 1899 | 2018 | 2763 | 106243
[15 empty] | 2770 | 1899 | 2019 | 2763 | 137303
[15 empty] | 2771 | 1899 | 2020 | 2763 | 150000
[15 empty] | 2772 | 1899 | 2021 | 2763 | 156000
[15 empty] | 2773 | 1899 | 2022 | 2763 | 162240
[15 empty] | 2861 | 1899 | 2023 | 2763 | 168730
[15 empty] | 3432 | 1899 | 2024 | 2763 | 175479
[15 empty] | 3580 | 1899 | 2025 | 2763 | 182498
[15 empty] | 3372 | 1900 | 2019 | 2742 | 840000
[15 empty] | 3373 | 1900 | 2021 | 2742
[15 empty] | 3819 | 1900 | 2022 | 2742
[15 empty] | 4030 | 1900 | 2022 | 2762
[15 empty] | 3358 | 1901 | 2018 | 2742 | 70000
[15 empty] | 3359 | 1901 | 2019 | 2742 | 105000
[15 empty] | 3400 | 1902 | 2017 | 2742 | 40000
[15 empty] | 3061 | 1902 | 2018 | 2742 | 360000
[15 empty] | 3062 | 1902 | 2018 | 2762 | 70000
[15 empty] | 3280 | 1903 | 2019 | 2742 | 366000
[15 empty] | 3541 | 1903 | 2019 | 2762 | 34000
[15 empty] | 3386 | 1904 | 2024 | 2742 | 192000
[15 empty] | 3387 | 1904 | 2025 | 2742 | 258000
[15 empty] | 3380 | 1905 | 2024 | 2742 | 329000
[15 empty] | 3381 | 1905 | 2025 | 2742 | 411000
[15 empty] | 3309 | 1906 | 2019 | 2770 | 1300000
[15 empty] | 3593 | 1906 | 2020 | 2770 | 700000
[15 empty] | 3399 | 1907 | 2017 | 2742 | 200000
[15 empty] | 3245 | 1908 | 2018 | 2742 | 165000
[15 empty] | 3246 | 1908 | 2019 | 2742 | 125000
[15 empty] | 3230 | 1909 | 2022 | 2742 | 760000
[15 empty] | 3231 | 1909 | 2023 | 2742 | 1140000
[15 empty] | 3696 | 1911 | 2019 | 2769 | 225000
[15 empty] | 3120 | 1911 | 2020 | 2769 | 100000
[15 empty] | 3121 | 1911 | 2021 | 2769 | 100000
[15 empty] | 3124 | 1911 | 2022 | 2769 | 875000
[15 empty] | 3695 | 1911 | 2023 | 2769 | 800000
[15 empty] | 3134 | 1912 | 2024 | 2769 | 442000
[15 empty] | 3135 | 1912 | 2025 | 2769 | 558000
[15 empty] | 3149 | 1913 | 2020 | 2769 | 630000
[15 empty] | 3150 | 1913 | 2021 | 2769 | 830000
[15 empty] | 3136 | 1914 | 2023 | 2769 | 838000
[15 empty] | 3137 | 1914 | 2024 | 2769 | 1062000
[15 empty] | 3152 | 1915 | 2024 | 2769 | 531000
[15 empty] | 3153 | 1915 | 2025 | 2769 | 669000
[15 empty] | 3132 | 1918 | 2024 | 2769 | 221000
[15 empty] | 3133 | 1918 | 2025 | 2769 | 279000
[15 empty] | 3161 | 1919 | 2019 | 2769 | 150000
[15 empty] | 3156 | 1920 | 2024 | 2769 | 90000
[15 empty] | 3157 | 1920 | 2025 | 2769 | 110000
[15 empty] | 3467 | 1921 | 2018 | 2769 | 368000
[15 empty] | 3466 | 1921 | 2019 | 2769 | 0
[15 empty] | 3465 | 1921 | 2020 | 2769 | 0
[15 empty] | 3464 | 1921 | 2021 | 2769 | 0
[15 empty] | 3112 | 1921 | 2022 | 2769 | 600000
[15 empty] | 3113 | 1921 | 2023 | 2769 | 600000
[15 empty] | 3114 | 1921 | 2024 | 2769 | 600000
[15 empty] | 3115 | 1921 | 2025 | 2769 | 600000
[15 empty] | 3116 | 1921 | 2026 | 2769 | 600000
[15 empty] | 2911 | 1922 | 2017 | 2710 | 50000
[15 empty] | 3513 | 1922 | 2017 | 2762 | 88000
[15 empty] | 3199 | 1922 | 2018 | 1625 | 0
[15 empty] | 2912 | 1922 | 2018 | 2296 | 257000
[15 empty] | 2913 | 1922 | 2018 | 2762 | 120000
[15 empty] | 3354 | 1922 | 2018 | 6640 | 64400
[15 empty] | 3046 | 1923 | 2025 | 2296 | 800000
[15 empty] | 3047 | 1923 | 2025 | 2762 | 775000
[15 empty] | 3056 | 1924 | 2020 | 2771 | 0
[15 empty] | 3057 | 1924 | 2020 | 6814 | 250000
[15 empty] | 3952 | 1924 | 2021 | 6814 | 250000
[15 empty] | 3402 | 1925 | 2024 | 1625 | 0
[15 empty] | 3401 | 1925 | 2025 | 2336 | 0
[15 empty] | 3194 | 1925 | 2025 | 2762 | 97000
[15 empty] | 3970 | 1925 | 2025 | 6814 | 500000
[15 empty] | 3318 | 1926 | 2022 | 2710 | 0
[15 empty] | 3967 | 1926 | 2023 | 1625 | 0
[15 empty] | 3718 | 1926 | 2024 | 2296 | 300000
[15 empty] | 3319 | 1926 | 2024 | 2710 | 288000
[15 empty] | 3966 | 1926 | 2024 | 2762 | 300000
[15 empty] | 3197 | 1927 | 2024 | 2710 | 765000
[15 empty] | 3195 | 1928 | 2025 | 2710 | 495000
[15 empty] | 3196 | 1929 | 2025 | 2710 | 552000
[15 empty] | 3193 | 1930 | 2025 | 2710 | 697500
[15 empty] | 3051 | 1931 | 2020 | 1625 | 0
[15 empty] | 3050 | 1931 | 2020 | 2762 | 231250
[15 empty] | 3049 | 1931 | 2026 | 2296 | 0
[15 empty] | 3973 | 1932 | 2025 | 1625 | 0
[15 empty] | 3214 | 1932 | 2025 | 2762 | 82500
[15 empty] | 3215 | 1932 | 2025 | 2771 | 110000
[15 empty] | 3394 | 1933 | 2026 | 2742 | 620000
[15 empty] | 3395 | 1933 | 2027 | 2742 | 780000
[15 empty] | 3119 | 1934 | 2020 | 2769 | 250000
[15 empty] | 3219 | 1935 | 2023 | 2742 | 570000
[15 empty] | 3220 | 1935 | 2024 | 2742 | 930000
[15 empty] | 3323 | 1936 | 2024 | 2743 | 158000
[15 empty] | 3324 | 1936 | 2025 | 2743 | 192000
[15 empty] | 3346 | 1937 | 2018 | 2743 | 298000
[15 empty] | 3347 | 1937 | 2019 | 2743 | 377000
[15 empty] | 3336 | 1938 | 2020 | 2743 | 0
[15 empty] | 3337 | 1938 | 2021 | 2743 | 0
[15 empty] | 3338 | 1938 | 2023 | 2743 | 0
[15 empty] | 3325 | 1939 | 2018 | 2743 | 150000
[15 empty] | 3326 | 1939 | 2019 | 2743 | 180000
[15 empty] | 3327 | 1940 | 2021 | 2336 | 880000
[15 empty] | 3348 | 1941 | 2018 | 2743 | 0
[15 empty] | 4045 | 1941 | 2019 | 2743 | 105000
[15 empty] | 4044 | 1941 | 2020 | 2743 | 155000
[15 empty] | 3329 | 1942 | 2018 | 6999 | 0
[15 empty] | 3330 | 1942 | 2019 | 6999 | 0
[15 empty] | 3331 | 1942 | 2020 | 6999 | 0
[15 empty] | 3332 | 1942 | 2021 | 6999 | 0
[15 empty] | 3333 | 1942 | 2022 | 6999 | 0
[15 empty] | 3278 | 1943 | 2024 | 2742 | 132000
[15 empty] | 3279 | 1943 | 2025 | 2742 | 168000
[15 empty] | 3287 | 1944 | 2018 | 2742 | 165000
[15 empty] | 3360 | 1945 | 2020 | 2742 | 0
[15 empty] | 3361 | 1945 | 2021 | 2742 | 0
[15 empty] | 3362 | 1945 | 2022 | 2742 | 0
[15 empty] | 3363 | 1945 | 2023 | 2742 | 0
[15 empty] | 3334 | 1946 | 2024 | 2743 | 1290000
[15 empty] | 3335 | 1946 | 2025 | 2743 | 1560000
[15 empty] | 3317 | 1947 | 2024 | 2710 | 0
[15 empty] | 3968 | 1947 | 2024 | 2762 | 0
[15 empty] | 3969 | 1947 | 2024 | 6814 | 428000
[15 empty] | 3210 | 1948 | 2024 | 2710 | 528000
[15 empty] | 3192 | 1949 | 2023 | 6814 | 495000
[15 empty] | 3203 | 1950 | 2025 | 2771 | 270000
[15 empty] | 3961 | 1951 | 2018 | 2762 | 53000
[15 empty] | 3026 | 1951 | 2019 | 2296 | 460000
[15 empty] | 3962 | 1951 | 2019 | 2762 | 30000
[15 empty] | 3028 | 1951 | 2020 | 1625 | 0
[15 empty] | 3027 | 1951 | 2020 | 2762 | 150000
[15 empty] | 3025 | 1951 | 2020 | 2771 | 15000
[15 empty] | 3500 | 1952 | 2018 | 2762 | 60000
[15 empty] | 3013 | 1952 | 2019 | 1625 | 0
[15 empty] | 3011 | 1952 | 2019 | 2296 | 100000
[15 empty] | 3012 | 1952 | 2019 | 2762 | 110500
[15 empty] | 2877 | 1953 | 2020 | 2762 | 0
[15 empty] | 2878 | 1953 | 2026 | 2762 | 15000
[15 empty] | 3491 | 1953 | 2027 | 2762 | 1704000
[15 empty] | 3492 | 1953 | 2028 | 2762 | 90000
[15 empty] | 2882 | 1954 | 2020 | 2762 | 130000
[15 empty] | 2847 | 1954 | 2021 | 2762 | 70000
[15 empty] | 3052 | 1955 | 2020 | 2296 | 87500
[15 empty] | 3055 | 1955 | 2020 | 2762 | 87500
[15 empty] | 3948 | 1955 | 2021 | 1625 | 0
[15 empty] | 3054 | 1955 | 2021 | 2296 | 87500
[15 empty] | 3946 | 1955 | 2021 | 2336 | 0
[15 empty] | 3053 | 1955 | 2021 | 2762 | 87500
[15 empty] | 3200 | 1956 | 2025 | 2710 | 507500
[15 empty] | 3188 | 1957 | 2024 | 2771 | 400000
[15 empty] | 3209 | 1958 | 2025 | 2710 | 400000
[15 empty] | 3058 | 1959 | 2018 | 6814 | 0
[15 empty] | 3321 | 1959 | 2019 | 6814 | 0
[15 empty] | 3059 | 1959 | 2022 | 2296 | 300000
[15 empty] | 3959 | 1959 | 2023 | 2296 | 300000
[15 empty] | 3060 | 1959 | 2024 | 2762 | 300000
[15 empty] | 3960 | 1959 | 2025 | 2762 | 33000
[15 empty] | 3003 | 1961 | 2021 | 2769 | 155000
[15 empty] | 3158 | 1961 | 2022 | 2769 | 195000
[15 empty] | 3552 | 1962 | 2024 | 2769 | 150000
[15 empty] | 3553 | 1962 | 2025 | 2769 | 95000
[15 empty] | 3138 | 1963 | 2026 | 2769 | 419000
[15 empty] | 3139 | 1963 | 2027 | 2769 | 531000
[15 empty] | 3169 | 1964 | 2020 | 1623 | 0
[15 empty] | 3170 | 1964 | 2022 | 1623 | 220000
[15 empty] | 3171 | 1964 | 2023 | 1623 | 255000
[15 empty] | 3111 | 1965 | 2020 | 2769 | 300000
[15 empty] | 3413 | 1966 | 2021 | 2336 | 0
[15 empty] | 3190 | 1966 | 2021 | 2710 | 0
[15 empty] | 3414 | 1966 | 2026 | 2296 | 1000000
[15 empty] | 3191 | 1966 | 2026 | 2710 | 750000
[15 empty] | 3316 | 1967 | 2019 | 6814 | 260000
[15 empty] | 2968 | 1968 | 2017 | 2710 | 850000
[15 empty] | 3296 | 1968 | 2018 | 2710 | 225000
[15 empty] | 3297 | 1968 | 2019 | 2710 | 300000
[15 empty] | 3298 | 1968 | 2020 | 2710 | 350000
[15 empty] | 3299 | 1968 | 2021 | 2710 | 250000
[15 empty] | 3300 | 1968 | 2022 | 2710 | 500000
[15 empty] | 3301 | 1968 | 2023 | 2710 | 350000
[15 empty] | 3507 | 1970 | 2017 | 2730 | 0
[15 empty] | 3508 | 1970 | 2018 | 2730 | 192000
[15 empty] | 3509 | 1970 | 2019 | 2730 | 3250000
[15 empty] | 3304 | 1970 | 2020 | 2730 | 2158000
[15 empty] | 3313 | 1970 | 2024 | 2730 | 0
[15 empty] | 3314 | 1971 | 2018 | 2296 | 0
[15 empty] | 3315 | 1971 | 2018 | 2721 | 67000
[15 empty] | 3293 | 1973 | 2019 | 2336 | 30000
[15 empty] | 3292 | 1973 | 2019 | 2721 | 200000
[15 empty] | 2967 | 1975 | 2019 | 2721 | 500000
[15 empty] | 3294 | 1976 | 2019 | 2296 | 1087500
[15 empty] | 3295 | 1976 | 2019 | 2721 | 120000
[15 empty] | 2824 | 1977 | 2019 | 2710 | 150000
[15 empty] | 2813 | 1978 | 2019 | 2710
[15 empty] | 2814 | 1978 | 2020 | 2710 | 200000
[15 empty] | 2815 | 1978 | 2021 | 2710 | 635000
[15 empty] | 2816 | 1978 | 2022 | 2710 | 1940000
[15 empty] | 3688 | 1978 | 2023 | 2710 | 1940000
[15 empty] | 2817 | 1979 | 2020 | 2710
[15 empty] | 2818 | 1979 | 2021 | 2710 | 50000
[15 empty] | 2819 | 1979 | 2022 | 2710 | 200000
[15 empty] | 2820 | 1979 | 2023 | 2710 | 585000
[15 empty] | 2821 | 1979 | 2024 | 2710 | 1940000
[15 empty] | 3746 | 1979 | 2025 | 2710 | 1940000
[15 empty] | 2825 | 1980 | 2019 | 2710 | 100000
[15 empty] | 3288 | 1981 | 2017 | 2742 | 1206500
[15 empty] | 3289 | 1981 | 2018 | 2742 | 1900000
[15 empty] | 2849 | 1983 | 2017 | 2710 | 10000
[15 empty] | 2848 | 1983 | 2017 | 2742 | 10000
[15 empty] | 2851 | 1983 | 2018 | 2710 | 40000
[15 empty] | 2850 | 1983 | 2018 | 2742 | 40000
[15 empty] | 2798 | 1985 | 2018 | 2710 | 600000
[15 empty] | 2804 | 1988 | 2018 | 2742 | 200000
[15 empty] | 3531 | 1989 | 2018 | 2742 | 440000
[15 empty] | 2796 | 1989 | 2020 | 2742 | 0
[15 empty] | 2797 | 1989 | 2021 | 2742 | 0
[15 empty] | 2937 | 1989 | 2023 | 2742 | 450000
[15 empty] | 3473 | 1989 | 2024 | 2742 | 8550000
[15 empty] | 2800 | 1990 | 2021 | 2742 | 250000
[15 empty] | 2801 | 1990 | 2022 | 2742 | 900000
[15 empty] | 2939 | 1990 | 2023 | 2742 | 600000
[15 empty] | 2802 | 1991 | 2019 | 2742 | 100000
[15 empty] | 2803 | 1991 | 2020 | 2742 | 562500
[15 empty] | 2940 | 1991 | 2021 | 2742 | 187500
[15 empty] | 3241 | 1992 | 2024 | 2742 | 442000
[15 empty] | 3242 | 1992 | 2025 | 2742 | 558000
[15 empty] | 3270 | 1993 | 2025 | 2742 | 176000
[15 empty] | 3271 | 1993 | 2026 | 2742 | 224000
[15 empty] | 3251 | 1994 | 2018 | 2742 | 0
[15 empty] | 3253 | 1994 | 2024 | 2742 | 500000
[15 empty] | 3382 | 1995 | 2024 | 2742 | 1100000
[15 empty] | 3383 | 1995 | 2025 | 2742 | 1400000
[15 empty] | 3370 | 1996 | 2024 | 2742 | 792000
[15 empty] | 3371 | 1996 | 2025 | 2742 | 1008000
[15 empty] | 3283 | 1997 | 2020 | 2742 | 30000
[15 empty] | 3284 | 1997 | 2021 | 2742 | 370000
[15 empty] | 3543 | 1997 | 2021 | 2762 | 0
[15 empty] | 3281 | 1998 | 2024 | 2742 | 308000
[15 empty] | 3282 | 1998 | 2025 | 2742 | 392000
[15 empty] | 3264 | 1999 | 2024 | 2742 | 310000
[15 empty] | 3265 | 1999 | 2025 | 2742 | 390000
[15 empty] | 3285 | 2000 | 2024 | 2742 | 440000
[15 empty] | 3286 | 2000 | 2025 | 2742 | 660000
[15 empty] | 4003 | 2000 | 2025 | 2762 | 0
[15 empty] | 2811 | 2001 | 2021 | 2710 | 50000
[15 empty] | 2805 | 2001 | 2022 | 2710 | 140000
[15 empty] | 2826 | 2002 | 2021 | 2742
[15 empty] | 2827 | 2002 | 2023 | 2742 | 500000
[15 empty] | 2941 | 2002 | 2024 | 2742 | 500000
[15 empty] | 2830 | 2003 | 2021 | 2742 | 200000
[15 empty] | 2831 | 2003 | 2022 | 2742 | 600000
[15 empty] | 2942 | 2003 | 2023 | 2742 | 400000
[15 empty] | 3365 | 2004 | 2019 | 2742 | 0
[15 empty] | 3366 | 2004 | 2022 | 2742 | 1300000
[15 empty] | 3896 | 2004 | 2023 | 2742 | 1300000
[15 empty] | 3356 | 2005 | 2026 | 2762 | 6100000
[15 empty] | 3142 | 2006 | 2026 | 2762 | 998000
[15 empty] | 3480 | 2007 | 2020 | 6814 | 350000
[15 empty] | 3349 | 2007 | 2021 | 6814 | 350000
[15 empty] | 3351 | 2008 | 2024 | 2762 | 430000
[15 empty] | 3850 | 2008 | 2025 | 2762 | 860000
[15 empty] | 3064 | 2009 | 2018 | 6814 | 1235000
[15 empty] | 2990 | 2010 | 2017 | 2762 | 0
[15 empty] | 2991 | 2010 | 2018 | 2762 | 0
[15 empty] | 2992 | 2010 | 2020 | 2762 | 100000
[15 empty] | 3828 | 2010 | 2021 | 2296 | 267500
[15 empty] | 3827 | 2010 | 2021 | 2762 | 400000
[15 empty] | 3830 | 2010 | 2022 | 2296 | 954000
[15 empty] | 3829 | 2010 | 2022 | 2762 | 400000
[15 empty] | 3474 | 2011 | 2022 | 2710 | 260000
[15 empty] | 3350 | 2011 | 2023 | 1626 | 0
[15 empty] | 3937 | 2011 | 2023 | 2710 | 785000
[15 empty] | 3080 | 2012 | 2023 | 2762 | 180000
[15 empty] | 3839 | 2012 | 2024 | 2762 | 360000
[15 empty] | 3073 | 2013 | 2021 | 2762 | 125000
[15 empty] | 3826 | 2013 | 2022 | 2762 | 255000
[15 empty] | 3070 | 2015 | 2019 | 2296 | 0
[15 empty] | 3068 | 2015 | 2019 | 2762 | 0
[15 empty] | 3751 | 2015 | 2020 | 2296 | 900000
[15 empty] | 3069 | 2015 | 2020 | 2762 | 500000
[15 empty] | 3808 | 2015 | 2021 | 2762 | 300000
[15 empty] | 3071 | 2016 | 2019 | 2762 | 195000
[15 empty] | 3072 | 2016 | 2020 | 2762 | 390000
[15 empty] | 3840 | 2017 | 2022 | 2296 | 570000
[15 empty] | 3079 | 2017 | 2022 | 2762 | 285000
[15 empty] | 3841 | 2017 | 2023 | 2762 | 285000
[15 empty] | 3078 | 2018 | 2023 | 2762 | 575000
[15 empty] | 3849 | 2018 | 2024 | 2762 | 1155000
[15 empty] | 3076 | 2019 | 2019 | 6814 | 515000
[15 empty] | 3837 | 2020 | 2022 | 2296 | 650000
[15 empty] | 3077 | 2020 | 2022 | 2762 | 225000
[15 empty] | 3838 | 2020 | 2023 | 2762 | 425000
[15 empty] | 3810 | 2021 | 2020 | 2336 | 445000
[15 empty] | 3075 | 2021 | 2020 | 2762 | 200000
[15 empty] | 3809 | 2021 | 2021 | 2762 | 330000
[15 empty] | 3067 | 2022 | 2023 | 2762 | 450000
[15 empty] | 3848 | 2022 | 2024 | 2762 | 780000
[15 empty] | 3074 | 2023 | 2022 | 2762 | 400000
[15 empty] | 3836 | 2023 | 2023 | 2762 | 800000
[15 empty] | 3384 | 2025 | 2025 | 2742 | 1364000
[15 empty] | 3385 | 2025 | 2026 | 2742 | 1736000
[15 empty] | 3544 | 2026 | 2020 | 2762 | 0
[15 empty] | 3368 | 2026 | 2024 | 2742 | 663000
[15 empty] | 3369 | 2026 | 2025 | 2742 | 837000
[15 empty] | 3822 | 2026 | 2025 | 2762 | 116000
[15 empty] | 3098 | 2027 | 2022 | 2769 | 250000
[15 empty] | 3175 | 2028 | 2021 | 2769 | 402000
[15 empty] | 3176 | 2028 | 2022 | 2769 | 498000
[15 empty] | 3177 | 2029 | 2024 | 2769 | 1000000
[15 empty] | 3178 | 2029 | 2025 | 2769 | 0
[15 empty] | 3794 | 2030 | 2022 | 2769 | 100000
[15 empty] | 2951 | 2031 | 2018 | 2772 | 8000
[15 empty] | 3663 | 2031 | 2019 | 2772 | 12000
[15 empty] | 3932 | 2031 | 2020 | 2772 | 100000
[15 empty] | 3091 | 2032 | 2018 | 2772 | 750000
[15 empty] | 3090 | 2033 | 2023 | 2772 | 6000000
[15 empty] | 2966 | 2034 | 2022 | 2710 | 250000
[15 empty] | 3328 | 2035 | 2018 | 2743 | 280000
[15 empty] | 3460 | 2036 | 2018 | 2742 | 0
[15 empty] | 3461 | 2036 | 2019 | 2742 | 79900
[15 empty] | 3276 | 2036 | 2024 | 2742 | 0
[15 empty] | 3277 | 2036 | 2025 | 2742 | 0
[15 empty] | 3140 | 2037 | 2026 | 2742 | 560000
[15 empty] | 3141 | 2037 | 2027 | 2742 | 712000
[15 empty] | 2898 | 2038 | 2026 | 2742 | 1550000
[15 empty] | 2899 | 2038 | 2027 | 2742 | 2325200
[15 empty] | 3254 | 2039 | 2024 | 2742 | 797400
[15 empty] | 3255 | 2039 | 2025 | 2742 | 1008600
[15 empty] | 3256 | 2040 | 2029 | 2742 | 932800
[15 empty] | 3257 | 2040 | 2030 | 2742 | 1174200
[15 empty] | 3125 | 2041 | 2026 | 2769 | 283200
[15 empty] | 3126 | 2041 | 2027 | 2769 | 424800
[15 empty] | 2844 | 2042 | 2021 | 2730 | 730000
[15 empty] | 2845 | 2042 | 2022 | 2730 | 270000
[15 empty] | 3016 | 2044 | 2020 | 2180 | 15000000
[15 empty] | 3021 | 2044 | 2020 | 2324 | 1800000
[15 empty] | 3017 | 2044 | 2020 | 2336 | 12000000
[15 empty] | 3018 | 2044 | 2020 | 2703 | 600000
[15 empty] | 3020 | 2044 | 2020 | 2710 | 600000
[15 empty] | 2866 | 2045 | 2018 | 2763 | 42656
[15 empty] | 2867 | 2045 | 2019 | 2763 | 250000
[15 empty] | 2868 | 2045 | 2020 | 2763 | 500000
[15 empty] | 2869 | 2045 | 2021 | 2763 | 515000
[15 empty] | 3429 | 2045 | 2022 | 2763 | 530450
[15 empty] | 3430 | 2045 | 2023 | 2763 | 546364
[15 empty] | 3431 | 2045 | 2024 | 2763 | 562754
[15 empty] | 3579 | 2045 | 2025 | 2763 | 579637
[15 empty] | 3258 | 2046 | 2027 | 2742 | 960320
[15 empty] | 3259 | 2046 | 2028 | 2742 | 1215480
[15 empty] | 3472 | 2047 | 2026 | 2742 | 2863800
[15 empty] | 3260 | 2048 | 2026 | 2742 | 987400
[15 empty] | 3261 | 2048 | 2027 | 2742 | 1248600
[15 empty] | 3262 | 2049 | 2027 | 2742 | 417400
[15 empty] | 3263 | 2049 | 2028 | 2742 | 528600
[15 empty] | 2902 | 2050 | 2019 | 2763 | 38213
[15 empty] | 2903 | 2050 | 2022 | 2763 | 424368
[15 empty] | 2904 | 2050 | 2023 | 2763 | 1269600
[15 empty] | 3392 | 2051 | 2025 | 2742 | 748000
[15 empty] | 3393 | 2051 | 2026 | 2742 | 952000
[15 empty] | 3228 | 2053 | 2023 | 2742 | 221000
[15 empty] | 3229 | 2053 | 2024 | 2742 | 279000
[15 empty] | 3290 | 2054 | 2024 | 2742 | 264000
[15 empty] | 3291 | 2054 | 2025 | 2742 | 336000
[15 empty] | 2949 | 2055 | 2018 | 2742 | 40000
[15 empty] | 2950 | 2055 | 2022 | 2742 | 400000
[15 empty] | 3039 | 2056 | 2022 | 2771 | 150000
[15 empty] | 3408 | 2058 | 2018 | 2336 | 0
[15 empty] | 2969 | 2058 | 2018 | 2710 | 0
[15 empty] | 3420 | 2058 | 2019 | 2710 | 440000
[15 empty] | 3421 | 2058 | 2020 | 2710 | 0
[15 empty] | 3396 | 2059 | 2025 | 2742 | 616000
[15 empty] | 3397 | 2059 | 2026 | 2742 | 784000
[15 empty] | 3250 | 2060 | 2019 | 2742 | 500000
[15 empty] | 3547 | 2061 | 2022 | 2762 | 0
[15 empty] | 3375 | 2061 | 2025 | 2742 | 704000
[15 empty] | 3376 | 2061 | 2026 | 2742 | 896000
[15 empty] | 2981 | 2062 | 2018 | 2742 | 40000
[15 empty] | 2982 | 2062 | 2019 | 2742 | 50000
[15 empty] | 3619 | 2062 | 2020 | 2742 | 140000
[15 empty] | 3216 | 2063 | 2020 | 2742 | 420000
[15 empty] | 3217 | 2063 | 2021 | 2742 | 280000
[15 empty] | 3243 | 2064 | 2024 | 2742 | 1012000
[15 empty] | 3244 | 2064 | 2025 | 2742 | 1288000
[15 empty] | 3389 | 2065 | 2024 | 2742 | 660000
[15 empty] | 3390 | 2065 | 2025 | 2742 | 840000
[15 empty] | 3234 | 2066 | 2021 | 2742 | 150000
[15 empty] | 3221 | 2067 | 2023 | 2742 | 250000
[15 empty] | 3538 | 2068 | 2020 | 2336 | 642000
[15 empty] | 3398 | 2068 | 2020 | 2742 | 642000
[15 empty] | 3881 | 2068 | 2021 | 2336 | 428000
[15 empty] | 3882 | 2068 | 2021 | 2742 | 428000
[15 empty] | 3341 | 2069 | 2024 | 2743 | 0
[15 empty] | 3342 | 2069 | 2026 | 2743 | 160000
[15 empty] | 3208 | 2070 | 2026 | 2762 | 1320000
[15 empty] | 4004 | 2070 | 2027 | 2762 | 0
[15 empty] | 3204 | 2071 | 2026 | 2769 | 453000
[15 empty] | 3205 | 2071 | 2027 | 2769 | 567000
[15 empty] | 3206 | 2072 | 2026 | 2742 | 303000
[15 empty] | 3207 | 2072 | 2027 | 2742 | 380000
[15 empty] | 3237 | 2073 | 2024 | 2742 | 880000
[15 empty] | 3238 | 2073 | 2025 | 2742 | 1120000
[15 empty] | 3239 | 2074 | 2025 | 2742 | 330000
[15 empty] | 3240 | 2074 | 2026 | 2742 | 420000
[15 empty] | 3305 | 2075 | 2023 | 2730 | 1500000
[15 empty] | 3302 | 2076 | 2018 | 2730 | 350000
[15 empty] | 3310 | 2076 | 2019 | 2730 | 500000
[15 empty] | 3505 | 2076 | 2020 | 2730 | 2770000
[15 empty] | 3506 | 2076 | 2021 | 2730 | 4160000
[15 empty] | 3303 | 2077 | 2020 | 2730 | 300000
[15 empty] | 3312 | 2077 | 2021 | 2730 | 3000000
[15 empty] | 3306 | 2078 | 2020 | 2730 | 300000
[15 empty] | 3311 | 2078 | 2021 | 2730 | 3000000
[15 empty] | 3307 | 2079 | 2023 | 2730 | 2500000
[15 empty] | 3308 | 2080 | 2023 | 2730 | 2000000
[15 empty] | 3417 | 2083 | 2022 | 2710 | 0
[15 empty] | 3416 | 2083 | 2026 | 2710 | 200000
[15 empty] | 3539 | 2084 | 2019 | 2703 | 100000
[15 empty] | 3540 | 2084 | 2019 | 2721 | 50000
[15 empty] | 3418 | 2085 | 2018 | 2296 | 290000
[15 empty] | 3419 | 2085 | 2018 | 2721 | 400000
[15 empty] | 3517 | 2087 | 2018 | 2730 | 78000
[15 empty] | 3518 | 2087 | 2019 | 2730 | 1692000
[15 empty] | 3519 | 2087 | 2020 | 2730
[15 empty] | 3520 | 2087 | 2021 | 2730
[15 empty] | 3433 | 2088 | 2018 | 2763 | 200000
[15 empty] | 3434 | 2088 | 2019 | 2763 | 2000000
[15 empty] | 3435 | 2088 | 2020 | 2763 | 12000000
[15 empty] | 3571 | 2088 | 2021 | 2763 | 7300000
[15 empty] | 3436 | 2089 | 2018 | 2763 | 500000
[15 empty] | 3437 | 2089 | 2019 | 2763 | 108161
[15 empty] | 3438 | 2089 | 2020 | 2763 | 111406
[15 empty] | 3439 | 2089 | 2021 | 2763 | 114748
[15 empty] | 3440 | 2089 | 2022 | 2763 | 118190
[15 empty] | 3442 | 2089 | 2023 | 2763 | 121736
[15 empty] | 3443 | 2089 | 2024 | 2763 | 125388
[15 empty] | 3444 | 2090 | 2018 | 2763 | 402204
[15 empty] | 3445 | 2090 | 2019 | 2763 | 204950
[15 empty] | 3446 | 2090 | 2020 | 2763 | 61099
[15 empty] | 3447 | 2090 | 2021 | 2763 | 62931
[15 empty] | 3448 | 2090 | 2022 | 2763 | 64819
[15 empty] | 3449 | 2090 | 2023 | 2763 | 66764
[15 empty] | 3450 | 2090 | 2024 | 2763 | 68767
[15 empty] | 3581 | 2090 | 2025 | 2763 | 70830
[15 empty] | 3459 | 2091 | 2018 | 2762 | 100000
[15 empty] | 3458 | 2091 | 2019 | 2762 | 100000
[15 empty] | 3712 | 2091 | 2020 | 2762 | 100000
[15 empty] | 3713 | 2091 | 2021 | 2762 | 100000
[15 empty] | 3714 | 2091 | 2022 | 2762 | 100000
[15 empty] | 3715 | 2091 | 2023 | 2762 | 100000
[15 empty] | 3716 | 2091 | 2024 | 2762 | 100000
[15 empty] | 3717 | 2091 | 2025 | 2762 | 100000
[15 empty] | 3510 | 2092 | 2019 | 2710 | 30000
[15 empty] | 3554 | 2092 | 2020 | 2710 | 40000
[15 empty] | 3555 | 2092 | 2021 | 2710 | 40000
[15 empty] | 3528 | 2093 | 2020 | 7119 | 350000
[15 empty] | 3529 | 2093 | 2021 | 7119 | 2325000
[15 empty] | 3530 | 2093 | 2022 | 7119 | 2325000
[15 empty] | 3496 | 2095 | 2018 | 2762 | 171000
[15 empty] | 3497 | 2095 | 2019 | 2762 | 657700
[15 empty] | 3462 | 2096 | 2018 | 2769 | 0
[15 empty] | 3463 | 2096 | 2019 | 2769 | 232000
[15 empty] | 3471 | 2097 | 2018 | 2769 | 700000
[15 empty] | 3953 | 2098 | 2018 | 2762 | 46000
[15 empty] | 3499 | 2098 | 2019 | 2296 | 406000
[15 empty] | 3498 | 2098 | 2019 | 2762 | 250000
[15 empty] | 3951 | 2098 | 2020 | 1625 | 97000
[15 empty] | 3954 | 2098 | 2020 | 2762 | 250000
[15 empty] | 3515 | 2099 | 2019 | 2296 | 105000
[15 empty] | 3516 | 2099 | 2019 | 2762 | 80000
[15 empty] | 3955 | 2103 | 2025 | 2761 | 250000
[15 empty] | 3701 | 2104 | 2021 | 2296 | 0
[15 empty] | 3702 | 2104 | 2022 | 2761 | 100000
[15 empty] | 3707 | 2104 | 2023 | 2761 | 100000
[15 empty] | 3708 | 2104 | 2024 | 2761 | 100000
[15 empty] | 3709 | 2104 | 2025 | 2761 | 100000
[15 empty] | 3710 | 2105 | 2022 | 2761 | 50000
[15 empty] | 3711 | 2105 | 2023 | 2761 | 50000
[15 empty] | 3972 | 2106 | 2025 | 1625 | 0
[15 empty] | 3971 | 2106 | 2025 | 2762 | 87000
[15 empty] | 3614 | 2107 | 2025 | 7119 | 650000
[15 empty] | 3670 | 2107 | 2026 | 7119 | 1750000
[15 empty] | 4037 | 2108 | 2022 | 2743 | 500000
[15 empty] | 4023 | 2109 | 2021 | 2743 | 125000
[15 empty] | 3668 | 2110 | 2025 | 7119 | 760000
[15 empty] | 3615 | 2110 | 2026 | 7119 | 2040000
[15 empty] | 4042 | 2111 | 2022 | 2743 | 290000
[15 empty] | 3683 | 2112 | 2020 | 2743 | 1200000
[15 empty] | 3672 | 2113 | 2020 | 2743 | 275000
[15 empty] | 3673 | 2113 | 2021 | 2743 | 2300000
[15 empty] | 4043 | 2114 | 2026 | 2743 | 6000000
[15 empty] | 3671 | 2115 | 2020 | 2743 | 700000
[15 empty] | 4040 | 2116 | 2024 | 2743 | 334400
[15 empty] | 4041 | 2116 | 2025 | 2743 | 425600
[15 empty] | 4046 | 2117 | 2020 | 2743 | 40000
[15 empty] | 3616 | 2118 | 2021 | 7119 | 200000
[15 empty] | 3617 | 2118 | 2022 | 7119 | 0
[15 empty] | 3618 | 2118 | 2023 | 7119 | 200000
[15 empty] | 4036 | 2119 | 2020 | 2743 | 75000
[15 empty] | 4031 | 2120 | 2025 | 2743 | 352000
[15 empty] | 4032 | 2120 | 2026 | 2743 | 448000
[15 empty] | 4034 | 2121 | 2025 | 2743 | 220000
[15 empty] | 4035 | 2121 | 2026 | 2743 | 280000
[15 empty] | 3611 | 2122 | 2019 | 2710 | 37500
[15 empty] | 3610 | 2122 | 2019 | 2742 | 37500
[15 empty] | 3613 | 2122 | 2020 | 2710 | 0
[15 empty] | 3612 | 2122 | 2020 | 2742 | 0
[15 empty] | 4063 | 2122 | 2021 | 2710 | 45000
[15 empty] | 4058 | 2122 | 2021 | 2742 | 45000
[15 empty] | 4066 | 2122 | 2022 | 2710 | 350000
[15 empty] | 4064 | 2122 | 2022 | 2742 | 350000
[15 empty] | 3875 | 2123 | 2022 | 2710 | 100000
[15 empty] | 3605 | 2124 | 2019 | 2742 | 210000
[15 empty] | 3609 | 2124 | 2020 | 2742 | 2250000
[15 empty] | 3603 | 2125 | 2022 | 2742 | 600000
[15 empty] | 3604 | 2125 | 2023 | 2742 | 1600000
[15 empty] | 4005 | 2126 | 2024 | 2742 | 352000
[15 empty] | 4006 | 2126 | 2025 | 2742 | 448000
[15 empty] | 3923 | 2127 | 2020 | 2703 | 900000
[15 empty] | 3898 | 2127 | 2020 | 2742 | 150000
[15 empty] | 3899 | 2127 | 2021 | 2742 | 150000
[15 empty] | 4028 | 2128 | 2025 | 2742 | 198000
[15 empty] | 4029 | 2128 | 2026 | 2742 | 252000
[15 empty] | 3990 | 2129 | 2020 | 2742 | 200000
[15 empty] | 4024 | 2130 | 2021 | 2742 | 125000
[15 empty] | 3633 | 2131 | 2020 | 2742 | 150000
[15 empty] | 4016 | 2132 | 2024 | 2742 | 2100000
[15 empty] | 4017 | 2132 | 2025 | 2742 | 2600000
[15 empty] | 4020 | 2133 | 2024 | 2742 | 350000
[15 empty] | 4021 | 2133 | 2025 | 2742 | 1695000
[15 empty] | 4022 | 2133 | 2026 | 2742 | 2155000
[15 empty] | 3697 | 2134 | 2019 | 2769 | 250000
[15 empty] | 3698 | 2134 | 2020 | 2769 | 400000
[15 empty] | 4014 | 2135 | 2025 | 2742 | 308000
[15 empty] | 4015 | 2135 | 2026 | 2742 | 392000
[15 empty] | 4018 | 2136 | 2025 | 2742 | 1430000
[15 empty] | 4019 | 2136 | 2026 | 2742 | 1820000
[15 empty] | 4008 | 2137 | 2025 | 2742 | 352000
[15 empty] | 4009 | 2137 | 2026 | 2742 | 448000
[15 empty] | 3994 | 2138 | 2020 | 2742 | 500000
[15 empty] | 3995 | 2138 | 2021 | 2742 | 1000000
[15 empty] | 3996 | 2138 | 2022 | 2742 | 1000000
[15 empty] | 3997 | 2138 | 2023 | 2742 | 1000000
[15 empty] | 3998 | 2138 | 2024 | 2742 | 1000000
[15 empty] | 3999 | 2138 | 2025 | 2742 | 1000000
[15 empty] | 4001 | 2138 | 2026 | 2742 | 8500000
[15 empty] | 4010 | 2139 | 2025 | 2742 | 340000
[15 empty] | 4011 | 2139 | 2026 | 2742 | 430000
[15 empty] | 3988 | 2140 | 2021 | 2742 | 663000
[15 empty] | 3989 | 2140 | 2022 | 2742 | 837000
[15 empty] | 3986 | 2141 | 2021 | 2742 | 350000
[15 empty] | 3987 | 2141 | 2022 | 2742 | 450000
[15 empty] | 3876 | 2142 | 2021 | 2742 | 25000
[15 empty] | 3878 | 2142 | 2021 | 2743 | 25000
[15 empty] | 3877 | 2142 | 2022 | 2742 | 175000
[15 empty] | 3879 | 2142 | 2022 | 2743 | 175000
[15 empty] | 4027 | 2143 | 2021 | 2742 | 450000
[15 empty] | 4012 | 2144 | 2025 | 2742 | 264000
[15 empty] | 4013 | 2144 | 2026 | 2742 | 336000
[15 empty] | 3720 | 2145 | 2019 | 2771 | 150000
[15 empty] | 3567 | 2147 | 2019 | 2763 | 400000
[15 empty] | 3748 | 2148 | 2019 | 2296 | 126300
[15 empty] | 3749 | 2148 | 2019 | 2762 | 31600
[15 empty] | 3634 | 2149 | 2023 | 2710 | 212000
[15 empty] | 3635 | 2150 | 2024 | 2710 | 166000
[15 empty] | 3639 | 2151 | 2020 | 2296 | 448000
[15 empty] | 3640 | 2151 | 2020 | 6814 | 280400
[15 empty] | 3648 | 2152 | 2019 | 2710 | 595000
[15 empty] | 3975 | 2152 | 2020 | 0100 | 115000
[15 empty] | 3684 | 2152 | 2020 | 2710 | 360000
[15 empty] | 3976 | 2152 | 2021 | 0100 | 115000
[15 empty] | 3685 | 2152 | 2021 | 2710 | 360000
[15 empty] | 3977 | 2152 | 2022 | 0100 | 115000
[15 empty] | 3686 | 2152 | 2022 | 2710 | 360000
[15 empty] | 3978 | 2152 | 2023 | 0100 | 115000
[15 empty] | 3687 | 2152 | 2023 | 2710 | 360000
[15 empty] | 3979 | 2152 | 2024 | 2710 | 360000
[15 empty] | 3980 | 2152 | 2025 | 2710 | 360000
[15 empty] | 3652 | 2153 | 2020 | 2721 | 150000
[15 empty] | 3654 | 2154 | 2022 | 2336 | 75000
[15 empty] | 3653 | 2154 | 2022 | 2721 | 25000
[15 empty] | 3922 | 2155 | 2020 | 2703 | 700000
[15 empty] | 3699 | 2156 | 2020 | 2710 | 250000
[15 empty] | 3936 | 2156 | 2021 | 1626 | 0
[15 empty] | 3795 | 2157 | 2020 | 2769 | 75000
[15 empty] | 3796 | 2157 | 2021 | 2769 | 155000
[15 empty] | 3853 | 2160 | 2025 | 2762 | 425000
[15 empty] | 3854 | 2160 | 2026 | 2762 | 875000
[15 empty] | 3851 | 2161 | 2024 | 2762 | 250000
[15 empty] | 3852 | 2161 | 2025 | 2762 | 520000
[15 empty] | 3752 | 2162 | 2020 | 2296 | 418000
[15 empty] | 3753 | 2162 | 2020 | 2762 | 200000
[15 empty] | 4052 | 2162 | 2021 | 2762 | 200000
[15 empty] | 3861 | 2163 | 2024 | 2762 | 600000
[15 empty] | 3862 | 2163 | 2025 | 2762 | 1000000
[15 empty] | 3804 | 2164 | 2019 | 2721 | 460000
[15 empty] | 3857 | 2167 | 2024 | 2762 | 200000
[15 empty] | 3858 | 2167 | 2025 | 2762 | 360000
[15 empty] | 3859 | 2168 | 2024 | 2762 | 250000
[15 empty] | 3860 | 2168 | 2025 | 2762 | 500000
[15 empty] | 3974 | 2171 | 2025 | 2336 | 150000
[15 empty] | 3655 | 2172 | 2022 | 2721 | 100000
[15 empty] | 3642 | 2173 | 2020 | 2336 | 250000
[15 empty] | 3641 | 2174 | 2020 | 2336 | 300000
[15 empty] | 3638 | 2175 | 2021 | 2324 | 50000
[15 empty] | 3637 | 2175 | 2021 | 2721 | 250000
[15 empty] | 3651 | 2176 | 2019 | 2299 | 650000
[15 empty] | 3657 | 2177 | 2019 | 2710 | 0
[15 empty] | 3658 | 2177 | 2019 | 2721 | 800000
[15 empty] | 3800 | 2178 | 2021 | 2769 | 75000
[15 empty] | 3700 | 2179 | 2020 | 2703 | 600000
[15 empty] | 3719 | 2179 | 2021 | 2703 | 1400000
[15 empty] | 3557 | 2180 | 2019 | 2710 | 35000
[15 empty] | 3558 | 2180 | 2020 | 2710 | 100000
[15 empty] | 3559 | 2180 | 2021 | 2710 | 100000
[15 empty] | 3560 | 2180 | 2022 | 2710 | 3000000
[15 empty] | 3561 | 2180 | 2023 | 2710 | 3000000
[15 empty] | 3563 | 2180 | 2024 | 2710 | 3000000
[15 empty] | 3802 | 2181 | 2025 | 2769 | 400000
[15 empty] | 3803 | 2181 | 2026 | 2769 | 400000
[15 empty] | 3692 | 2182 | 2020 | 2769 | 525000
[15 empty] | 3693 | 2182 | 2021 | 2769 | 475000
[15 empty] | 3694 | 2182 | 2022 | 2769 | 0
[15 empty] | 3582 | 2185 | 2018 | 2763 | 362568
[15 empty] | 3583 | 2185 | 2019 | 2763 | 500000
[15 empty] | 3584 | 2185 | 2020 | 2763 | 450000
[15 empty] | 3585 | 2185 | 2021 | 2763 | 450000
[15 empty] | 3586 | 2185 | 2022 | 2763 | 350000
[15 empty] | 3587 | 2186 | 2020 | 2703 | 550000
[15 empty] | 3588 | 2186 | 2021 | 2703 | 550000
[15 empty] | 3589 | 2186 | 2022 | 2703 | 550000
[15 empty] | 3590 | 2186 | 2023 | 2703 | 550000
[15 empty] | 3591 | 2186 | 2024 | 2703 | 550000
[15 empty] | 3592 | 2186 | 2025 | 2703 | 550000
[15 empty] | 3596 | 2188 | 2020 | 2710 | 400000
[15 empty] | 3855 | 2196 | 2024 | 2762 | 120000
[15 empty] | 3856 | 2196 | 2025 | 2762 | 240000
[15 empty] | 3664 | 2198 | 2021 | 2772 | 200000
[15 empty] | 3805 | 2199 | 2020 | 2721 | 220000
[15 empty] | 3806 | 2199 | 2020 | 6988 | 220000
[15 empty] | 3743 | 2216 | 2020 | 2703 | 722000
[15 empty] | 3744 | 2216 | 2020 | 2721 | 127500
[15 empty] | 3745 | 2216 | 2020 | 2762 | 180000
[15 empty] | 3755 | 2216 | 2021 | 2721 | 127500
[15 empty] | 3754 | 2216 | 2021 | 2762 | 180000
[15 empty] | 3742 | 2217 | 2019 | 2703 | 230000
[15 empty] | 3741 | 2217 | 2019 | 2721 | 138000
[15 empty] | 4025 | 2218 | 2019 | 2742 | 600000
[15 empty] | 4026 | 2218 | 2020 | 2742 | 0
[15 empty] | 3624 | 2219 | 2021 | 2742 | 25000
[15 empty] | 3626 | 2219 | 2021 | 2743 | 25000
[15 empty] | 3627 | 2219 | 2022 | 2742 | 175000
[15 empty] | 3628 | 2219 | 2022 | 2743 | 175000
[15 empty] | 3900 | 2220 | 2025 | 2769 | 250000
[15 empty] | 3902 | 2220 | 2026 | 2769 | 300000
[15 empty] | 4050 | 2221 | 2025 | 2742 | 264000
[15 empty] | 4051 | 2221 | 2026 | 2742 | 336000
[15 empty] | 3740 | 2222 | 2020 | 2721 | 200000
[15 empty] | 3739 | 2222 | 2020 | 2722 | 200000
[15 empty] | 3782 | 2222 | 2021 | 2721 | 200000
[15 empty] | 3783 | 2222 | 2021 | 2722 | 200000
[15 empty] | 3784 | 2222 | 2022 | 2721 | 200000
[15 empty] | 3791 | 2222 | 2022 | 2722 | 200000
[15 empty] | 3785 | 2222 | 2023 | 2721 | 200000
[15 empty] | 3786 | 2222 | 2023 | 2722 | 200000
[15 empty] | 3788 | 2222 | 2024 | 2721 | 200000
[15 empty] | 3787 | 2222 | 2024 | 2722 | 200000
[15 empty] | 3790 | 2222 | 2025 | 2721 | 200000
[15 empty] | 3789 | 2222 | 2025 | 2722 | 200000
[15 empty] | 3931 | 2224 | 2019 | 2772 | 50000
[15 empty] | 3761 | 2225 | 2025 | 2296 | 1350000
[15 empty] | 3762 | 2225 | 2025 | 2762 | 670000
[15 empty] | 3763 | 2226 | 2026 | 2296 | 2310000
[15 empty] | 3764 | 2226 | 2026 | 2762 | 1184000
[15 empty] | 3765 | 2227 | 2027 | 2296 | 1350000
[15 empty] | 3766 | 2227 | 2027 | 2762 | 650000
[15 empty] | 3768 | 2228 | 2025 | 2769 | 325000
[15 empty] | 3769 | 2228 | 2026 | 2769 | 655000
[15 empty] | 3770 | 2229 | 2027 | 2769 | 549000
[15 empty] | 3772 | 2229 | 2028 | 2769 | 1281000
[15 empty] | 3773 | 2230 | 2029 | 2769 | 382000
[15 empty] | 3774 | 2230 | 2030 | 2769 | 708000
[15 empty] | 3775 | 2231 | 2025 | 2742 | 474000
[15 empty] | 3778 | 2231 | 2026 | 2742 | 316000
[15 empty] | 3779 | 2232 | 2026 | 2742 | 108000
[15 empty] | 3780 | 2232 | 2027 | 2742 | 108000
[15 empty] | 3924 | 2233 | 2028 | 2762 | 16350000
[15 empty] | 3926 | 2234 | 2029 | 2762 | 9450000
[15 empty] | 3925 | 2235 | 2030 | 2762 | 6200000
[15 empty] | 3807 | 2236 | 2019 | 2721 | 235000
[15 empty] | 3894 | 2237 | 2021 | 2742 | 820000
[15 empty] | 3895 | 2237 | 2022 | 2742 | 1480000
[15 empty] | 3918 | 2238 | 2020 | 2336 | 70000
[15 empty] | 3917 | 2238 | 2020 | 2769 | 100000
[15 empty] | 3919 | 2239 | 2028 | 2769 | 4400000
[15 empty] | 3920 | 2240 | 2029 | 2769 | 2300000
[15 empty] | 3921 | 2241 | 2030 | 2769 | 1500000
[15 empty] | 3927 | 2242 | 2020 | 2769 | 115000
[15 empty] | 3928 | 2243 | 2021 | 2769 | 65000
[15 empty] | 3983 | 2244 | 2022 | 2763 | 1000000
[15 empty] | 4067 | 2246 | 2021 | 2742 | 1000000
[15 empty] | 4068 | 2246 | 2022 | 2742 | 710000
[15 empty] | 4069 | 2246 | 2022 | 2762 | 550000
[15 empty] | 4070 | 2247 | 2019 | 2743 | 40000